Toyota Insurance Services Philippines

Data Migration and Cutover Plan

Date - 10 October 2026

Version - 0.10 Draft

Prepared by – iorta TechNXT

TABLE OF CONTENTS

1.	Document Control	4

2.	Acronyms and Glossary	6

1.	Purpose, scope and audience	7

2.	Summary	7

3.	Requirements and contracted scope	8

4.	Migration principles	9

5.	Templates and the go-live kit	10

5.1	The Go-Live Data Workbench	10

5.2	Configuration workbook (masters and settings)	11

5.3	Migration workbook (open business)	12

5.4	Single-object templates and go-live imports	13

5.5	Promotion of configuration between environments	13

6.	Legacy mapping	14

6.1	Sources	14

6.2	Object mapping	14

6.3	Field-level rules carried by the kit	15

6.4	Legacy numbers and new numbers	15

7.	Data cleansing	16

8.	Validation	16

8.1	How validation works	16

8.2	Validation rules of the migration kit	17

8.3	Fix cycle	17

9.	Upload (load)	18

10.	Reconciliation	18

10.1	Control totals produced by the system	18

10.2	Reconciliation against the legacy records	19

10.3	Reconciliation report and sign-off	20

11.	Mock migrations	20

11.1	Plan	20

11.2	Tools used in the mocks	21

11.3	Environment for the dress rehearsal	21

11.4	Personal data in mock migrations	22

11.5	Evidence from the product rehearsal	22

12.	Production migration sequence	22

13.	Cutover runbook	23

13.1	Flow	23

13.2	Timetable	24

13.3	Business validation samples (step CO-8)	25

14.	Roles	25

15.	Timings	27

16.	Go / No-Go criteria	27

17.	Rollback	27

17.1	Rollback points	28

17.2	How each rollback works in the system	28

17.3	Corrections after go-live	28

17.4	Legacy records	28

18.	Hypercare	29

19.	Sign-off	29

20.	Evidence, audit and retention	29

20.1	Audit coverage of the migration	30

21.	Planned items register	31

22.	Open questions for TISPH	32

23.	Requirements traceability	33

Appendix A. File references	34

24.	Document Sign-Off	35

# Document Control

| Date | Version | Author & Business Unit Info | Reviewed By & Business Unit Info | Approved By & Business Unit Info | Change History |
| --- | --- | --- | --- | --- | --- |
| 10 October 2026 | 0.9 Draft | iorta TechNXT iorta TechNXT, Migration Lead (TISPH programme) | Pending review: Project Sponsor (to be named) (TISPH); Finance Head (to be named) (TISPH); Operations Unit Head (to be named) (TISPH); Head of IT (to be named) (TISPH); Data Protection Officer (to be named) (TISPH); Internal Audit representative (to be named) (TISPH); Delivery lead (iorta TechNXT); DevOps lead (iorta TechNXT) | Pending approval: TISPH Project Sponsor; TISPH Finance Head; TISPH Head of IT; iorta TechNXT Delivery | First issue for review. Describes the go-live data tooling as built at commit 58ad7702 and the migration and cutover plan built on it, with planned items and open questions. |
| 10 October 2026 | 0.9 Draft | iorta TechNXT | As above | As above | Review notes (architecture and audit review against the code). Corrected: row limit per sheet is 20,000 (IMPORT_MAX_ROWS), not unlimited; the transaction reset also removes the load history and the accounting calendar, so period set-up moves after the reset and evidence is exported before any reset; the reconciliation's BrokerVerse totals are cumulative over every record carrying the migration flag; the load notification goes to the loading administrator only; a planned-item dependency (M-03) corrected; BRD wording of NFR-07.4 and step references for SEC-05 and 5.13 corrected. Added: audit coverage and its gaps (no per-record before and after values for workbook loads, no second-person approval of a load or of the go-live lock), Settings rows that must not be promoted into PROD, pausing schedules and e-mail during cutover, the production marker and masking registration at go-live, request time-outs, opening balances not sent to SAP, the Azure reset procedure gap, vendor access removal at hypercare exit. Cutover steps renumbered CO-1 to CO-10 so they no longer clash with "C-1" (the day before cutover). Open questions Q16 to Q18 added. |
| 10 October 2026 | 0.9 Draft | iorta TechNXT | As above | As above | Go-live checks: sample data purged before go-live (section 12 step 1, criterion G7); the platform roles nobody holds inactive with tis-superid (G7). |
| 10 October 2026 | 0.10 Draft | iorta TechNXT | As above | As above | Controls brought to the Data Migration & Go-Live workspace as built on branch tisph/migration-workspace: sections 20 and 20.1 describe the built controls (second-person approval of every load, per-record audit with before and after values, two-person go-live lock over every migration import, reconciliation signed in the system, evidence pack, origin of migrated records on every business screen); Q17 answered and section 21 updated. The other sections still describe the baseline 58ad7702 and are brought up to date in the next issue. |
| 11 October 2026 | 0.10 Draft | iorta TechNXT | As above | As above | Documentation cleanup: Appendix A cites the go-live set-up and reset procedures and the Azure runbook instead of the retired deploy/README.md sections 6 to 8. |

Document information

| Item | Value |
| --- | --- |
| Document | BrokerVerse for TISPH: Data Migration and Cutover Plan |
| Client | Toyota Insurance Services Philippines (TISPH) |
| Prepared by | iorta TechNXT |
| Owner | iorta TechNXT, Migration Lead (TISPH programme) |
| Version | 0.10 Draft |
| Date | 10 October 2026 |
| Status | Draft for review |
| Classification | Confidential: TISPH and iorta TechNXT |
| Code baseline | TISPH-DEV line, integration branch tisph/integration6, commit 58ad7702 (Azure deployment work of tisph/azure-deploy merged) |
| Requirements baseline | TISPH Business Requirement Document v2.2 (signed): Module 25 (MIG-01), SEC-05, section 6.3 (non-functional), 5.13 (integrations), 5.14 (access, approval and audit), 9 (delivery approach) |

Reviewers

| Name / role | Organisation | Review focus |
| --- | --- | --- |
| Project Sponsor (to be named) | TISPH | Scope of the migration, cutover date, Go/No-Go body |
| Finance Head (to be named) | TISPH | Trial balance, receivables, reconciliation tolerances and sign-off |
| Operations Unit Head (to be named) | TISPH | Policy, client and claim data; business validation samples |
| Head of IT (to be named) | TISPH | Environments, backups, rollback, user provisioning |
| Data Protection Officer (to be named) | TISPH | Personal data in mock migrations and in the workbooks |
| Internal Audit representative (to be named) | TISPH | Evidence, controls, retention of migration records |
| Delivery lead | iorta TechNXT | Scope, planned items, dependencies |
| DevOps lead | iorta TechNXT | Snapshots, restore, reset and rollback procedures |

- A statement without a label describes the code, scripts or runbooks at the code baseline. Appendix A lists the files that support each section. Back-end paths are relative to backend/; other paths are relative to the repository root.

- Planned marks something designed but not built. Each planned item names the work package of the platform build plan (codes such as MU-A, PD-1a, PR-1b) or the remittance build phase (R1 to R4), and the TISPH decision it depends on. All planned items are listed in section 21.

- Not built marks a gap that has no work package yet. Each one points to an open question in section 22.

- Procedure marks a step of this plan that people perform; it is not a system function.

- BRD references are given by identifier and short phrase only. The signed BRD remains the authoritative text.

- "Cutover date" means the setting golive.cutover_date: the first day of live transactions in BrokerVerse. "Cutover minus one" (C-1) is the day before it; balances and open items are taken as at the close of C-1. "C-n business days" counts back from the cutover date. The steps of the cutover runbook are numbered CO-1 to CO-10 (section 13).

# Acronyms and Glossary

| Acronym / Term | Definition / Meaning |
| --- | --- |
| C-1 | The day before the cutover date; balances and open items are taken at its close |
| Cutover date | golive.cutover_date: the first day of live transactions in BrokerVerse |
| Dry run | A validation that runs the real importers inside a transaction that is rolled back |
| Go-live lock | golive.locked: once on, the migration kit and the transaction reset are refused |
| Held row | A row of an all-or-nothing sheet not loaded because other rows of the sheet are in error |
| Kit | One of the two go-live workbooks: configuration or migration |
| Load batch | One uploaded workbook with its rows, validation result and load result |
| Natural key | The business key a row is matched on (code, username, legacy number) |
| Open item | An unpaid premium bill of the legacy records loaded as a BrokerVerse receivable |
| Transaction reset | npm run reset:transactions: removes business records and keeps masters, configuration and users |

# Purpose, scope and audience

This plan describes how TISPH's data moves from its current records into BrokerVerse and how the business switches to BrokerVerse: the templates and the go-live kit that carry the data, how legacy data is mapped, cleansed, validated, uploaded and reconciled, how the mock migrations rehearse it, the cutover runbook with its roles and timings, the Go/No-Go decision, rollback, hypercare and sign-off.

It is written for three readers:

- TISPH IT and the business data owners, who extract, cleanse and sign off the data and run the cutover with iorta TechNXT.

- Auditors, who need to see that what was migrated is complete, accurate, authorised and evidenced.

- A future support team, who must understand, years later, where every migrated record came from and how to tell it apart from business entered in BrokerVerse.

It does not repeat the environment, release and backup design (see the Environment Strategy document of this pack) or the security design (see the Security document); it refers to them where the cutover depends on them.

# Summary

| Topic | As built at the code baseline |
| --- | --- |
| Tooling | The Go-Live Data Workbench (/api/data-load): two Excel workbooks, the configuration kit (44 sheets: everything needed for new business) and the migration kit (5 sheets: the open business at cutover) |
| User interface | API only. The screen was removed from the front end; the go-live scripts and an administrator with an API client call the API. A screen for the configuration workbook is Planned (MU-A) |
| Who may load | Role system-admin (System Administrator) only: permissions read:data-load and write:data-load (migration 0244). The TISPH IT AppSupport role tis-it-admin does not hold them |
| Validation | Every upload is a dry run of the real importers in load order, in one database transaction that is rolled back; errors per sheet, row and column; an errors workbook to fix and upload again |
| Load | One transaction, all rows or nothing (or "valid rows only"); serialised by an advisory lock; one audit entry per load (counts, not record values); an in-app notification to the loading administrator |
| Controls not built | No second-person approval of a load or of the go-live lock; no per-record before and after values in the audit trail for workbook loads. Compensating procedures in sections 14 and 20.1 |
| Reconciliation | Computed at every validation and load of the migration kit: counts and totals per sheet, trial balance debits = credits, premiums receivable control account = open items; downloadable as a workbook. Comparison with the legacy control figures, ageing, per-insurer totals, due-to-insurer and bank reconciliations are procedures on standard reports (section 10.2) |
| Migrated records | Keep their legacy numbers; flagged go-live-migration (or opening for open items) with the load batch id; post no journal, bill booking or commission accrual |
| Safety nets | Cutover date required before migration; rows dated on or after cutover refused; legacy numbers that a numbering series would issue again refused; go-live lock (golive.locked) refuses the migration kit and the transaction reset once switched on |
| Rehearsal | npm run rehearsal:golive rehearses the whole go-live between two running environments; its last recorded run passed 52 of 52 checks |
| Contracted scope | BRD MIG-01 (Phase 2): masters migration from Excel, "per the confirmed masters-only scope". Whether TISPH's open business is migrated with the migration kit is open (Q1) |

Diagram 1

| No. | Step | Next |
| --- | --- | --- |
| 1 | Legacy records, TISPH Excel files | step 2 (Extract at C-1, data owners) |
| 2 | Extract at C-1, data owners | step 3 (Map and cleanse, into the workbooks) |
| 3 | Map and cleanse, into the workbooks | step 4 (Upload = dry run, validation) |
| 4 | Upload = dry run, validation | errors: step 5 (Errors workbook, fix, upload again) no error: step 6 (Load, one transaction) |
| 5 | Errors workbook, fix, upload again | step 4 (Upload = dry run, validation) |
| 6 | Load, one transaction | step 7 (Reconciliation, control totals and checks) |
| 7 | Reconciliation, control totals and checks | step 8 (Business validation, samples on screen) |
| 8 | Business validation, samples on screen | step 9 (Go / No-Go) |
| 9 | Decision: Go / No-Go | Go: step 10 (golive.locked on, open for business) No-Go: step 11 (Rollback, section 17) |
| 10 | golive.locked on, open for business | End |
| 11 | Rollback, section 17 | End |

Only the boxes "Upload = dry run validation", "Errors workbook", "Load" and "Reconciliation (control totals and checks)" are system functions. Extraction, mapping, cleansing, business validation and the Go/No-Go are procedures performed by people (section 13).

# Requirements and contracted scope

| BRD reference | Short phrase | How this plan addresses it |
| --- | --- | --- |
| MIG-01 (Module 25), Phase 2 | "Migration of existing policy records and master data from Excel", "product-wise migration templates", "document file-naming convention", "sample dataset" | Masters: configuration kit (section 5.2). Policy records: migration kit (section 5.3), whose use for TISPH is open (Q1). Product-wise templates and the document file-naming convention are Not built (Q3). The sample dataset is the entry criterion of Mock 1 (section 11) |
| Customisation table, MIG-01 | "Masters migration tooling and loads (per the confirmed masters-only scope)" | The configuration kit carries the masters; section 5.2 lists them |
| SEC-05 | "licensed user list (20 users) and their role mapping loaded at cutover", "demo accounts disabled" | Users sheet of the configuration kit (section 5.2); Microsoft Entra ID sign-in, demo accounts and password sign-in in section 13.2 (readiness at C-5 business days) and criterion G7 |
| NFR-07.4 | Batch notification logs "identify issues and allow continuation to next record" | Each row runs in its own savepoint; errors carry sheet, row, column and message; "load valid rows only" (section 9) |
| NFR-07.5 | Batch processing time, "TBD c/o IORTA" | Measured in the mock migrations (section 15) |
| NFR-08 | Environment-specific configuration "consistency across" environments | Configuration promotion with the configuration workbook and the environment comparison (section 5.5) |
| NFR-06.2, NFR-06.3 | RPO 1 hour, RTO 4 hours | Restore points used by rollback (section 17); backup design in the Environment Strategy document |
| NFR-11, NFR-11.1, NFR-11.2, NFR-11.3 | Retention of backups, contracts and logs | Retention of migration evidence (section 20); legacy records kept read-only (section 17.4) |
| NFR-17 | Non-public personal information | Personal data in workbooks and mock environments (section 11.4) |
| NFR-5.3 | Output controls: "reconciliation, business owner review" | System control totals (section 10.1), legacy reconciliation and business validation signed by the data owners (sections 10.2, 13.3, 19) |
| Section 5.14 | Audit trail with actor, timestamp, before and after values and remark | Partly met for migration. Every validation, load, export of current data and comparison has an audit entry with actor and time; a workbook load does not write before and after values per record (section 20.1) |
| Section 5.13 | Interfaces are file-based or e-mail-based | Interfaces, schedules and e-mail are switched on at step CO-10 (section 13); migration itself does not use them. Opening balances are not journals and are not sent in the SAP GL file (Q5) |
| Section 9 | Delivery from sign-off to go-live; traceability | Mock migrations and cutover sit at the end of the delivery sequence (section 11 to 13); traceability in section 23 |

Scope statement. The signed BRD places data migration in Phase 2 with a masters-only scope, and states that the estimate firms up once the source extracts have been profiled. The product nevertheless contains a complete migration kit for open business (clients, in-force policies, open premium receivables, open claims, GL opening balances). This plan therefore describes both, and treats the open-business migration as an option for TISPH to confirm or decline (Q1). If declined, sections 6 to 10 apply to the configuration kit only, and TISPH runs off its legacy open business outside BrokerVerse.

# Migration principles

| # | Principle | Where it is enforced |
| --- | --- | --- |
| P1 | Open positions, not history. BrokerVerse receives what is open at cutover; expired, cancelled and lapsed policies, settled claims, paid bills and journals before cutover stay in the legacy records, kept read-only | Migration kit: expiry on or after cutover, claim status registered or in-review, open balance greater than zero (section 8.2) |
| P2 | One cutover date. Balances and open items are taken as at the close of C-1; every BrokerVerse transaction is dated on or after the cutover date | golive.cutover_date; rows dated on or after it refused; opening balances as at C-1 |
| P3 | Legacy numbers are kept. Client codes, policy numbers, claim numbers and bill numbers of the legacy records stay the same | Natural keys of the migration kit; numbering collision checks (section 6.4) |
| P4 | Load again without duplicates. A corrected workbook can be loaded again; equal rows are reported unchanged | Natural keys; "unchanged" comparison with the stored data |
| P5 | The money comes from the opening balances. Migration posts no journal, bill booking or commission accrual | Migration importers (section 5.3) |
| P6 | Reconcile everything. Counts and totals of each load are compared with control figures produced from the legacy records before the load | Reconciliation (section 10) |
| P7 | Rehearse. The full sequence runs at least twice before the production cutover | Mock migrations (section 11) |
| P8 | TISPH owns the data. TISPH data owners extract, cleanse and sign off; iorta TechNXT maps, loads and reports | Roles (section 14) Procedure |

# Templates and the go-live kit

## The Go-Live Data Workbench

The workbench is the back-end module data-load. It offers two kits, each one Excel workbook:

| Kit | File | Content |
| --- | --- | --- |
| configuration | GoLive_Configuration_Workbook.xlsx | Everything needed to run new business (section 5.2) |
| migration | GoLive_Migration_Workbook.xlsx | The open business of the legacy records at cutover (section 5.3) |

Every workbook has an Instructions sheet (load order, rules, the cutover date rule, new versus migrated data, what is entered on screen, every column), a Lists sheet (allowed values that the drop-downs of the object sheets point to) and one sheet per object in load order. On each object sheet row 1 holds the headers (required columns end with " *"), row 2 a sample row whose first cell starts with SAMPLE and is never loaded, and data starts on row 3. Cells are formatted as text so codes and dates stay as typed; dates may be YYYY-MM-DD or Excel date serial numbers; amounts may carry thousands separators but no currency sign.

API. The module has no screen at the baseline (the former "Go-Live Data Load" screen was removed from the front end). It is used through these calls, all under /api/data-load:

| Call | Purpose |
| --- | --- |
| GET /kits | The two kits with their sheets in load order, columns and natural keys; the cutover date and the go-live lock |
| GET /kits/:kit/template | Blank workbook; with prefill=true, the current data of this environment (audited as export-current-data) |
| POST /batches | Upload a workbook (multipart file, field kit): creates a load batch and validates it as a dry run |
| GET /batches, GET /batches/:id | Load history; one batch with its result per sheet and its errors |
| POST /batches/:id/validate | Validate again (for example after the cutover date changed) |
| GET /batches/:id/errors | The rows in error as a workbook in the kit layout with an Errors column |
| POST /batches/:id/load | Load a validated batch (option validRowsOnly) |
| GET /batches/:id/reconciliation | Reconciliation workbook of a migration batch |
| POST /compare and GET /compare... | Compare a configuration export with this environment, or two exports with each other; never loads |

The operator signs in as a System Administrator and calls the API with an API client; the exported API collection is backend/docs/api/BrokerVerse.postman_collection.json and the OpenAPI description backend/docs/api/openapi.json. Planned (M-01): a screen for the configuration workbook ("Setup Workbook") and upload with template on every master screen (work package MU-A; TISPH decisions M1, M2, M5). No screen is planned for the migration kit; whether one is wanted is open (Q15).

Batch lifecycle.

Diagram 2

| From state | Event or action | To state |
| --- | --- | --- |
| Start | upload, validation finds errors | failed |
| Start | upload, validation finds no error | validated |
| failed | validate again after a fix (same rows) | validated |
| validated | validate again finds errors | failed |
| validated | load (one transaction) | loaded |
| failed | load with validRowsOnly | loaded |
| validated | load stopped (data changed since validation), nothing saved | failed |
| loaded | - | End |

A batch keeps the rows read from the workbook (data_load_rows), not the file itself; a load re-runs the importers on those rows. A corrected file is uploaded as a new batch.

## Configuration workbook (masters and settings)

The configuration kit holds 44 sheets in dependency order. Every sheet upserts on its natural key, so a corrected workbook updates and never duplicates.

| Group | Sheets, in load order | Natural key |
| --- | --- | --- |
| Organisation and settings | Company; Settings (editable settings of Master > Configuration, including golive.cutover_date) | Company code; setting key |
| Location | Countries, Regions, Provinces, Cities and Municipalities, Barangays | First unique key of each master |
| People | Branches, Departments, Hierarchy, Designations, Users | Code; username |
| Finance | Currencies, Exchange Rates, Chart of Accounts, Banks, Bank Accounts, Signatories, Transaction Codes, Write-off Reasons | Code; account code |
| Insurance | Insurers, Lines of Business, Products, Policy Types, Covers, Vehicle Brands, Vehicle Models, Vehicle Variants, Vehicles | Code (brand + model for models) |
| Other masters | Suppliers, Asset Classes, Short-Period Rates, Cancellation Reasons, Claim Document Checklist, Repair Shops, Lead Sources, Reason Codes | Code |
| Rules | Commission Rates, Premium Taxes, LGU Rates, Authority Limits, Numbering | Insurer + product + line + policy type + effective from; code; transaction type + role; series code |
| Interfaces | Payee Bank Accounts, COC Series | Payee type + payee; series |

Rules that matter at cutover:

- Users. Passwords are never in a workbook. A new user receives a temporary password returned once by the load (response marked Cache-Control: no-store, never stored in the batch), to be changed at first sign-in. A load cannot change the loading administrator's own account. Segregation-of-duties rules apply as on the User screen.

- Authority limits loaded by the workbook are proposals that a second administrator approves (maker-checker).

- Numbering. Next Number is the next sequence number of the current period: the last legacy number plus one. It cannot go below a number already issued, and is also kept as the period start, so the transaction reset after a smoke test restarts the series there.

- Settings. Only editable settings of Master > Configuration that no other screen owns and that are not under second-user approval are exported and loaded. golive.locked is never exported or loaded; secrets are never in settings. golive.cutover_date and the environment marker system.environment are exported and loaded, so a workbook promoted from another environment carries that environment's values (section 5.5). A setting changed by the workbook is recorded only in the load's single audit entry (counts) and in the stored batch rows, not as a separate settings audit entry with before and after values; a change on Master > Configuration is audited with before and after values.

- Not in the workbook (entered on screen): roles and permissions, segregation-of-duties rules, approval of authority limits, tax codes, account determination and posting rules, statement and bank file formats, product templates and tariffs, package bundles, payment gateway and interface credentials, branding, schedules, fiscal years and periods, remittance masters, incentive programmes, referrer accounts. The full list is on the Instructions sheet.

## Migration workbook (open business)

| # | Sheet | Natural key | Main columns | What a row creates |
| --- | --- | --- | --- | --- |
| 1 | Clients | Client Code | Client Type (individual / corporate), names, e-mail, phone, TIN, birth date, Philippine address (barangay, city / municipality, province, region, ZIP) | A client with source = 'go-live-migration' and the load batch id |
| 2 | Policies | Policy Number | Client Code, Insurer, Product, Insured Name, Inception, Expiry and Issue Dates, Sum Insured, Net and Gross Premium, Commission Rate, Billing Mode, Payment Status, Plate Number, Account Executive | An active in-force policy (insurer at 100%) through the policy service in migration mode: no bill, no booking journal, no commission accrual; premium taxes derived; doc.source = 'go-live-migration' |
| 3 | Open Items | Policy Number + Bill Reference | Due Date, Original Amount, Open Balance | An open premium bill (receivable source = 'opening', go_live_date = cutover) keeping the legacy bill number; ages and is collected with normal official receipts; no journal |
| 4 | Open Claims | Claim Number | Policy Number, Loss and Reported Dates, Status, Loss Type, Description, Outstanding Estimate, Insurer Claim Number, Handler | A claim (registered or in-review) with details.source = 'go-live-migration', a claim history line and a due date from claims.sla_days; no acknowledgement e-mail or settlement journal |
| 5 | Opening Balances | Account Code | Account Name (reference only), Debit, Credit | GL opening balances of the fiscal year containing the cutover date, source_run = 'go-live:<cutover>'; no journal |

What the migration kit does not carry, and where it goes:

| Position | Treatment in BrokerVerse |
| --- | --- |
| Premium due to insurers; commission due to referrers and agents | Part of the GL opening balances; paid with payment vouchers (Accounts > Disbursement) |
| Commission receivable from insurers on direct-bill business | Part of the opening balance of Commission Receivable - Insurers; cleared by journal voucher when the insurer pays |
| Co-insured in-force policies | Loaded with the lead insurer at 100%; participants added on the policy screen |
| Expired, cancelled and lapsed policies; settled claims; paid bills; journals before cutover | Not migrated; kept in the legacy records |
| Leads and quotations in progress | Their own bulk uploads (Prospects, Quotations) |
| Unreconciled bank items | Stay on the legacy bank reconciliation; BrokerVerse reconciles each bank account from its reconcile-from date |
| Documents and images of the legacy records | Attached on the policy or claim screen when needed; bulk document migration is Not built (Q3) |
| Opening remittances to insurers | Planned (M-07): off-cycle remittances created from a policy list with purpose "Go-live opening" (remittance phase R2; TISPH question Q14 of the remittance specification) |

## Single-object templates and go-live imports

Besides the two kits, the platform has one upload template per object in docs/package/05_Delivery/Upload_Templates (generated by scripts/build-upload-templates.js; each with Data, Columns and Instructions sheets) and three single-object go-live imports that the migration kit supersedes but which remain available:

| Import | Route | Permission | Note |
| --- | --- | --- | --- |
| In-force policies, go-live mode | POST /api/policies/bulk-upload with mode=go-live (Policy screen, Bulk Upload) | write:policies | Each row creates a client and a policy; no bill, journal or commission; one audit entry per policy (go-live-migration) |
| Open premium items | POST /api/receipts/opening-items/import with goLiveDate (Collections, Import open items) | write:receipts | Same importer as the Open Items sheet |
| GL opening balances | POST /api/period-end/opening-balances/import (Period Management, Import opening balances) | write:period-end | Same importer as the Opening Balances sheet; loading the same date again replaces the set; audited as go-live-import |

This plan uses the kits, because they validate all sheets together, keep legacy client codes and give the reconciliation.

Control gap. The go-live lock does not cover these three imports: they stay open after go-live to every holder of the permission, which in the TISPH role set includes sales and operations roles (write:policies), the CCD roles (write:receipts) and tis-finance (write:period-end). After go-live a user could add policies flagged as migrated without a bill, add opening open items, or replace the opening balances of the cutover date (the posted journal check looks only at journals dated before the cutover). Blocking them under golive.locked is Not built (Q17). Until then: their use after CO-10 needs the written agreement of the Finance Head, and the weekly hypercare review and the monthly audit review list the audit actions go-live-migration and go-live-import and opening open items created after the cutover Procedure (sections 18, 20.1).

## Promotion of configuration between environments

The configuration workbook downloaded with current data (prefill=true) from one environment loads into the next (DEV, SIT, UAT, then PROD): rows equal to the target are skipped, differences update it, missing records are created. The environment comparison (POST /api/data-load/compare, or npm run compare:environments between two running APIs) proves the two environments are mirrored apart from environment-specific values (cutover date, addresses, e-mail senders, gateway modes, environment names, numbering counters unless asked); exit code 0 means mirrored.

- Planned (M-04): the environment marker system.environment, the golive.* settings and environment-bound interface settings are neither exported nor loaded by the workbook (work package W0-4). Until then, before a workbook exported from UAT is loaded into PROD, the operator deletes from its Settings sheet the rows system.environment, golive.cutover_date and any URL, host, folder or interface-mode setting, and the validation result is checked for unexpected "changed" settings Procedure. Loading UAT's system.environment into PROD would mark PROD as uat, and the masking tool refuses only a database marked production (section 11.4). The environment comparison reports these settings as environment-specific; it does not stop them being loaded.

- Planned (M-06): signed, approved Environment Promotion packages replace workbook promotion for configuration (work packages PR-1a, PR-1b; TISPH decisions E1 to E15).

# Legacy mapping

## Sources

The BRD names Excel as the legacy source (MIG-01). The exact files, their owners and volumes are not yet known; MIG-01 asks for a sample dataset to assess feasibility. Mapping starts from that sample (Q2). Procedure: for each source file the migration lead records, in a mapping register kept with the project records:

| Field of the register | Content |
| --- | --- |
| Source | File name, sheet, owner, extraction date, row count |
| Target | Kit, sheet, column |
| Rule | Copy, translate (code table), derive, default, or not migrated (with reason) |
| Code table | Legacy value to BrokerVerse value (insurer, product, status, client type, branch, user) |
| Quality checks | Which cleansing rules of section 7 apply |
| Sign-off | Data owner, date |

## Object mapping

| Legacy object | Target | Key decision to record |
| --- | --- | --- |
| Company, branches, departments, designations | Configuration kit, organisation sheets | TISPH branch and department codes |
| Licensed users (20, SEC-05) and their roles | Users sheet; roles from the TISPH role set (for example tis-finance, tis-ops-officer, tis-it-admin) | One username per person; e-mail = Microsoft 365 address for Entra ID sign-in |
| Insurers, products, lines, covers | Insurance sheets; TISPH lists already seeded are kept | Legacy insurer and product names to BrokerVerse codes (Lists sheet values) |
| Commission rates | Commission Rates sheet | Rate as a fraction (0.20 for 20%); line of business must be a code of the Line of Business master |
| Chart of accounts | Chart of Accounts sheet | Mapping to TISPH's account codes and to SAP accounts used in the GL file (Q5) |
| Document series | Numbering sheet | Last legacy number per series (Q8) |
| Clients | Clients sheet (migration kit) | Legacy client number kept as Client Code; one row per distinct client |
| In-force policies | Policies sheet | Legacy policy number kept; insurer and product codes; billing mode; account executive username |
| Unpaid premium | Open Items sheet | Legacy bill / debit note number as Bill Reference; open balance at C-1 |
| Open claims | Open Claims sheet | Legacy claim number kept; outstanding estimate at C-1 |
| Trial balance at C-1 | Opening Balances sheet | Account mapping; one line per account; debit or credit |

## Field-level rules carried by the kit

| Rule | Behaviour |
| --- | --- |
| Client type | individual needs First and Last Name; corporate needs Company Name |
| Region | Filled from the province when empty; country defaults to Philippines |
| Net premium | The gross premium when empty; cannot exceed the gross premium |
| Commission rate | The insurer's default rate when empty, else setting commission.default_rate |
| Billing mode | broker or direct; the insurer default when empty |
| Payment status | One of the configured statuses; Completed when empty |
| Insured name | The client name when empty |
| Claim status | registered when empty; only registered or in-review accepted |
| Reported date | The loss date when empty |
| Account executive, handler | Username of an existing user |

TISPH-specific policy attributes (distribution channel, branch, business type, subline and any TFS loan or dealer reference) have no column on the Policies sheet: Not built (Q4).

## Legacy numbers and new numbers

Migrated records keep their legacy numbers; new business takes the next number of its Document Numbering series. Both kits refuse a collision:

- the configuration kit refuses a series' Next Number that would issue a number a migrated record already has;

- the migration kit refuses a legacy client, policy, bill or claim number that has the format of a series in the current period at or above its next number.

Procedure: before Mock 1, compare the legacy number formats with the TISPH numbering masks (BRD 5.12: product type, subline type, business type, branch and sequence) and set each Next Number above the legacy range. An open item whose bill number another bill already carries (one debit note over several policies) receives the next invoice number and keeps the legacy number as its reference, which is shown and searchable.

# Data cleansing

Cleansing is done by the TISPH data owners in the source files or in the workbooks, never by changing records in the database Procedure. The table lists the checks to run before each upload; most mirror a rule the validation enforces (section 8), so cleansing early avoids repeated error cycles.

| # | Check | Objects | Enforced by validation |
| --- | --- | --- | --- |
| CL-01 | Required columns filled | All | Yes |
| CL-02 | No duplicate natural keys in a sheet | All | Yes ("Same key as row n") |
| CL-03 | One client per legacy client number; merge duplicate persons under one code before loading | Clients | No: two codes for the same person load as two clients |
| CL-04 | E-mail format valid; TIN in the Philippine format; mobile numbers complete | Clients | E-mail only |
| CL-05 | Dates real and in YYYY-MM-DD; birth, issue, loss and reported dates before cutover | Clients, Policies, Claims | Yes |
| CL-06 | In force at cutover: expiry on or after the cutover date, after inception | Policies | Yes |
| CL-07 | Insurer and product names translated to master codes | Policies | Yes (must exist) |
| CL-08 | Gross premium above zero; net not above gross; commission rate between 0 and 1 | Policies | Yes |
| CL-09 | Open balance above zero and not above the original amount; no item on a direct-billed policy | Open Items | Yes |
| CL-10 | Loss date inside the policy period; reported not before loss | Claims | Yes |
| CL-11 | Trial balance balances; each account in the chart and active; one line per account | Opening Balances | Yes |
| CL-12 | Premiums receivable control account at C-1 equals the sum of open items, or the difference is listed | Open Items, Opening Balances | Reported by the reconciliation check, not refused |
| CL-13 | Usernames of account executives and handlers exist | Policies, Claims | Yes |
| CL-14 | Personal data only where needed; no extra columns with personal data in the workbook | Clients | No (unknown columns are ignored) |

Planned (M-02): a pre-flight report of duplicate business keys in the masters of every environment, and case-insensitive unique keys on the masters (work package REG-1, migration 0411).

# Validation

## How validation works

An upload creates a load batch and runs every sheet through its real importer, in load order, inside one database transaction that is rolled back at the end. Cross-sheet references therefore validate as they will load: a policy may refer to a client and an insurer added by the same workbook. Each row runs in its own savepoint, so a failing row is undone alone and the next rows carry on (NFR-07.4). A transaction-level advisory lock serialises validations and loads. Sequence counters advanced during the dry run are rolled back with it, and the settings caches are cleared after it.

The result per sheet gives rows read, valid, in error, held, and the actions (new, changed, unchanged, for approval, ignored). Each error has its sheet, row number, column and message. The migration kit's reconciliation is computed in the dry run too, so control totals can be compared before anything is saved.

## Validation rules of the migration kit

| Sheet | The row is refused when |
| --- | --- |
| Any | A required column is empty; the key repeats a key of an earlier row; the cutover date is not set; golive.locked is on |
| Clients | Client type is not individual or corporate; names missing for the type; e-mail malformed; birth date on or after cutover; the client code belongs to a client created in BrokerVerse; the code falls in the range the client series still has to issue |
| Policies | Policy number already exists; client, insurer or product not found; issue date on or after cutover; expiry not after inception or before cutover; gross premium not above zero; net above gross; commission rate outside 0 to 1; billing mode or payment status not allowed; account executive unknown; number in the policy series' range |
| Open Items | Policy not in BrokerVerse or direct-billed; due date missing; open balance not above zero; original amount below open balance; bill already loaded for another cutover date; bill number in the invoice series' range |
| Open Claims | Claim number exists; status not registered or in-review; policy not found; loss date outside the policy period, or loss or reported date on or after cutover; reported before loss; handler unknown; number in the claim series' range |
| Opening Balances (whole sheet) | Any account unknown or inactive; a line with both debit and credit or a negative amount; an account twice; debits not equal to credits; the fiscal year not open or already holding balances carried forward by a year-end close; balances already loaded for another cutover date; journals posted in the fiscal year before the cutover date |

The Opening Balances sheet loads all or nothing: when a row is in error, that row shows its error, the other rows are counted as held and one message explains the sheet. A row with neither debit nor credit is accepted and ignored. Loading opening balances again for the same cutover date replaces the earlier set as a whole. A bill already loaded for the same cutover date is reported unchanged, so a corrected workbook can be loaded again.

The opening balances go into the fiscal year that contains the cutover date (the year is created if the calendar does not reach it). When the cutover date is not the first day of the fiscal year, the trial balance at C-1 includes the year-to-date income and expense accounts, and they are loaded as they are; the year-end close of that year then includes them. Whether to align the cutover with a month or year start is open (Q6).

## Fix cycle

Diagram 3

| Step | From | To | Message |
| --- | --- | --- | --- |
| 1 | Migration lead | Workbench API | POST /batches (workbook, kit) |
| 2 | Workbench API | Migration lead | batch, result per sheet, errors (reply) |
|  | If: errors |  |  |
| 3 | Migration lead | Workbench API | GET /batches/:id/errors |
| 4 | Workbench API | Migration lead | errors workbook (rows in error + Errors column) (reply) |
| 5 | Migration lead | Data owner | errors workbook |
| 6 | Data owner | Migration lead | corrected rows (or whole corrected workbook) (reply) |
| 7 | Migration lead | Workbench API | POST /batches (corrected workbook) |
|  | Otherwise: no error |  |  |
| 8 | Migration lead | Workbench API | POST /batches/:id/load |
| 9 | Workbench API | Migration lead | loaded counts, reconciliation (reply) |
|  | End of condition |  |  |

The errors workbook has the same layout as the kit; for an all-or-nothing sheet it contains all rows of the sheet, with the sheet message on the first row, because that sheet is uploaded again as a whole.

# Upload (load)

A load is accepted only when the batch is not already loaded, has been validated, and its latest validation has no error (or the operator asks for valid rows only, which skips the rows in error and keeps them in the errors workbook for a later batch). For the migration kit the cutover date must be the same as at validation; if it changed, the batch must be validated again.

The load re-runs the importers on the stored rows in one transaction under the same advisory lock. If any row fails at load time (the data changed since validation), nothing is saved, the new errors are recorded on the batch and the load is refused. On success the batch records who loaded it, when, the counts per sheet and the reconciliation; the load is written to the audit trail (entity data_load_batch, action load, with the counts but not the record values) and the loading administrator receives an in-app notification.

For the migration cutover this plan loads the migration workbook without "valid rows only": a partial migration would break the reconciliation. "Valid rows only" is reserved for the configuration workbook during build Procedure.

Request time-outs. Upload, validation and load run inside one HTTP request. Through the public address the request passes Azure Front Door (origin response time-out 120 seconds) and the web container's /api proxy, which sets no read time-out and so uses the nginx default of 60 seconds. A load that runs longer returns a gateway error to the client while the server transaction carries on and commits or rolls back on its own. Procedure: after a time-out, read GET /api/data-load/batches/:id and act on its status before trying again; a second load of a loaded batch is refused ("already loaded"). If Mock 2 shows a load near 60 seconds, the production load is run from inside the environment against the API container's own port, which avoids both proxies (Q16).

# Reconciliation

## Control totals produced by the system

Every validation and load of the migration kit computes, inside the transaction, the totals of the workbook and of BrokerVerse after the load (all records carrying the migration flag), and two checks:

| Sheet | Workbook totals | BrokerVerse totals |
| --- | --- | --- |
| Clients | Rows | Count; corporate and individual |
| Policies | Rows; gross premium; net premium; sum insured | Count; gross premium; net premium; sum insured; policies expiring within 90 days of cutover |
| Open Items | Rows; original amount; open balance | Count; original amount; open balance (for the cutover date) |
| Open Claims | Rows; outstanding estimate | Count; outstanding estimate |
| Opening Balances | Rows; debit; credit; zero-balance rows | Accounts loaded; debit; credit |

| Check | Rule | Result |
| --- | --- | --- |
| Trial balance | Total debits = total credits of the opening balances | Agrees or Difference (tolerance 0.005) |
| Receivables control | Opening balance of the premiums receivable control account (setting accounting.account.premium_receivable, seeded 1202001) = total open balance of the open items | Agrees or Difference |

The reconciliation workbook (GET /api/data-load/batches/:id/reconciliation) has a Summary sheet and a Checks sheet.

How to read it:

- Workbook totals count only the rows of the batch that are not in error.

- BrokerVerse totals are not limited to the batch. Clients, policies and claims are every record carrying go-live-migration, including records of earlier batches and policies loaded by the single-object go-live import (section 5.4); open items and opening balances are those of the current cutover date. After several loads into the same environment, the BrokerVerse totals are cumulative. Procedure: in PROD the final migration is a single batch loaded into an environment holding no migrated records (the reset dry run shows no client, policy, receivable or claim row), so the two columns must agree.

- A Difference on the receivables control check is not a load error. In the product rehearsal the control account exceeded the open items by 790.40, the GL balance of a policy that was not migrated (section 11.5). Each difference is explained and accepted by the Finance Head (criterion G3).

## Reconciliation against the legacy records

Procedure. Before each load the data owners produce control figures from the legacy records, signed by the Finance Head for financial objects. After the load the same figures are read from BrokerVerse and compared.

| Object | Legacy control figure | BrokerVerse source | Tolerance |
| --- | --- | --- | --- |
| Masters | Count per master | Configuration batch counts; environment comparison | Exact |
| Users | Licensed user list (20) with roles | Users sheet counts; user list | Exact |
| Clients | Distinct clients | Reconciliation: Clients | Exact |
| In-force policies | Count; count per insurer and per line; sum insured; gross and net premium | Reconciliation: Policies; production reports filtered on source go-live-migration (GET /api/policies?source=go-live-migration) | Exact |
| Open premium receivables | Count; open balance; balance per ageing bucket and per insurer | Reconciliation: Open Items; receivables ageing report | Exact |
| Open claims | Count; outstanding estimate | Reconciliation: Open Claims | Exact |
| Trial balance at C-1 | Debit and credit per account; totals | Reconciliation: Opening Balances; trial balance report (GET /api/accounting/trial-balance) | Exact |
| Premiums receivable | GL control account = open items | Reconciliation check | Exact, or each difference listed and accepted by the Finance Head |
| Due to insurers | GL balance per insurer = insurer statements less items in dispute | Trial balance; payables reports | Exact, or reconciled list |
| Bank accounts | GL cash = bank balance less legacy outstanding items | Trial balance; bank statements | Exact |

Ageing per bucket, totals per insurer and per line, due-to-insurer and bank reconciliations are produced from the standard reports; the workbench does not compute them.

## Reconciliation report and sign-off

Procedure. Each load produces a reconciliation report: the legacy control figures, the BrokerVerse figures (the reconciliation workbook plus report extracts), each difference with its explanation and action, and the sign-off of the data owner and, for financial objects, the Finance Head. The report is filed with the batch number.

# Mock migrations

## Plan

Two mock migrations and a dress rehearsal precede the production cutover. Each runs the full sequence of section 12 on an environment reset to reference data plus the agreed configuration.

| Run | Environment | Data | Purpose | Exit criteria |
| --- | --- | --- | --- | --- |
| Mock 1 | UAT | Sample dataset (MIG-01), then a full extract at a recent month-end | Prove the mapping and the templates; find data-quality issues; first timings | Every sheet uploads; all errors listed, assigned and explained; mapping register signed for the sample |
| Mock 2 | UAT | Fresh full extract after cleansing | Prove cleansing; reconcile; measure every step | No validation error at the final upload; every control figure of section 10 reconciles; business validation of section 13.3 (step CO-8) passes |
| Dress rehearsal (Mock 3) | PRE-PROD (Planned, M-05) or, until it exists, PROD before go-live (section 11.3) | Fresh extract with the legacy freeze simulated | Run the cutover runbook to the clock with the cutover team | Completed inside the cutover window; reconciliation signed; Go/No-Go rehearsed; rollback step RB-2 rehearsed |

A further mock is added when Mock 2 does not meet its exit criteria Procedure.

## Tools used in the mocks

- Go-Live Data Workbench (section 5) for every load.

- Transaction reset (npm run reset:transactions): removes all business records of a mock or smoke test and keeps every master, configuration setting and user; restarts document series at the next numbers set by the Numbering sheet; removes the go-live opening balances unless --keep-opening-balances. Dry run by default, --execute to delete, one transaction, requires CONFIRM_RESET=yes, refuses while golive.locked is on, and refuses to run when a table is not classified. It also removes the load history (data_load_batches, data_load_rows, data_load_comparisons) and the accounting calendar (fiscal years and periods; with --keep-opening-balances the years holding opening balances are kept and reopened). The audit trail is kept unless --purge-audit is given; the reset records itself either way. Procedure: --purge-audit is never used in UAT mocks or in PROD, and the batch, errors and reconciliation workbooks of a mock are downloaded before the reset that follows it.

- Running the reset on Azure. The reset must run with the API instances stopped, because it locks the tables. The API image contains the scripts (COPY scripts), but the Azure runbook (deploy/AZURE.md) gives no command for running the reset while the API container app is stopped: az containerapp exec needs a running API replica, and the Container Apps job of the environment runs only the database migrations. The exact procedure (for example a one-off job execution with the reset command, or the API scaled to one replica with ingress closed) is to be written and rehearsed by the DevOps lead in Mock 1 Procedure (Q16).

- Go-live rehearsal (npm run rehearsal:golive): rehearses the go-live between two running BrokerVerse environments (SOURCE plays the legacy system, TARGET the environment going live): configuration promoted with deliberate errors, smoke test and reset, migration workbook filled from SOURCE's open book at C-1 with injected errors, reconciliation against SOURCE, reload without duplicates, new and migrated business side by side, go-live lock. It requires CONFIRM_RESET=yes and must never point at a live database. It proves the tooling, not TISPH's data: TISPH's legacy source is not a BrokerVerse database, so the mocks use the workbench directly.

- Environment comparison (npm run compare:environments) after each configuration promotion.

## Environment for the dress rehearsal

PRE-PROD is not defined on Azure at the baseline (Planned, M-05: environment work item P-01 of the Environment Strategy document; TISPH decision E1). Before go-live, production holds no live book and golive.locked is off, so the dress rehearsal can run in PROD itself and be removed with the transaction reset afterwards, keeping the configuration that will go live. A point-in-time restore point is noted before the rehearsal (section 17.2). The reset that follows the rehearsal also removes the rehearsal's load history and accounting calendar (section 11.2), so the rehearsal's evidence is exported first and the fiscal year set-up of step 7 in section 12 is done after it.

## Personal data in mock migrations

Mock 1 and Mock 2 load real client data from the legacy records into UAT. Procedure: the TISPH Data Protection Officer approves this, with UAT access restricted to the named migration team, or the data owners pseudonymise the extract before loading (Q9). The masking command npm run mask:data masks a copy of a production database; it can be run on UAT after a mock (it refuses a database marked production, and a database without an environment marker whose go-live lock is on). A new database is marked dev while its go-live lock is off (migration 0249), so PROD is marked production by the System Administrator when it is built (section 12, step 1) and registered with npm run mask:data -- --register-production at go-live (step CO-10).

The current-data download of the migration workbook contains client personal data, including the TIN in clear, for a holder of read:data-load (System Administrator), because /api/data-load is on the default list of paths answered without masking. Planned (M-03): current-data workbooks masked unless the user holds view:pii, and /api/data-load removed from the exempt list (work packages PD-1a and MU-A, migration 0430). Workbooks are kept on the project's restricted storage and deleted after sign-off (section 20) Procedure.

## Evidence from the product rehearsal

The last recorded run of npm run rehearsal:golive (docs/e2e/GOLIVE_REHEARSAL_RUN.md) passed 52 of 52 checks in 11 seconds against two local environments: 2,820 configuration rows promoted (three deliberate errors found and fixed), 171 migration rows (60 clients, 68 policies, 24 open items, 2 open claims, 17 trial balance lines) loaded after three injected errors were reported and fixed, 11 control totals agreeing with the source, a reload with every row unchanged, the migrated renewals and receipts working, and the go-live lock refusing the migration kit and the reset. These figures describe synthetic test data, not TISPH volumes.

# Production migration sequence

The production migration follows the dependency order of the kits. Steps 1 to 6 happen in the weeks before cutover; steps 7 to 12 are the cutover itself (section 13). The order matters: the transaction reset (step 5) removes the accounting calendar and the load history, so the fiscal year set-up comes after it.

| # | Step | Kit or tool | Precondition |
| --- | --- | --- | --- |
| 1 | Production deployed with reference data only (SEED_SAMPLE_DATA=false in the Azure configuration; an environment once seeded with sample data is cleared with npm run purge:sample and checked empty of demo records), backups running, a restore tested (DR drill of deploy/AZURE.md section 12); system.environment set to production (Master > Configuration, group System) Procedure | Deployment | Environment Strategy document |
| 2 | Configuration loaded (all 44 sheets), including users and the Numbering sheet, from the UAT export with the Settings rows of section 5.5 removed; authority limits approved by a second administrator | Configuration kit | Configuration signed off in UAT |
| 3 | Environment comparison UAT against PROD: mirrored apart from environment-specific values | compare:environments or POST /api/data-load/compare | Step 2 |
| 4 | Users: Microsoft Entra ID sign-in tested; demo and sample accounts and the UAT-only tis-superid role inactive; security.password_sign_in_enabled off, break-glass administrator kept (deploy/AZURE.md section 14) | On screen | Step 2 |
| 5 | Smoke test or dress rehearsal in PROD (if agreed), then transaction reset; or no transactions in PROD | Reset | golive.locked off; evidence exported first |
| 6 | Bank accounts' reconcile-from date set to the cutover date | Bank Accounts sheet or screen | Step 5 |
| 7 | Cutover date set (golive.cutover_date, Master > Configuration, audited); fiscal year of the cutover date checked open | Screen | Step 5 |
| 8 | Schedules that write to clients or to interfaces paused and e-mail sending off (notification.email_enabled) until step 12 Procedure | Master > Schedules, Master > Configuration | Before the load |
| 9 | Migration workbook uploaded, validated, fixed, loaded | Migration kit | Legacy frozen and extracted (CO-1, CO-2) |
| 10 | Reconciliation and business validation | Sections 10, 13.3 | Step 9 |
| 11 | Go decision; golive.locked switched on (Master > Configuration, audited); accounting periods before the cutover date closed (Accounts > Period End > Period Management) Procedure, rehearsed in Mock 2 | Screen | Step 10 |
| 12 | Schedules, e-mail and SFTP interfaces on; production registered for the masking tool; users admitted | On screen; npm run mask:data -- --register-production | Step 11 |

Opening balances must be loaded before anyone posts a journal in the fiscal year of the cutover date: a load is refused once journals dated before the cutover exist in that year.

# Cutover runbook

## Flow

Diagram 4

| No. | Step | Next |
| --- | --- | --- |
| 1 | CO-1 Legacy freeze, last transactions posted, day-end | step 2 (CO-2 Extract, files and control figures signed) |
| 2 | CO-2 Extract, files and control figures signed | step 3 (CO-3 Pre-load checks, restore time noted, schedules paused) |
| 3 | CO-3 Pre-load checks, restore time noted, schedules paused | step 4 (CO-4 Validate, dry-run upload, fix cycle) |
| 4 | CO-4 Validate, dry-run upload, fix cycle | step 5 (CO-5 Migrate, load in one transaction) |
| 5 | CO-5 Migrate, load in one transaction | step 6 (CO-6 Reconcile, system checks + legacy figures) |
| 6 | CO-6 Reconcile, system checks + legacy figures | step 7 (CO-7 Differences, explained and accepted?) |
| 7 | Decision: CO-7 Differences, explained and accepted? | no: data wrong: step 8 (RB-2 reset, fix, back to CO-4) yes: step 9 (CO-8 Business validation, key-user samples) |
| 8 | RB-2 reset, fix, back to CO-4 | step 4 (CO-4 Validate, dry-run upload, fix cycle) |
| 9 | CO-8 Business validation, key-user samples | step 10 (CO-9 Go / No-Go) |
| 10 | Decision: CO-9 Go / No-Go | Go: step 11 (CO-10 Production, lock on, interfaces on, open) No-Go: step 12 (Rollback RB-2, legacy reopened) |
| 11 | CO-10 Production, lock on, interfaces on, open | End |
| 12 | Rollback RB-2, legacy reopened | End |

A loaded batch cannot be loaded again. A second, corrected batch on top of the first would update clients and replace the opening balances, but refuses every policy and claim already migrated with other values ("correct it on the policy screen"). A correction after CO-5 is therefore either made on screen (a few records, each audited) or by the transaction reset and a new load (RB-2) Procedure.

## Timetable

The timetable assumes the support window of NFR-13 (Monday to Saturday, 08:30 to 17:30 Philippine time) and a go-live on a Monday; the cutover date is that Monday, so C-1 is the Sunday. The legacy records are frozen at the Saturday close and no business is transacted on the Sunday, so the Saturday close equals the C-1 close that the opening balances represent (the reconciliation workbook shows "Opening balances as at" C-1). Durations are planning estimates to be replaced by the timings measured in Mock 2 and the dress rehearsal (section 15). The actual dates are open (Q6).

| When | Step | Activity | Owner | Evidence |
| --- | --- | --- | --- | --- |
| C-10 business days | Checkpoint 1 | UAT signed off; Mock 2 reconciled; dress rehearsal done; training done; configuration loaded in PROD and mirrored (section 12, steps 1 to 3) | Steering committee | Minutes; comparison workbook |
| C-5 business days | Readiness | Users loaded in PROD; first Microsoft sign-in tested; demo accounts and tis-superid inactive; password sign-in off except break-glass (section 12, step 4); communications to staff, insurers and banks | TISPH IT, Project Sponsor | User list; sign-in history |
| C-3 business days | Numbering | Next numbers checked against the last legacy numbers; official receipt series against the BIR registration | Finance Head, System Administrator | Numbering sheet export |
| Saturday 17:30 | CO-1 Legacy freeze | No new legacy transactions; last receipts and payments of the day posted; legacy day-end; legacy write access withdrawn | Operations and Finance leads; TISPH IT | Freeze notice; last numbers used |
| Saturday 18:00 to 22:00 | CO-2 Extract | Extract clients, in-force policies, open items, open claims, trial balance at C-1, due-to-insurers; control figures produced and signed | Data owners, Finance Head | Extract files with row counts and file checksums; signed control figures |
| Saturday 22:00 | CO-3 Pre-load checks | Note the PROD restore time; confirm golive.locked off, cutover date set, reset dry run shows no client, policy, receivable or claim row; schedules paused and e-mail off (section 12, step 8) | DevOps lead, System Administrator | Cutover log entries |
| Sunday 08:00 to 11:00 | CO-4 Validate | Fill the migration workbook; upload; fix cycle until no error; compare dry-run totals with control figures | Migration lead with data owners | Batch numbers; errors workbooks |
| Sunday 11:00 to 12:00 | CO-5 Migrate | Load the validated batch (all rows), with the Finance Head or a delegate present as second person (section 14) | Migration lead (System Administrator) | Batch loaded; audit entry; witness signature |
| Sunday 12:00 to 14:00 | CO-6 Reconcile | Reconciliation workbook; trial balance; receivables, due-to-insurer and bank reconciliations | Finance Head, migration lead | Signed reconciliation report |
| Sunday 14:00 | CO-7 Differences | Every difference explained and accepted, or RB-2 and back to CO-4 | Finance Head, data owners | Difference list with decisions |
| Sunday 14:00 to 16:00 | CO-8 Business validation | Key users check samples on screen (section 13.3) | Operations and Finance key users | Signed sample sheets |
| Sunday 16:00 | CO-9 Go / No-Go | Criteria of section 16 reviewed; decision recorded | Steering committee | Decision minute |
| Sunday 16:30 to 18:00 | CO-10 Production | golive.locked on; periods before cutover closed; schedules, e-mail and SFTP interfaces on; production registered for the masking tool; batch, errors and reconciliation workbooks archived; legacy set to read-only; users informed | System Administrator, DevOps lead | Audit entries; job list; archive reference |
| Monday 08:30 | Go-live | Floor support; first receipts, policies, payments and bank imports watched | Hypercare team | Hypercare log |

## Business validation samples (step CO-8)

| Sample | Check on screen |
| --- | --- |
| 20 policies per line of business (all if fewer) | Insured, insurer, product, dates, sum insured, premiums, plate number for motor, account executive |
| 20 open items | Policy, bill number (legacy), due date, balance, ageing bucket |
| All open claims (or 20) | Policy, loss and reported dates, status, estimate, handler |
| 20 clients | Type, name, TIN, address, contact details against the legacy record |
| Trial balance | Line by line against the legacy trial balance at C-1 |
| One test of each document series (in UAT or as the first live document) | The next number follows the last legacy number |
| One receipt on a migrated open item (in the dress rehearsal) | The bill is found by its legacy number and its balance falls |
| One migrated policy near expiry (in the dress rehearsal) | It appears in the renewal queue; the renewal term is new business |

Samples are chosen by the data owners, not by the migration team, and include the largest items by amount Procedure.

# Roles

| Role | Party | Responsibilities | Decides |
| --- | --- | --- | --- |
| Project Sponsor | TISPH | Owns the cutover date and the steering committee | Go / No-Go, rollback |
| Steering committee | TISPH and iorta TechNXT | Checkpoint 1 and CO-9 | Go / No-Go |
| Data owner (per object) | TISPH business units | Extract, cleanse, approve each file, produce control figures, sign the reconciliation | Acceptance of their data |
| Finance Head | TISPH | Trial balance, receivables, due to insurers, numbering of financial series; signs financial reconciliation; second person at the load | Accounting tolerances |
| Operations Unit Head | TISPH | Policies, clients, claims; business validation samples | Operational acceptance |
| TISPH IT (Head of IT, IT AppSupport) | TISPH | User list and Entra ID group, legacy freeze and read-only access, interface switch-on | IT readiness |
| Data Protection Officer | TISPH | Approves personal data handling in mocks and workbooks | Personal data use |
| Migration lead | iorta TechNXT | Mapping register, workbooks, loads, reconciliation workbooks, cutover log | Technical readiness of the data |
| System Administrator | TISPH (with iorta TechNXT during cutover) | Holds role system-admin and with it write:data-load; loads; switches golive.locked; a second administrator approves authority limits | — |
| DevOps lead | iorta TechNXT | Restore points, reset, rollback execution, environment health | Technical rollback feasibility |
| Hypercare team | iorta TechNXT and TISPH key users | First-line and second-line support after go-live | — |

Segregation of duties at cutover. The platform lets one System Administrator upload, load and switch the go-live lock with no second approval (section 20.1). The following procedures compensate Procedure:

- each production load (CO-5) and each change of golive.locked or golive.cutover_date is done with a second named person present, who signs the cutover log;

- the iorta TechNXT migration lead uses a named production account with role system-admin for the cutover and hypercare only; it is set inactive at hypercare exit and the change is checked in the access review;

- the person who loads does not sign the reconciliation alone: the data owners and the Finance Head sign it.

RACI for the cutover steps (R responsible, A accountable, C consulted, I informed):

| Step | Data owners | Finance Head | Migration lead | System Admin | DevOps lead | Steering committee |
| --- | --- | --- | --- | --- | --- | --- |
| CO-1 Freeze | R | A | I | I | I | I |
| CO-2 Extract | R | A | C | I | I | I |
| CO-3 Pre-load checks | I | I | C | R | R/A | I |
| CO-4 Validate | C | C | R/A | C | I | I |
| CO-5 Migrate | I | C | R | A | C | I |
| CO-6 Reconcile | R | A | R | I | I | I |
| CO-7 Differences | R | A | C | I | I | I |
| CO-8 Business validation | R | A | C | I | I | I |
| CO-9 Go / No-Go | C | C | C | C | C | R/A |
| CO-10 Production | I | I | C | R | R | A |

# Timings

| Item | Value | Source |
| --- | --- | --- |
| Product rehearsal, all steps (2,820 configuration rows, 171 migration rows) | 11 seconds elapsed, two local environments | Recorded run (section 11.5) |
| Upload size limit | IMPORT_MAX_MB (default 10 MB) per workbook; inflated content capped by IMPORT_MAX_INFLATED_MB (default 50 MB) | config.js, lib/uploadLimits.js |
| Rows | At most IMPORT_MAX_ROWS (default 20,000) rows per sheet, checked as the workbook is read; stored in chunks of 500. A larger object (for example clients) is split over several workbooks loaded in turn, which makes the BrokerVerse totals of the reconciliation cumulative (section 10.1) | documents/xlsx.js (sheetRows), lib/uploadLimits.js (assertRowLimit), data-load/service.js |
| Request time-outs | Front Door 120 seconds; web proxy 60 seconds (nginx default) | Section 9 |
| TISPH volumes per object | Unknown | Q2 |
| Batch processing time target | "TBD c/o IORTA" | NFR-07.5 |

Procedure. In Mock 2 and the dress rehearsal the migration lead records, per step of section 13.2, start and end times and the elapsed time of each upload and load, and the time of the transaction reset and of a point-in-time restore. The cutover timetable is then fixed with a contingency of at least 50% on the measured times, and the latest time for the Go / No-Go is set so that rollback RB-2 can still complete before Monday 08:30. The measured load time is reported against NFR-07.5 ("TBD c/o IORTA"), for which TISPH and iorta TechNXT agree a figure after Mock 2.

# Go / No-Go criteria

Go-live goes ahead only when all of these are met:

| # | Criterion | Evidence |
| --- | --- | --- |
| G1 | UAT signed off by each process owner; no open severity 1 or 2 defect | UAT sign-off |
| G2 | Migration batch loaded with no row in error and without "valid rows only" | Batch record |
| G3 | Trial balance check and receivables control check agree, or each difference is explained and accepted in writing by the Finance Head | Reconciliation workbook and report |
| G4 | Every legacy control figure of section 10.2 reconciled within its tolerance | Signed reconciliation report |
| G5 | Business validation samples passed | Signed sample sheets |
| G6 | Configuration mirrored with UAT apart from environment-specific values | Comparison workbook (exit code 0) |
| G7 | Users loaded and able to sign in; sample data purged (npm run purge:sample); demo accounts, the UAT-only tis-superid role and the platform roles nobody holds inactive; password sign-in off except break-glass; second administrator available | User list; sign-in history |
| G8 | Numbering continues above every legacy number; official receipt series matches the BIR registration | Numbering export; test document |
| G9 | Restore point noted and rollback team available | Cutover log |
| G10 | Hypercare team and support contacts in place | Hypercare roster |
| G11 | Batch, errors and reconciliation workbooks and the signed reports archived outside BrokerVerse | Archive reference |

A No-Go names the reason, the actions and the new date. Criteria G2 to G5 may not be waived; others only by the Project Sponsor in writing.

# Rollback

## Rollback points

| Point | When | Action | Effect |
| --- | --- | --- | --- |
| RB-1 | Before the migration load (CO-1 to CO-4) | Stop; declare No-Go; reopen the legacy records; resume schedules and e-mail as they were | Nothing in BrokerVerse to undo; configuration stays |
| RB-2 | After the load, before golive.locked (CO-5 to CO-9) | Export the batch, errors and reconciliation workbooks; then the transaction reset (removes the migrated records, the opening balances, the load history and the accounting calendar, keeps configuration and users; allowed while unlocked), or, if the reset fails, a point-in-time restore to the time noted at CO-3 | PROD back to configuration only; calendar set up again (section 12, step 7); fix the data and repeat from CO-4, or No-Go |
| RB-3 | After go-live, within the rollback window | Fix forward is the default. Full fallback only on a severity 1 issue with no workaround: legacy records reopened; transactions entered in BrokerVerse since go-live re-keyed there from BrokerVerse registers | Decision of the steering committee |
| RB-4 | Application release problem at any time | Redeploy the previous images (pipeline rollback mode or wait-for-revision.sh); no data change | Environment Strategy document |

The rollback window ends at the end of the first business week after go-live Procedure; after it, issues are fixed forward.

## How each rollback works in the system

- Transaction reset (RB-2): CONFIRM_RESET=yes npm run reset:transactions -- --execute from inside the environment, API instances stopped first (the Azure procedure is to be written and rehearsed, Q16); one transaction; never with --purge-audit; refused once golive.locked is on. Any System Administrator can switch the lock off again on Master > Configuration; the change is audited but needs no second approval (section 20.1). The reset records itself in the audit trail.

- Point-in-time restore (RB-2 or data damage): Azure Database for PostgreSQL restores to any second of the retention window (35 days in production) into a new server; the database-url secret is then pointed at it and the API restarted (deploy/AZURE.md section 12). The restored server is created outside the Terraform state, which the DevOps lead brings back in line afterwards (Environment Strategy document). A restore loses every transaction after the restore point, so it is not used after go-live except for data damage.

- Go-live lock: once on, the migration kit (upload, validation, load) and the reset are refused; the configuration kit stays available for new masters. The single-object go-live imports are not refused (section 5.4).

## Corrections after go-live

After the lock, migrated data is corrected on the normal screens (policy, client, claim, receipt allocation, journal voucher under maker-checker), each change audited. A migrated policy whose number exists cannot be loaded again by the migration kit ("correct it on the policy screen").

## Legacy records

The legacy records stay available read-only from CO-10 until hypercare exit and then for the retention periods of NFR-11.1 and NFR-11.2 (closed contracts 5 years; contracts with cases 10 years), under TISPH's custody (Q11) Procedure.

# Hypercare

| Item | Plan |
| --- | --- |
| Duration | Four weeks from go-live, including the first month-end close (Q12) |
| Hours | NFR-13 support window, Monday to Saturday 08:30 to 17:30; on-call for severity 1 outside it |
| Team | Migration lead, a functional consultant per area, DevOps lead; TISPH key users as first line |
| Daily checks | Trial balance balances; premiums receivable control account against open items; receipts on migrated open items; new numbers issued above legacy numbers; scheduled jobs and interfaces ran (SAP GL file, bank files); sign-in and authority-limit issues |
| Weekly checks | Renewal queue picks up migrated policies; ageing of migrated open items; due-to-insurer payments from opening balances; audit trail review of corrections to migrated records and of any use of the single-object go-live imports (section 5.4); golive.locked still on |
| Corrections | On screen with audit (section 17.3); a bulk correction only through a single-object import agreed in writing with the Finance Head |
| Exit criteria | First month-end closed in BrokerVerse; no open severity 1 or 2 defect; reconciliation differences cleared; migration evidence archived (section 20); iorta TechNXT cutover accounts set inactive and checked in an access review; TISPH support team trained and handed the runbooks |

# Sign-off

| Sign-off | When | Signed by |
| --- | --- | --- |
| Mapping register | Before Mock 1 (sample), before Mock 2 (full) | Data owners, migration lead |
| Mock 1 report | End of Mock 1 | Migration lead, Project Sponsor |
| Mock 2 report with reconciliation | End of Mock 2 | Data owners, Finance Head |
| Dress rehearsal report with timings | End of the rehearsal | Steering committee |
| Legacy control figures at C-1 | Cutover, step CO-2 | Data owners, Finance Head |
| Production reconciliation report and difference list | Cutover, steps CO-6 and CO-7 | Data owners, Finance Head |
| Witness of the production load | Cutover, step CO-5 | Finance Head or delegate |
| Business validation samples | Cutover, step CO-8 | Key users, Operations Unit Head |
| Go decision | Cutover, step CO-9 | Steering committee |
| Hypercare exit and migration acceptance | End of hypercare | Project Sponsor, Finance Head, Head of IT |

# Evidence, audit and retention

The controls of this section are those of the Data Migration & Go-Live workspace (Master > System Configuration), built on branch tisph/migration-workspace (migrations 0440 to 0444). Sections 5 to 19 still describe the baseline and the procedures that compensated for the gaps; where they differ, this section applies.

| Evidence | Where it is kept | Retention |
| --- | --- | --- |
| Loads: load number (MIG-000012, CFG-000045), kit, run, legacy system, file name and SHA-256, status from validation to load or undo, counts per result, uploader, submitter, approver, undo requester and approver, timings | data_load_batches | Kept in PROD; kept and marked by the transaction reset (mocks, rehearsals) |
| Rows of a load with their result (New, Changed with the changed fields, Unchanged, Duplicate, Error), the values before a change and the record created or changed; identifiers (TIN) encrypted | data_load_rows | Rows of the production run's loads kept for the retention years; others deleted after housekeeping.data_load_rows_days (365) |
| The workbook as uploaded | Encrypted storage folder, with its hash | As the rows. Released only to holders of write:data-load and view:pii; each download audited |
| Origin of migrated records: origin, legacy_system, legacy_number, migrated_at, migrated_by, load_batch_id | Clients, policies, receivables, claims, journal vouchers, post-dated cheques; load_batch_id on opening balances and CTPL authentications | Life of the record; read-only after the load |
| Reconciliations: lines per object and measure with the legacy figure, differences with explanation, action and acceptance, sign-off slots, the signed PDF and its hash | migration_reconciliations and lines, differences, sign-offs | Never purged |
| Mock and production runs, cutover checklist with owner, times and evidence, defects, Go / No-Go decisions with criteria, waivers and votes, lock and unlock requests | migration_runs, migration_run_steps, migration_run_defects, go_live_decisions, go_live_lock_requests, migration_evidence | Never purged; kept by the transaction reset |
| Evidence pack of a run: workbooks (masked per user), reconciliation reports, checklist, decision, evidence files and a SHA-256 manifest | Downloaded from the run (Mock Runs tab); its hash is recorded on the run | Archived per TISPH's record policy (Q14); criterion G11 checks the recorded hash |
| Audit entries of every action of the workspace and one entry per migrated record | Audit trail | Not purged unless housekeeping.audit_log_days is set, and then never below 7 years |

## Audit coverage of the migration

| Event | What the system records and enforces |
| --- | --- |
| Upload and validation of a workbook | Load entry (validate) with the file, its hash and the counts per result; every row with its result and, for a changed record, the fields changed with the values before. A file identical to an earlier load is flagged |
| Approval of a load | Submit, approve, reject (reason from the list) and withdraw are audited. The approver must hold approve:data-load and is never the uploader, the submitter or a user who resolved one of the load's duplicates (refused by the server). A segregation-of-duties rule flags anyone holding both write and approve. Load approval cannot be switched off in production or pre-production |
| Load | One migrate-create or migrate-update entry per record with the values before and after, the load and its number, in the load transaction; the record's activity log starts with "Migrated from <legacy system>, load MIG-000012". A load that fails saves nothing and writes no record entry |
| Undo of a load (before the lock only) | Requested with a reason and approved by a second person; refused while a later record depends on the load. migrate-undo entry per record |
| Settings owned by the workspace (golive.*, migration.*) | Changed only on the Go-Live tab (cutover date: write:data-load; settings: approve:data-load), with before and after values; never by the Settings sheet or Master > Configuration |
| Go-live lock and unlock | Requested by one user and approved by another (go_live_lock request, approve, reject); the lock needs a Go decision, a signed reconciliation and no load waiting. An unlock names the imports it reopens and relocks itself after its hours (relock) |
| Imports of legacy business | Every migration import is under the lock and needs write:data-load: the migration workbook, the policies go-live upload, the open items import, the opening balances import, legacy-dated rows of the ordinary policy bulk upload, the transaction reset and undo. A refused attempt is audited (refused-locked) |
| Reconciliation | Legacy figures, tolerances, explanations, acceptance and signatures audited; acceptance and signing refused to anyone who uploaded, submitted or approved one of its loads; the first signature freezes it |
| Go / No-Go | Criteria results, waivers (refused on G2 to G5), votes of the named approvers with remarks |
| Business after go-live on migrated records | Endorsements, claims, receipts and renewals on a migrated policy are issued business, flagged with the policy's origin and legacy number on screen. Edits to migrated records are audited like any record; their origin, legacy number and load cannot be changed |
| Downloads of migration data | Personal data masked for users without view:pii; downloads of current data, uploaded files and evidence packs audited |

How migrated and issued business are told apart on the screens (chip Migrated with the legacy number and the load, Migrated policy on endorsements and claims, Renewal of legacy policy, Origin filters on the lists and reports, dashboards opening on Issued since go-live) is described in the workspace guide (GO_LIVE_DATA_WORKBENCH.md, section Migrated and issued on the screens).

# Planned items register

| Ref | Item | Depends on |
| --- | --- | --- |
| M-01 | Setup Workbook screen for the configuration workbook and upload with template on every master screen, with approval of masters under maker-checker | Work package MU-A (after REG-1, ADP-1, PD-1a); TISPH decisions M1, M2, M5 |
| M-02 | Shared master registry, case-insensitive business keys and a pre-flight duplicate-key report | Work package REG-1 (migration 0411) |
| M-03 | Current-data workbooks masked for users without view:pii; /api/data-load removed from the masking exempt list | Work packages PD-1a (after W0-3) and MU-A (migration 0430) |
| M-04 | system.environment, the golive.* settings and environment-bound interface settings never exported or loaded by the configuration workbook; system.environment read-only on Master > Configuration | Work package W0-4 |
| M-05 | PRE-PROD environment on Azure for the dress rehearsal | Environment item P-01; TISPH decision E1 |
| M-06 | Configuration promotion by signed, approved Environment Promotion packages with verification and rollback | Work packages PR-1a, PR-1b; TISPH decisions E1 to E15 |
| M-07 | Go-live remittance readiness (remittance specification section 8: a go-live script run first as a dry run whose report TISPH Finance signs, clean-up of remittances in progress) and opening remittances created from a policy list (purpose "Go-live opening") | Remittance build phase R2; remittance specification question Q14 (this plan's Q13) |

Number of Planned items: 7.

Built since the baseline (Data Migration & Go-Live workspace, section 20): product-wise policy sheets and the document file-naming convention with its checker (Q3), TISPH policy attributes on the product sheets (Q4), the workspace screens (Q15), second-person approval of loads, per-record audit, the two-person go-live lock over every migration import (Q17). Not built and without a work package: bulk migration of legacy documents (Q3); a documented Azure procedure for the transaction reset (Q16).

# Open questions for TISPH

| Serial Number | Description | Owner | Status |
| --- | --- | --- | --- |
| Q1 | Scope: MIG-01 is confirmed as masters-only for Phase 2. Is TISPH's open business (clients, in-force policies, unpaid premium, open claims, GL opening balances) to be migrated with the migration kit, or does TISPH start BrokerVerse with new business only and run off the legacy book outside it? A migration of open business is a change request against the signed scope Needed by: Before Mock 1 | TISPH | Open |
| Q2 | Legacy sources: which Excel files (and any other system) hold masters, policies, receivables, claims and the trial balance; who owns each; volumes per object; when is the MIG-01 sample dataset available? Needed by: Before Mock 1 | TISPH | Open |
| Q3 | MIG-01 "product-wise migration templates" and "document file-naming convention": what does TISPH expect (one template per product, or the one Policies sheet with product codes)? Are legacy policy documents to be migrated, and in what naming convention? Needed by: Before Mock 1 | TISPH | Open |
| Q4 | Which TISPH-specific attributes must a migrated policy carry (distribution channel, branch, business type, subline, TFS loan or dealer reference)? The Policies sheet does not carry them Needed by: Before Mock 1 | TISPH | Open |
| Q5 | Accounting: given that SAP receives the daily GL file (INTG-04), is BrokerVerse's GL loaded with opening balances at cutover, and from which trial balance (SAP or legacy)? Which chart of accounts mapping applies? The SAP GL file carries posted journals only, so the opening balances are never sent to SAP Needed by: Before Mock 2 | TISPH | Open |
| Q6 | Cutover date and window: target go-live date, whether the freeze may start Saturday 17:30, and whether cutover should align with a month-end Needed by: Checkpoint 1 | TISPH | Open |
| Q7 | Final licensed user list (20) with roles, Microsoft 365 addresses and the Entra ID group; the named break-glass administrator; the second administrator for authority-limit approval Needed by: C-5 business days | TISPH | Open |
| Q8 | Last legacy number used per document series and the legacy number formats; the BIR-registered official receipt series Needed by: Before Mock 1 | TISPH | Open |
| Q9 | May real legacy personal data be loaded into UAT for the mocks (DPO approval, restricted access), or must extracts be pseudonymised first? Needed by: Before Mock 1 | TISPH | Open |
| Q10 | Members of the steering committee for Go / No-Go; who signs the financial reconciliation; accepted tolerances for differences Needed by: Checkpoint 1 | TISPH | Open |
| Q11 | How long the legacy records stay available read-only after go-live, and who keeps them for the NFR-11.1 and NFR-11.2 retention periods Needed by: Checkpoint 1 | TISPH | Open |
| Q12 | Hypercare length (four weeks proposed) and the TISPH first-line team Needed by: Checkpoint 1 | TISPH | Open |
| Q13 | Opening remittances: which policies form the first remittance to each insurer after go-live (remittance specification Q14) Needed by: Before Mock 2 | TISPH | Open |
| Q14 | Where migration evidence (workbooks, reconciliation, sign-offs) is archived and for how long; whether housekeeping.data_load_rows_days should be 0 in production Needed by: Before go-live | TISPH | Open |
| Q15 | Screen for the migration kit: built as Master > System Configuration > Data Migration & Go-Live (section 20). Remaining for TISPH: who operates it in each mock run Needed by: Before Mock 2 | TISPH | Open |
| Q16 | Azure operation (for iorta TechNXT DevOps, agreed with TISPH IT): how the transaction reset is run in PROD with the API stopped, and whether the production load is run from inside the environment to avoid the 60-second proxy time-out Needed by: Mock 1 | TISPH | Open |
| Q17 | Controls: built in the Data Migration & Go-Live workspace (section 20.1): second-person approval of every load and undo, per-record audit with before and after values, the two-person go-live lock over every migration import including the single-object imports. Remaining for TISPH: confirm the default grants (read and write for TIS IT AppSupport; approve for Finance, Operations Unit Head and General Manager; read-only TIS Auditor), the unlock window (7 days, 4 hours per unlock) and whether undo stays open up to the lock or ends at the reconciliation sign-off Needed by: Before Mock 2 | TISPH | Open |
| Q18 | May the iorta TechNXT migration lead hold a named System Administrator account in PROD from Checkpoint 1 to hypercare exit? Needed by: Checkpoint 1 | TISPH | Open |

# Requirements traceability

| BRD reference | Sections |
| --- | --- |
| MIG-01 | 3, 5, 6, 11, 21, 22 (Q1 to Q4) |
| SEC-05 | 5.2, 6.2, 12 (step 4), 13.2, 16 (G7), 22 (Q7) |
| NFR-07.4 | 8.1, 9 |
| NFR-07.5 | 15 |
| NFR-5.3 | 10, 13.3, 19 |
| NFR-08 | 5.5, 16 (G6) |
| NFR-06.2, NFR-06.3 | 17 |
| NFR-11, NFR-11.1, NFR-11.2, NFR-11.3 | 17.4, 20 |
| NFR-13 | 13.2, 18 |
| NFR-17 | 5.5, 11.4 |
| Section 5.12 (numbering mask) | 6.4 |
| Section 5.13 | 3, 12 (steps 8, 12), 13.2 (CO-10), 18 |
| Section 5.14 | 9, 14, 20, 20.1 |
| Section 9 | 11, 12, 13 |

# Appendix A. File references

All paths are relative to the repository root at commit 58ad7702 unless stated. Azure files are those of branch tisph/azure-deploy.

| Section | Files |
| --- | --- |
| 2, 5.1 | backend/src/modules/data-load/router.js (routes, permissions, audit, notification, Cache-Control: no-store); backend/src/modules/data-load/service.js (kits, template, createBatch, validateBatch, loadBatch, errorsWorkbook, assertKitAllowed); backend/src/modules/data-load/workbook.js (KITS, instructions, kitWorkbook, readKitWorkbook, reconciliationWorkbook); backend/src/modules/data-load/compare.js (readSheets); backend/src/db/migrations/0244_go_live_data_workbench.sql; front-end commit c9898114 "Remove the Go-Live Data Load screen"; backend/docs/api/openapi.json, backend/docs/api/BrokerVerse.postman_collection.json |
| 5.2 | backend/src/modules/data-load/configuration.js (configurationSheets, settingsSheet, loadableSetting, usersSheet, authoritySheet, numberingSheet, CONFIGURATION_ON_SCREEN); docs/onboarding/GO_LIVE_DATA_WORKBENCH.md |
| 5.3 | backend/src/modules/data-load/migration.js (clientsSheet, policiesSheet, openItemsSheet, claimsSheet, openingBalancesSheet, MIGRATION_ON_SCREEN); backend/src/modules/data-load/common.js (MIGRATION_SOURCE); backend/src/modules/receipts/opening.js (loadOpenItem, OPENING_SOURCE); backend/src/modules/period-end/opening.js (importOpeningBalances, GO_LIVE_PREFIX); backend/src/modules/policies/service.js (issuePolicy migration mode) |
| 5.3 (M-07) | Remittance build specification SPEC.md sections 4.3, 8, 11 (not in the repository) |
| 5.4 | docs/package/05_Delivery/Upload_Templates/README.md; backend/scripts/build-upload-templates.js; backend/src/modules/policies/router.js (/bulk-upload, mode=go-live, write:policies); backend/src/modules/receipts/router.js (/opening-items/import, write:receipts); backend/src/modules/period-end/router.js (/opening-balances/import, write:period-end, audit go-live-import); backend/src/db/migrations/0348_tisph_roles.sql (TISPH role permissions) |
| 2, 14 | backend/src/db/migrations/0244_go_live_data_workbench.sql (grants to system-admin only); backend/src/db/migrations/0348_tisph_roles.sql (tis-it-admin without data-load permissions; tis-superid UAT only) |
| 5.2, 5.5 | backend/src/modules/data-load/configuration.js (loadableSetting, LOCK_KEY); backend/src/lib/settings.js (setSetting, no audit); backend/src/modules/settings/router.js (PUT /settings, audit with before and after); backend/src/db/migrations/0249_system_environment.sql |
| 5.5 | backend/src/modules/data-load/comparisons.js, compare.js (ENVIRONMENT_SPECIFIC); backend/scripts/compare-environments.js; deploy/RELEASE_PIPELINE.md section 12 |
| 6.3 | backend/src/modules/data-load/migration.js (column definitions and importRow defaults) |
| 6.4 | backend/src/modules/data-load/numbering.js (seriesShape, sequenceOf, collidingNumber, MIGRATED_NUMBER_TARGETS); backend/src/modules/data-load/migration.js (assertNoSeriesClash) |
| 7 | backend/src/modules/data-load/common.js (beforeCutover, amountValue, dateValue, numberCell, cellString) |
| 8 | backend/src/modules/data-load/service.js (runSheets, savepoints, advisory lock, held rows); backend/src/db/pool.js (runInTransaction, withTransaction); backend/src/modules/data-load/migration.js (check, importRow, importSheet); backend/src/modules/period-end/opening.js |
| 9 | backend/src/modules/data-load/service.js (loadBatch); backend/src/modules/data-load/router.js (/batches/:id/load, notify to the loading user); deploy/azure/modules/environment/frontdoor.tf (response_timeout_seconds = 120); brokerverse/nginx/default.conf.template (no proxy_read_timeout) |
| 10 | backend/src/modules/data-load/migration.js (reconciliation, totals); backend/src/modules/data-load/workbook.js (reconciliationWorkbook); backend/src/db/seeds/40_finance.sql (accounting.account.premium_receivable); backend/src/modules/accounting/router.js (/trial-balance); backend/src/modules/policies/router.js (source filter) |
| 11 | backend/scripts/reset-transactions.js; backend/scripts/lib/table-classification.js; backend/src/lib/goLiveLock.js; backend/src/db/migrations/0243_golive_lock_for_transaction_reset.sql; backend/scripts/golive-rehearsal.js; backend/scripts/golive/*.js; backend/scripts/mask-data.js; backend/src/lib/piiPolicy.js (DEFAULT_EXEMPT_PATHS); backend/src/db/migrations/0276_personal_data_masking.sql; backend/Dockerfile (COPY scripts); docs/e2e/GOLIVE_REHEARSAL_RUN.md; docs/onboarding/SMOKE_TEST_AND_RESET.md; docs/onboarding/DATA_MASKING.md |
| 11.3, 17.2 | deploy/azure/environment/environments/*.tfvars (no PRE-PROD file); deploy/azure/modules/environment/database.tf; deploy/AZURE.md sections 10, 12 (branch tisph/azure-deploy) |
| 12 | docs/onboarding/GO_LIVE_DATA_SETUP.md; docs/onboarding/SMOKE_TEST_AND_RESET.md (sample data purge); deploy/AZURE.md (rollback); deploy/azure/modules/environment/containerapps.tf (SEED_SAMPLE_DATA = "false", migration job); backend/src/modules/period-end/opening.js (posted-journal check, fiscalYearOf); backend/src/db/seeds/jobs.json (scheduled jobs); backend/src/db/seeds/settings.json (notification.email_enabled); backend/src/db/migrations/0116_bank_reconciliation.sql (reconcileFrom); backend/src/modules/sap-gl/README.md (journals only) |
| 11.2, 17 | backend/scripts/lib/table-classification.js (data_load_* removed, fiscal_years and accounting_periods transaction tables, audit_log optional); docs/onboarding/SMOKE_TEST_AND_RESET.md (API stopped first) |
| 13.2 | deploy/AZURE.md section 14 (Entra ID sign-in, demo accounts, security.password_sign_in_enabled) (branch tisph/azure-deploy); backend/src/db/seeds/82_tisph_roles.sql; backend/scripts/mask-data.js (--register-production); docs/onboarding/DATA_MASKING.md |
| 15 | backend/src/config.js (IMPORT_MAX_MB, IMPORT_MAX_INFLATED_MB, IMPORT_MAX_ROWS); backend/src/lib/uploadLimits.js (assertRowLimit); backend/src/modules/documents/xlsx.js (readWorkbook, sheetRows); backend/src/modules/data-load/compare.js (readSheets); backend/src/modules/data-load/service.js (chunks of 500) |
| 17 | backend/scripts/reset-transactions.js; backend/src/modules/data-load/service.js (assertKitAllowed); .github/workflows/azure-deploy.yml; deploy/azure/wait-for-revision.sh |
| 20 | backend/src/jobs/housekeeping.js (RULES, AUDIT_MIN_DAYS); backend/src/db/seeds/settings.json (housekeeping.data_load_rows_days, housekeeping.audit_log_days); backend/src/db/migrations/0244_go_live_data_workbench.sql (load_batch_id, ON DELETE SET NULL); backend/src/db/migrations/0248_data_load_comparisons.sql |
| 20.1 | backend/src/modules/data-load/router.js (audit entries export-current-data, validate, load, compare); backend/src/modules/data-load/configuration.js and migration.js (no per-record audit); backend/src/modules/settings/router.js; backend/src/lib/goLiveLock.js |
| 21 | Platform build plan BUILD_PLAN.md sections 3, 6, 7, 8 (not in the repository) |
| Tests | backend/test/go-live-workbench.test.js, go-live-roundtrip.test.js, go-live.test.js, environment-comparison.test.js, reset-transactions.test.js, mask-data.test.js, upload-templates.test.js |

# Document Sign-Off

| Sign Off Date | Signature | Approved By | Department & Project Role |
| --- | --- | --- | --- |
|  |  |  | TISPH Project Sponsor |
|  |  |  | TISPH Finance Head |
|  |  |  | TISPH Head of IT |
|  |  |  | iorta TechNXT Delivery |