## Read me
BrokerVerse OOTB Implementation Plan
Companion workbook of the BrokerVerse Implementation Approach and Plan and of the Dependency Map and Critical Path, version 1.1, 04 October 2026, iorta TechNXT.
Sheets
Summary: the weeks of each phase and milestone for the four broker sizes.
Small (8 weeks), Medium (12 weeks), Large (20 weeks), Enterprise (26 weeks): the task-level plan of each size, with duration, party, owner role, deliverable, predecessors, dates from the kick-off date, float to go-live and the critical path, and the Gantt bars.
Milestones: the eight milestones of the plan, their evidence and their week by size.
Dependencies: every link between tasks, with its type and lag by size.
RACI: who is Responsible, Accountable, Consulted and Informed, for iorta TechNXT, the broker roles and the partners.
Sizes (named users, as in the Service Catalogue and Rate Annex)
Small: 1 to 25 users; Dev, UAT, Production; Pre-Prod temporary; hypercare 2 weeks.
Medium: 26 to 100 users; Dev, UAT, Production; Pre-Prod temporary; hypercare 3 weeks.
Large: 101 to 300 users; Dev, SIT, UAT, Production (high availability); Pre-Prod temporary; hypercare 6 weeks.
Enterprise: above 300 users; Dev, SIT, UAT, Production (high availability, cross-region backup copy); Pre-Prod temporary; hypercare 6 weeks.
Notes
Durations are working days of elapsed time, not effort. They and the lead times of the regulatory registrations are planning assumptions; the steering committee re-baselines them at mobilisation.
A registration the broker already holds (ATP or CAS, AMLC registration, NPC registration, IC licences) takes no lead time: confirm it at mobilisation and close the task.
Tasks marked "Feature only" do not hold the go-live: the feature goes live later and the documented fallback is used meanwhile (Dependency Map and Critical Path).
Hypercare extends to cover the first month-end close when the close falls after the planned hypercare exit.
The plan assumes an out-of-the-box implementation: configuration only, no customisation.
Source: docs/package/tools/delivery/plan_model.py. Rebuild: python3 build_plan_xlsx.py ../05_Delivery/BrokerVerse_Implementation_Plan.xlsx

## Summary
Summary: phases and milestones by broker size
Weeks from the kick-off (week 1). A phase runs from the first week of its first task to the last week of its last task.
Phase | Small (8 weeks) | Medium (12 weeks) | Large (20 weeks) | Enterprise (26 weeks)
Mobilisation | W1 | W1 | W1 | W1
Environments and pipeline | W1 to W2 | W1 to W3 | W1 to W4 | W1 to W5
Discovery and fit-gap | W1 to W2 | W1 to W3 | W1 to W4 | W1 to W6
Client inputs | W1 to W2 | W1 to W3 | W1 to W4 | W1 to W6
Regulatory registrations | W1 to W6 | W1 to W6 | W1 to W9 | W1 to W12
Configuration (go-live configuration kit) | W2 to W4 | W2 to W6 | W3 to W10 | W4 to W13
Compliance set-up | W3 to W4 | W4 to W6 | W6 to W8 | W8 to W10
Branding and brand pack | W3 to W4 | W4 to W5 | W6 to W7 | W8 to W9
Integrations with partners | W2 to W7 | W2 to W10 | W3 to W15 | W3 to W21
Data migration (go-live migration kit) | W1 to W5 | W1 to W7 | W1 to W13 | W1 to W18
Training | W4 to W6 | W6 to W9 | W8 to W14 | W10 to W19
SIT and UAT | W4 to W6 | W6 to W9 | W10 to W14 | W13 to W20
Rehearsal and cutover | W5 to W7 | W8 to W10 | W12 to W15 | W16 to W21
Hypercare | W7 to W8 | W10 to W12 | W15 to W20 | W21 to W26
Milestone | Small | Medium | Large | Enterprise
Kick-off | Start of W1 | Start of W1 | Start of W1 | Start of W1
Configuration decisions and fit-gap register signed | End of W2 | End of W3 | End of W4 | End of W6
Configuration complete | End of W4 | End of W6 | End of W10 | End of W13
SIT exit | End of W4 | End of W7 | End of W12 | End of W16
UAT sign-off | End of W6 | End of W9 | End of W14 | End of W20
Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | End of W6 | End of W9 | End of W14 | End of W20
Go-live | Start of W7 | Start of W10 | Start of W15 | Start of W21
Knowledge transfer, configuration baseline (Current data workbook of Production), handover; Pre-Prod removed | End of W8 | End of W12 | End of W20 | End of W26
Size | Named users | Environments | Mock loads | Hypercare
Small | 1 to 25 | Dev, UAT, Production; Pre-Prod temporary | Mock loads 1 and 2 in UAT; the cutover rehearsal in Pre-Prod is the third load | 2 weeks, extended to the first month-end close
Medium | 26 to 100 | Dev, UAT, Production; Pre-Prod temporary | Mock loads 1 and 2 in UAT; the cutover rehearsal in Pre-Prod is the third load | 3 weeks, extended to the first month-end close
Large | 101 to 300 | Dev, SIT, UAT, Production (high availability); Pre-Prod temporary | Mock loads 1 and 2 in SIT, mock load 3 in UAT; the cutover rehearsal in Pre-Prod is the fourth load | 6 weeks, extended to the first month-end close
Enterprise | above 300 | Dev, SIT, UAT, Production (high availability, cross-region backup copy); Pre-Prod temporary | Mock loads 1 and 2 in SIT, mock loads 3 and 4 in UAT; the cutover rehearsal in Pre-Prod is the fifth load | 6 weeks, extended to the first month-end close

## Small
BrokerVerse OOTB implementation plan: Small broker (8 weeks, go-live at the start of week 7)
Kick-off date (a Monday): |  |  | 2026-11-02 |  | Type the kick-off date in the yellow cell: start and finish dates follow (working days, weekends skipped; add holidays as a third WORKDAY argument). Environments: Dev, UAT, Production; Pre-Prod temporary. Mock loads 1 and 2 in UAT; the cutover rehearsal in Pre-Prod is the third load.
Bars: blue iorta TechNXT, green broker, gold partner; red border and red ID = on the critical path to go-live. Float = working days a task can slip before the go-live date moves (empty: the task does not hold the go-live).
ID | Phase | Task | Party | Owner role | Deliverable or evidence | Predecessors | Duration (working days) | Start day | Finish day | Start date | Finish date | Start week | End week | Float to go-live (days) | Critical | Holds back | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
Mobilisation
M1 | Mobilisation | Kick-off | iorta TechNXT | iorta TechNXT PM | Kick-off held; plan and go-live date confirmed |  | 0 | 0 | 0 |  |  | 1 | 1 | 0 | Yes | Go-live | bar: W1
M3 | Mobilisation | Data request list and the go-live kits issued (configuration and migration workbooks, upload templates) | iorta TechNXT | iorta TechNXT PM | Data request list; blank workbooks handed over | M1 | 1 | 0 | 1 |  |  | 1 | 1 | 0 | Yes | Go-live | bar: W1
M4 | Mobilisation | Broker team named: PM, key users, Accounting Manager, System Administrator, compliance officer, DPO | Broker | Broker sponsor | Named team with committed time | M1 | 1 | 0 | 1 |  |  | 1 | 1 | 10 |  | Go-live | bar: W1
M5 | Mobilisation | Hosting option, environment set and data location confirmed; environments ordered | Broker | Broker sponsor and IT head | Order Form hosting fields; transfer decision recorded | M1 | 1 | 0 | 1 |  |  | 1 | 1 | 4 |  | Go-live | bar: W1
M2 | Mobilisation | Project charter, baselined plan, governance calendar, RAID log | iorta TechNXT | iorta TechNXT PM | Charter and plan signed | M1 | 2 | 0 | 2 |  |  | 1 | 1 | 10 |  | Go-live | bar: W1
Environments and pipeline
E1 | Environments and pipeline | Dev provisioned | iorta TechNXT | iorta TechNXT DevOps lead | Environment sheet: Dev | M5 | 2 | 1 | 3 |  |  | 1 | 1 | 4 |  | Go-live | bar: W1
E3 | Environments and pipeline | UAT provisioned | iorta TechNXT | iorta TechNXT DevOps lead | Environment sheet: UAT | M5 | 2 | 1 | 3 |  |  | 1 | 1 | 6 |  | Go-live | bar: W1
E5 | Environments and pipeline | Application secrets per environment in the secret store: JWT_SECRET, DATA_ENCRYPTION_KEY, PII_ENCRYPTION_KEY generated; key custody and escrow copy agreed | iorta TechNXT | iorta TechNXT DevOps lead with the broker IT head | Key custody record signed by both | E1 | 1 | 3 | 4 |  |  | 1 | 1 | 5 |  | Go-live | bar: W1
E4 | Environments and pipeline | GitHub Environments (dev, sit, uat, preprod, production): protection rules, reviewers, variables, environment secrets | iorta TechNXT | iorta TechNXT DevOps lead | Settings recorded in the environment sheet | E1 | 2 | 3 | 5 |  |  | 1 | 1 | 4 |  | Go-live | bar: W1
E7 | Environments and pipeline | Production provisioned at production topology; backups, monitoring, restore test | iorta TechNXT | iorta TechNXT DevOps lead | Environment sheet; restore test record | E5 | 5 | 4 | 9 |  |  | 1 | 2 | 13 |  | Go-live | bar: W1 to W2
E6 | Environments and pipeline | First deployment through the pipeline (CI, deploy, smoke test) to Dev and UAT (and SIT) | iorta TechNXT | iorta TechNXT DevOps lead | Deploy run summaries; smoke test passed | E4, E5, E3 | 1 | 5 | 6 |  |  | 2 | 2 | 4 |  | Go-live | bar: W2
Discovery and fit-gap
D1 | Discovery and fit-gap | Process workshops on the delivered system: organisation, sales, placement, servicing, claims, billing, remittance, commission, ledger, tax, distribution | iorta TechNXT | iorta TechNXT consultants | Workshop notes; decisions in the configuration workbook | M1 | 7 | 0 | 7 |  |  | 1 | 2 | 2 |  | Go-live | bar: W1 to W2
D2 | Discovery and fit-gap | Compliance workshop: AML/CFT programme, IC registers, complaints, breach procedure, masking by role | iorta TechNXT | iorta TechNXT consultant with the compliance officer and DPO | Compliance decisions recorded | M4 | 1 | 1 | 2 |  |  | 1 | 1 | 10 |  | Go-live | bar: W1
D3 | Discovery and fit-gap | Integration workshop: banks, SMS or Viber, CTPL authentication and LTO, insurers, payment gateway, BIR EIS, AMLC reporting | iorta TechNXT | iorta TechNXT technical lead | Integration list with partner contacts | M4 | 1 | 1 | 2 |  |  | 1 | 1 | 10 |  | Go-live | bar: W1
D4 | Discovery and fit-gap | Branding workshop: theme, logo, sign-in picture, documents, e-signatures, brand pack choice | iorta TechNXT | iorta TechNXT consultant | Branding decisions; client brand pack needed or not, with its contract reference | M4 | 1 | 1 | 2 |  |  | 1 | 1 | 10 |  | Go-live | bar: W1
D5 | Discovery and fit-gap | Configuration decisions and fit-gap register signed | Broker | Broker process owners | Signed fit-gap register | D1, D2, D3, D4, M2 | 0 | 7 | 7 |  |  | 2 | 2 | 5 |  | Go-live | bar: W2
Client inputs
I10 | Client inputs | UAT testers and sign-off authority named | Broker | Broker PM | UAT roster | M4 | 2 | 1 | 3 |  |  | 1 | 1 | 18 |  | Go-live | bar: W1
I4 | Client inputs | SMTP mailbox and credentials | Broker | Broker IT head | Mailbox in the secret store | M3 | 3 | 1 | 4 |  |  | 1 | 1 | 23 |  | Go-live | bar: W1
I1 | Client inputs | Insurer list and agreements, commission and referrer rates, product list | Broker | Broker key users | Filled sheets of the configuration kit | M3 | 4 | 1 | 5 |  |  | 1 | 1 | 0 | Yes | Go-live | bar: W1
I2 | Client inputs | Chart of accounts and the accountant's mapping decisions | Broker | Broker Accounting Manager | Chart of Accounts sheet; mapping decisions | M3 | 4 | 1 | 5 |  |  | 1 | 1 | 0 | Yes | Go-live | bar: W1
I3 | Client inputs | User list with roles, branches and reporting lines (My Team follows the reporting line) | Broker | Broker System Administrator | Users sheet | M3 | 4 | 1 | 5 |  |  | 1 | 1 | 0 | Yes | Go-live | bar: W1
I5 | Client inputs | Bank accounts, one statement export per account, bank contacts for payment files, payee bank accounts | Broker | Broker Accounting | Statement samples; Payee Bank Accounts sheet | M3 | 5 | 1 | 6 |  |  | 1 | 2 | 19 |  | Feature only | bar: W1 to W2
I7 | Client inputs | COC number series from each insurer | Broker | Broker Operations | COC Series sheet | M3 | 5 | 1 | 6 |  |  | 1 | 2 |  |  | Feature only | bar: W1 to W2
I9 | Client inputs | Training rooms, devices and attendance list | Broker | Broker PM | Training schedule | M4 | 5 | 1 | 6 |  |  | 1 | 2 | 17 |  | Go-live | bar: W1 to W2
I8 | Client inputs | Logo, sign-in picture, signatories with e-signature consent | Broker | Broker marketing and signatories | Images; consents on file | D4 | 3 | 2 | 5 |  |  | 1 | 1 | 12 |  | Go-live | bar: W1
I6 | Client inputs | Partner contracts and credentials: SMS provider, CTPL authentication provider, payment gateway, insurer API access | Broker | Broker IT head and sponsor | Signed contracts; credentials in the secret store | D3 | 8 | 2 | 10 |  |  | 1 | 2 |  |  | Feature only | bar: W1 to W2
Regulatory registrations
R3 | Regulatory registrations | AMLC: registration of the broker as covered person, portal access, institution code | Broker | Broker compliance officer | Portal access; aml.amlc_institution_code | M1 | 15 | 0 | 15 |  |  | 1 | 3 | 12 |  | Go-live | bar: W1 to W3
R1 | Regulatory registrations | BIR: Authority to Print or CAS registration and the invoice serial range confirmed (new or existing); last numbers used | Broker | Broker Accounting Manager with the tax adviser | ATP or CAS acknowledgement; invoice.* settings | M1 | 20 | 0 | 20 |  |  | 1 | 4 | 2 |  | Go-live | bar: W1 to W4
R5 | Regulatory registrations | NPC: registration of the DPO and the data processing systems confirmed; privacy notice version | Broker | Broker DPO | NPC registration; privacy.notice_version | M1 | 20 | 0 | 20 |  |  | 1 | 4 | 8 |  | Go-live | bar: W1 to W4
R2 | Regulatory registrations | BIR: EIS enrolment and certification (when the broker is covered) | Broker | Broker Accounting Manager | EIS accreditation id and credentials | M1 | 30 | 0 | 30 |  |  | 1 | 6 |  |  | Feature only | bar: W1 to W6
R4 | Regulatory registrations | IC: licence data of the firm, officers and agents; certificates of authority of the insurers | Broker | Broker compliance officer | Licence copies; certificate numbers and validity | M4 | 5 | 1 | 6 |  |  | 1 | 2 | 10 |  | Go-live | bar: W1 to W2
R8 | Regulatory registrations | Contract reference covering the use of the client's marks on the engagement file (client brand pack only) | Broker | Broker sponsor | Contract reference on the engagement file | D4 | 3 | 2 | 5 |  |  | 1 | 1 |  |  | Feature only | bar: W1
R7 | Regulatory registrations | Screening lists: UN and AMLC lists obtained; PEP list licence from a provider (when used) | Broker | Broker compliance officer | List files and licence | D2 | 10 | 2 | 12 |  |  | 1 | 3 | 15 |  | Go-live | bar: W1 to W3
R6 | Regulatory registrations | Tax adviser confirmation: tax codes, ATC, rates, invoice and receipt wording, VAT treatment of commission | Broker | Broker tax adviser | Written confirmation | C3SS+3d | 5 | 15 | 20 |  |  | 4 | 4 | 8 |  | Go-live | bar: W4
Configuration (go-live configuration kit)
C1 | Configuration (go-live configuration kit) | Configuration kit filled: company, settings, PSGC addresses, branches, users, chart of accounts, banks, insurers, products, commission, taxes, authority limits, numbering | Broker | Broker key users with iorta TechNXT consultants | Filled configuration workbook | D1SS+3d, I1, I2, I3 | 5 | 5 | 10 |  |  | 2 | 2 | 0 | Yes | Go-live | bar: W2
C2 | Configuration (go-live configuration kit) | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | iorta TechNXT | iorta TechNXT consultant | Batch Loaded; load history | C1, E6 | 2 | 10 | 12 |  |  | 3 | 3 | 0 | Yes | Go-live | bar: W3
C4 | Configuration (go-live configuration kit) | Configuration promoted to UAT for the first mock load (Current data workbook) | iorta TechNXT | iorta TechNXT consultant | Load history in UAT | C2 | 1 | 12 | 13 |  |  | 3 | 3 | 6 |  | Go-live | bar: W3
C3 | Configuration (go-live configuration kit) | On-screen configuration: Product Configurator (templates, rating factors, acceptance rules, document templates, market mapping), tax codes, posting rules, approvals, roles, schedules | iorta TechNXT | iorta TechNXT consultants | Configuration workbook updated with the values set | C2, D5 | 7 | 12 | 19 |  |  | 3 | 4 | 0 | Yes | Go-live | bar: W3 to W4
C5 | Configuration (go-live configuration kit) | Configuration complete | iorta TechNXT | iorta TechNXT delivery lead | Checklist of GO_LIVE_DATA_SETUP steps 1 to 12 | C3, K1, B1 | 0 | 19 | 19 |  |  | 4 | 4 | 1 |  | Go-live | bar: W4
Compliance set-up
K1 | Compliance set-up | Compliance set-up: AML settings, risk factors, monitoring rules; licence register, fit and proper, insurer authority; complaints and breach settings; view:pii grants and masking | iorta TechNXT | iorta TechNXT consultant with the compliance officer | AML Settings saved; registers filled | C2, D2, R4 | 4 | 12 | 16 |  |  | 3 | 4 | 4 |  | Go-live | bar: W3 to W4
K2 | Compliance set-up | Screening lists loaded (UN, AMLC, PEP, internal); clients rescreened | Broker | Broker compliance officer | Versions on Screening Lists; rescreen result | K1, R7 | 1 | 16 | 17 |  |  | 4 | 4 | 11 |  | Go-live | bar: W4
K3 | Compliance set-up | AMLC report file test: CTR file generated in UAT and checked against the AMLC portal requirements | Broker | Broker compliance officer | Test file; portal access confirmed | K1, R3 | 1 | 16 | 17 |  |  | 4 | 4 | 11 |  | Go-live | bar: W4
Branding and brand pack
B1 | Branding and brand pack | Theme and Branding, letterhead, sign-in page, branded documents and e-mails; e-signatures captured and mapped; brand pack exported | iorta TechNXT | iorta TechNXT consultant with the broker System Administrator | Brand pack file; sample documents approved | C2, I8 | 3 | 12 | 15 |  |  | 3 | 3 | 5 |  | Go-live | bar: W3
B2 | Branding and brand pack | Client brand pack applied only in that client's environments under its contract with iorta TechNXT (for example the Toyota Insurance Services pack) | iorta TechNXT | iorta TechNXT consultant | Pack enabled with the engagement confirmation; contract reference on file | B1, R8 | 1 | 15 | 16 |  |  | 4 | 4 |  |  | Feature only | bar: W4
Integrations with partners
N1 | Integrations with partners | E-mail: SMTP set, password reset and approval link tested | iorta TechNXT | iorta TechNXT DevOps lead | Test e-mails received | E6, I4 | 1 | 6 | 7 |  |  | 2 | 2 | 21 |  | Go-live | bar: W2
N2 | Integrations with partners | Bank statement formats: one statement per bank account imported with a balancing preview | iorta TechNXT | iorta TechNXT consultant with Accounting | Import preview per account | C2, I5 | 3 | 12 | 15 |  |  | 3 | 3 | 13 |  | Go-live | bar: W3
N7 | Integrations with partners | Payment gateway: sandbox payment receipted, then one live test payment | Partner | Payment gateway, with Accounting | Receipt of the sandbox payment | C2, I6 | 3 | 12 | 15 |  |  | 3 | 3 |  |  | Feature only | bar: W3
N4 | Integrations with partners | SMS or Viber connector: provider account, sender name, live test message | Partner | SMS provider, with the broker IT head | Connector Live; test message in the outbox | C2, I6 | 5 | 12 | 17 |  |  | 3 | 4 |  |  | Feature only | bar: W3 to W4
N5 | Integrations with partners | CTPL authentication provider and LTO feed: broker accredited, COC series loaded, live authentication of one COC | Partner | IC-accredited authentication provider, with Operations | Authenticated COC; LTO column result | C2, I6, I7 | 8 | 12 | 20 |  |  | 3 | 4 |  |  | Feature only | bar: W3 to W4
N3 | Integrations with partners | Bank payment files: each layout validated with the bank and a test file accepted by the bank | Partner | Bank, with Accounting and iorta TechNXT | Bank acceptance of the test file | C2, I5 | 10 | 12 | 22 |  |  | 3 | 5 |  |  | Feature only | bar: W3 to W5
N6 | Integrations with partners | Insurer API connectors: mapping per insurer, preview, test issuance and claim status with the insurer | Partner | Insurers, with the Processing Team | Accepted test request per insurer | C3SS+2d, I6 | 10 | 14 | 24 |  |  | 3 | 5 |  |  | Feature only | bar: W3 to W5
N8 | Integrations with partners | BIR EIS connector set in test mode; payloads checked | iorta TechNXT | iorta TechNXT consultant | Accepted test submissions | C3 | 1 | 19 | 20 |  |  | 4 | 4 |  |  | Feature only | bar: W4
N9 | Integrations with partners | BIR EIS connector live (after enrolment); earlier invoices queued | iorta TechNXT | iorta TechNXT consultant with Accounting | Accepted live submission | N8, R2, X6 | 2 | 30 | 32 |  |  | 7 | 7 |  |  | Feature only
Data migration (go-live migration kit)
G1 | Data migration (go-live migration kit) | Extraction and cleansing of the old system data for the first mock load | Broker | Broker data owners | Extract files; data quality notes | M3 | 8 | 1 | 9 |  |  | 1 | 2 | 10 |  | Go-live | bar: W1 to W2
G2 | Data migration (go-live migration kit) | Mapping to the migration kit (clients, policies, open items, open claims, opening balances) | iorta TechNXT | iorta TechNXT migration lead | Mapping sheets | G1SS+3d | 3 | 4 | 7 |  |  | 1 | 2 | 12 |  | Go-live | bar: W1 to W2
G3 | Data migration (go-live migration kit) | Mock load 1: cutover date set, validate, errors workbook, load, reconciliation | iorta TechNXT | iorta TechNXT migration lead | Reconciliation workbook signed | G1, G2, C4, C2 | 3 | 13 | 16 |  |  | 3 | 4 | 6 |  | Go-live | bar: W3 to W4
G4 | Data migration (go-live migration kit) | Mock load 2 on a fresh extract, with transaction reset before it | iorta TechNXT | iorta TechNXT migration lead | Reconciliation workbook signed | G3, C5 | 3 | 19 | 22 |  |  | 4 | 5 | 3 |  | Go-live | bar: W4 to W5
Training
L2 | Training | Compliance officer, DPO and System Administrator training on the compliance and privacy screens | iorta TechNXT | iorta TechNXT consultant | Attendance and assessment | K1 | 1 | 16 | 17 |  |  | 4 | 4 | 11 |  | Go-live | bar: W4
L1 | Training | Train-the-trainer for key users, with trainer skills and teach-back | iorta TechNXT | iorta TechNXT consultants | Key users passed at 90% | C5 | 3 | 19 | 22 |  |  | 4 | 5 | 1 |  | Go-live | bar: W4 to W5
L3 | Training | End-user training per role, run by key users | Broker | Broker key users | Every user trained and assessed | L1, T3, I9 | 5 | 22 | 27 |  |  | 5 | 6 | 1 |  | Go-live | bar: W5 to W6
SIT and UAT
T1 | SIT and UAT | System integration test in Dev (small, medium) or SIT (large, enterprise): end-to-end flows, uat-scenario.js, connectors in test mode | iorta TechNXT | iorta TechNXT test lead | SIT results; defect log | C3SS+4d, C2 | 4 | 16 | 20 |  |  | 4 | 4 | 0 | Yes | Go-live | bar: W4
T2 | SIT and UAT | SIT exit | iorta TechNXT | iorta TechNXT test lead | SIT exit report | T1, C5 | 0 | 20 | 20 |  |  | 4 | 4 | 0 | Yes | Go-live | bar: W4
T3 | SIT and UAT | Release candidate and frozen configuration promoted to UAT (Current data workbook, brand pack); comparison report clean | iorta TechNXT | iorta TechNXT delivery lead | Deploy run; comparison workbook | T2, E3 | 1 | 20 | 21 |  |  | 5 | 5 | 0 | Yes | Go-live | bar: W5
T4 | SIT and UAT | UAT cycles with the UAT scripts and broker scenarios, including compliance, BIR and integration scripts | Broker | Broker key users | UAT results per script | T3, I10 | 6 | 21 | 27 |  |  | 5 | 6 | 0 | Yes | Go-live | bar: W5 to W6
T5 | SIT and UAT | UAT sign-off | Broker | Broker sponsor and process owners | UAT Sign-off Certificate (Form 1) | T4, R6 | 0 | 27 | 27 |  |  | 6 | 6 | 1 |  | Go-live | bar: W6
Rehearsal and cutover
X1 | Rehearsal and cutover | Release tag and frozen configuration deployed to Production; production smoke test; transaction reset | iorta TechNXT | iorta TechNXT DevOps lead | Deploy run; smoke test record; reset audit entry | T3, E7, R1 | 2 | 21 | 23 |  |  | 5 | 5 | 1 |  | Go-live | bar: W5
X2 | Rehearsal and cutover | Pre-Prod created from a production backup (masked when people without production access take part) | iorta TechNXT | iorta TechNXT DevOps lead | Restore record (counts as a restore test) | X1 | 1 | 23 | 24 |  |  | 5 | 5 | 1 |  | Go-live | bar: W5
X3 | Rehearsal and cutover | Cutover rehearsal in Pre-Prod: reset, migration load of a fresh extract, reconciliation, go-live lock, comparison against Production, timings | iorta TechNXT | iorta TechNXT migration lead | Rehearsal log; reconciliation signed | X2, G4, T4SS+4d | 3 | 25 | 28 |  |  | 6 | 6 | 0 | Yes | Go-live | bar: W6
X4 | Rehearsal and cutover | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | Broker | Steering committee | Minutes | X3, T5, L3, L2, K2, K3, N1, N2, R5, B1 | 0 | 28 | 28 |  |  | 6 | 6 | 0 | Yes | Go-live | bar: W6
X5 | Rehearsal and cutover | Cutover: freeze, final extract, final load, reconciliation, go/no-go 2, golive.locked, mask:data --register-production | Broker | Broker PM with the iorta TechNXT migration lead | Signed reconciliation; go decision; audit entries | X4 | 2 | 28 | 30 |  |  | 6 | 6 | 0 | Yes | Go-live | bar: W6
X6 | Rehearsal and cutover | Go-live | Broker | Broker sponsor | First day of transactions in BrokerVerse | X5 | 0 | 30 | 30 |  |  | 7 | 7 | 0 | Yes | Go-live | bar: W7
Hypercare
H1 | Hypercare | Hypercare: daily check-ins in week 1, then weekly; first receipts, remittances, bank imports and payment files watched | iorta TechNXT | iorta TechNXT PM | Hypercare log | X6 | 10 | 30 | 40 |  |  | 7 | 8 |  |  | Hypercare exit | bar: W7 to W8
H2 | Hypercare | First month-end close and BIR working papers of the first month supported | Broker | Broker Accounting Manager | Approved Month-End Close run | X6+5d | 5 | 35 | 40 |  |  | 8 | 8 |  |  | Hypercare exit | bar: W8
H3 | Hypercare | Knowledge transfer, configuration baseline (Current data workbook of Production), handover; Pre-Prod removed | iorta TechNXT | iorta TechNXT PM and support manager | Hypercare Exit and Handover Certificate | H1, H2 | 0 | 40 | 40 |  |  | 8 | 8 |  |  | Hypercare exit | bar: W8
Formulas:
Start date = WORKDAY(D2,[Start day])
Finish date = IF([Duration (working days)]=0,[Start date],WORKDAY(D2,[Finish day]-1))

## Medium
BrokerVerse OOTB implementation plan: Medium broker (12 weeks, go-live at the start of week 10)
Kick-off date (a Monday): |  |  | 2026-11-02 |  | Type the kick-off date in the yellow cell: start and finish dates follow (working days, weekends skipped; add holidays as a third WORKDAY argument). Environments: Dev, UAT, Production; Pre-Prod temporary. Mock loads 1 and 2 in UAT; the cutover rehearsal in Pre-Prod is the third load.
Bars: blue iorta TechNXT, green broker, gold partner; red border and red ID = on the critical path to go-live. Float = working days a task can slip before the go-live date moves (empty: the task does not hold the go-live).
ID | Phase | Task | Party | Owner role | Deliverable or evidence | Predecessors | Duration (working days) | Start day | Finish day | Start date | Finish date | Start week | End week | Float to go-live (days) | Critical | Holds back | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Mobilisation
M1 | Mobilisation | Kick-off | iorta TechNXT | iorta TechNXT PM | Kick-off held; plan and go-live date confirmed |  | 0 | 0 | 0 |  |  | 1 | 1 | 0 | Yes | Go-live | bar: W1
M3 | Mobilisation | Data request list and the go-live kits issued (configuration and migration workbooks, upload templates) | iorta TechNXT | iorta TechNXT PM | Data request list; blank workbooks handed over | M1 | 1 | 0 | 1 |  |  | 1 | 1 | 0 | Yes | Go-live | bar: W1
M4 | Mobilisation | Broker team named: PM, key users, Accounting Manager, System Administrator, compliance officer, DPO | Broker | Broker sponsor | Named team with committed time | M1 | 2 | 0 | 2 |  |  | 1 | 1 | 14 |  | Go-live | bar: W1
M5 | Mobilisation | Hosting option, environment set and data location confirmed; environments ordered | Broker | Broker sponsor and IT head | Order Form hosting fields; transfer decision recorded | M1 | 2 | 0 | 2 |  |  | 1 | 1 | 8 |  | Go-live | bar: W1
M2 | Mobilisation | Project charter, baselined plan, governance calendar, RAID log | iorta TechNXT | iorta TechNXT PM | Charter and plan signed | M1 | 3 | 0 | 3 |  |  | 1 | 1 | 16 |  | Go-live | bar: W1
Environments and pipeline
E1 | Environments and pipeline | Dev provisioned | iorta TechNXT | iorta TechNXT DevOps lead | Environment sheet: Dev | M5 | 3 | 2 | 5 |  |  | 1 | 1 | 8 |  | Go-live | bar: W1
E3 | Environments and pipeline | UAT provisioned | iorta TechNXT | iorta TechNXT DevOps lead | Environment sheet: UAT | M5 | 3 | 2 | 5 |  |  | 1 | 1 | 10 |  | Go-live | bar: W1
E5 | Environments and pipeline | Application secrets per environment in the secret store: JWT_SECRET, DATA_ENCRYPTION_KEY, PII_ENCRYPTION_KEY generated; key custody and escrow copy agreed | iorta TechNXT | iorta TechNXT DevOps lead with the broker IT head | Key custody record signed by both | E1 | 1 | 5 | 6 |  |  | 2 | 2 | 9 |  | Go-live | bar: W2
E4 | Environments and pipeline | GitHub Environments (dev, sit, uat, preprod, production): protection rules, reviewers, variables, environment secrets | iorta TechNXT | iorta TechNXT DevOps lead | Settings recorded in the environment sheet | E1 | 2 | 5 | 7 |  |  | 2 | 2 | 8 |  | Go-live | bar: W2
E7 | Environments and pipeline | Production provisioned at production topology; backups, monitoring, restore test | iorta TechNXT | iorta TechNXT DevOps lead | Environment sheet; restore test record | E5 | 8 | 6 | 14 |  |  | 2 | 3 | 23 |  | Go-live | bar: W2 to W3
E6 | Environments and pipeline | First deployment through the pipeline (CI, deploy, smoke test) to Dev and UAT (and SIT) | iorta TechNXT | iorta TechNXT DevOps lead | Deploy run summaries; smoke test passed | E4, E5, E3 | 1 | 7 | 8 |  |  | 2 | 2 | 8 |  | Go-live | bar: W2
Discovery and fit-gap
D1 | Discovery and fit-gap | Process workshops on the delivered system: organisation, sales, placement, servicing, claims, billing, remittance, commission, ledger, tax, distribution | iorta TechNXT | iorta TechNXT consultants | Workshop notes; decisions in the configuration workbook | M1 | 11 | 0 | 11 |  |  | 1 | 3 | 3 |  | Go-live | bar: W1 to W3
D4 | Discovery and fit-gap | Branding workshop: theme, logo, sign-in picture, documents, e-signatures, brand pack choice | iorta TechNXT | iorta TechNXT consultant | Branding decisions; client brand pack needed or not, with its contract reference | M4 | 1 | 2 | 3 |  |  | 1 | 1 | 16 |  | Go-live | bar: W1
D2 | Discovery and fit-gap | Compliance workshop: AML/CFT programme, IC registers, complaints, breach procedure, masking by role | iorta TechNXT | iorta TechNXT consultant with the compliance officer and DPO | Compliance decisions recorded | M4 | 2 | 2 | 4 |  |  | 1 | 1 | 15 |  | Go-live | bar: W1
D3 | Discovery and fit-gap | Integration workshop: banks, SMS or Viber, CTPL authentication and LTO, insurers, payment gateway, BIR EIS, AMLC reporting | iorta TechNXT | iorta TechNXT technical lead | Integration list with partner contacts | M4 | 2 | 2 | 4 |  |  | 1 | 1 | 15 |  | Go-live | bar: W1
D5 | Discovery and fit-gap | Configuration decisions and fit-gap register signed | Broker | Broker process owners | Signed fit-gap register | D1, D2, D3, D4, M2 | 0 | 11 | 11 |  |  | 3 | 3 | 8 |  | Go-live | bar: W3
Client inputs
I4 | Client inputs | SMTP mailbox and credentials | Broker | Broker IT head | Mailbox in the secret store | M3 | 5 | 1 | 6 |  |  | 1 | 2 | 36 |  | Go-live | bar: W1 to W2
I3 | Client inputs | User list with roles, branches and reporting lines (My Team follows the reporting line) | Broker | Broker System Administrator | Users sheet | M3 | 6 | 1 | 7 |  |  | 1 | 2 | 1 |  | Go-live | bar: W1 to W2
I1 | Client inputs | Insurer list and agreements, commission and referrer rates, product list | Broker | Broker key users | Filled sheets of the configuration kit | M3 | 7 | 1 | 8 |  |  | 1 | 2 | 0 | Yes | Go-live | bar: W1 to W2
I2 | Client inputs | Chart of accounts and the accountant's mapping decisions | Broker | Broker Accounting Manager | Chart of Accounts sheet; mapping decisions | M3 | 7 | 1 | 8 |  |  | 1 | 2 | 0 | Yes | Go-live | bar: W1 to W2
I5 | Client inputs | Bank accounts, one statement export per account, bank contacts for payment files, payee bank accounts | Broker | Broker Accounting | Statement samples; Payee Bank Accounts sheet | M3 | 8 | 1 | 9 |  |  | 1 | 2 | 30 |  | Feature only | bar: W1 to W2
I7 | Client inputs | COC number series from each insurer | Broker | Broker Operations | COC Series sheet | M3 | 8 | 1 | 9 |  |  | 1 | 2 |  |  | Feature only | bar: W1 to W2
I10 | Client inputs | UAT testers and sign-off authority named | Broker | Broker PM | UAT roster | M4 | 2 | 2 | 4 |  |  | 1 | 1 | 31 |  | Go-live | bar: W1
I9 | Client inputs | Training rooms, devices and attendance list | Broker | Broker PM | Training schedule | M4 | 5 | 2 | 7 |  |  | 1 | 2 | 28 |  | Go-live | bar: W1 to W2
I8 | Client inputs | Logo, sign-in picture, signatories with e-signature consent | Broker | Broker marketing and signatories | Images; consents on file | D4 | 5 | 3 | 8 |  |  | 1 | 2 | 18 |  | Go-live | bar: W1 to W2
I6 | Client inputs | Partner contracts and credentials: SMS provider, CTPL authentication provider, payment gateway, insurer API access | Broker | Broker IT head and sponsor | Signed contracts; credentials in the secret store | D3 | 10 | 4 | 14 |  |  | 1 | 3 |  |  | Feature only | bar: W1 to W3
Regulatory registrations
R3 | Regulatory registrations | AMLC: registration of the broker as covered person, portal access, institution code | Broker | Broker compliance officer | Portal access; aml.amlc_institution_code | M1 | 20 | 0 | 20 |  |  | 1 | 4 | 22 |  | Go-live | bar: W1 to W4
R1 | Regulatory registrations | BIR: Authority to Print or CAS registration and the invoice serial range confirmed (new or existing); last numbers used | Broker | Broker Accounting Manager with the tax adviser | ATP or CAS acknowledgement; invoice.* settings | M1 | 25 | 0 | 25 |  |  | 1 | 5 | 12 |  | Go-live | bar: W1 to W5
R5 | Regulatory registrations | NPC: registration of the DPO and the data processing systems confirmed; privacy notice version | Broker | Broker DPO | NPC registration; privacy.notice_version | M1 | 25 | 0 | 25 |  |  | 1 | 5 | 18 |  | Go-live | bar: W1 to W5
R2 | Regulatory registrations | BIR: EIS enrolment and certification (when the broker is covered) | Broker | Broker Accounting Manager | EIS accreditation id and credentials | M1 | 30 | 0 | 30 |  |  | 1 | 6 |  |  | Feature only | bar: W1 to W6
R4 | Regulatory registrations | IC: licence data of the firm, officers and agents; certificates of authority of the insurers | Broker | Broker compliance officer | Licence copies; certificate numbers and validity | M4 | 8 | 2 | 10 |  |  | 1 | 2 | 14 |  | Go-live | bar: W1 to W2
R8 | Regulatory registrations | Contract reference covering the use of the client's marks on the engagement file (client brand pack only) | Broker | Broker sponsor | Contract reference on the engagement file | D4 | 5 | 3 | 8 |  |  | 1 | 2 |  |  | Feature only | bar: W1 to W2
R7 | Regulatory registrations | Screening lists: UN and AMLC lists obtained; PEP list licence from a provider (when used) | Broker | Broker compliance officer | List files and licence | D2 | 12 | 4 | 16 |  |  | 1 | 4 | 26 |  | Go-live | bar: W1 to W4
R6 | Regulatory registrations | Tax adviser confirmation: tax codes, ATC, rates, invoice and receipt wording, VAT treatment of commission | Broker | Broker tax adviser | Written confirmation | C3SS+5d | 5 | 24 | 29 |  |  | 5 | 6 | 14 |  | Go-live | bar: W5 to W6
Configuration (go-live configuration kit)
C1 | Configuration (go-live configuration kit) | Configuration kit filled: company, settings, PSGC addresses, branches, users, chart of accounts, banks, insurers, products, commission, taxes, authority limits, numbering | Broker | Broker key users with iorta TechNXT consultants | Filled configuration workbook | D1SS+5d, I1, I2, I3 | 8 | 8 | 16 |  |  | 2 | 4 | 0 | Yes | Go-live | bar: W2 to W4
C2 | Configuration (go-live configuration kit) | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | iorta TechNXT | iorta TechNXT consultant | Batch Loaded; load history | C1, E6 | 3 | 16 | 19 |  |  | 4 | 4 | 0 | Yes | Go-live | bar: W4
C4 | Configuration (go-live configuration kit) | Configuration promoted to UAT for the first mock load (Current data workbook) | iorta TechNXT | iorta TechNXT consultant | Load history in UAT | C2 | 1 | 19 | 20 |  |  | 4 | 4 | 13 |  | Go-live | bar: W4
C3 | Configuration (go-live configuration kit) | On-screen configuration: Product Configurator (templates, rating factors, acceptance rules, document templates, market mapping), tax codes, posting rules, approvals, roles, schedules | iorta TechNXT | iorta TechNXT consultants | Configuration workbook updated with the values set | C2, D5 | 11 | 19 | 30 |  |  | 4 | 6 | 0 | Yes | Go-live | bar: W4 to W6
C5 | Configuration (go-live configuration kit) | Configuration complete | iorta TechNXT | iorta TechNXT delivery lead | Checklist of GO_LIVE_DATA_SETUP steps 1 to 12 | C3, K1, B1 | 0 | 30 | 30 |  |  | 6 | 6 | 0 | Yes | Go-live | bar: W6
Compliance set-up
K1 | Compliance set-up | Compliance set-up: AML settings, risk factors, monitoring rules; licence register, fit and proper, insurer authority; complaints and breach settings; view:pii grants and masking | iorta TechNXT | iorta TechNXT consultant with the compliance officer | AML Settings saved; registers filled | C2, D2, R4 | 6 | 19 | 25 |  |  | 4 | 5 | 5 |  | Go-live | bar: W4 to W5
K2 | Compliance set-up | Screening lists loaded (UN, AMLC, PEP, internal); clients rescreened | Broker | Broker compliance officer | Versions on Screening Lists; rescreen result | K1, R7 | 1 | 25 | 26 |  |  | 6 | 6 | 17 |  | Go-live | bar: W6
K3 | Compliance set-up | AMLC report file test: CTR file generated in UAT and checked against the AMLC portal requirements | Broker | Broker compliance officer | Test file; portal access confirmed | K1, R3 | 1 | 25 | 26 |  |  | 6 | 6 | 17 |  | Go-live | bar: W6
Branding and brand pack
B1 | Branding and brand pack | Theme and Branding, letterhead, sign-in page, branded documents and e-mails; e-signatures captured and mapped; brand pack exported | iorta TechNXT | iorta TechNXT consultant with the broker System Administrator | Brand pack file; sample documents approved | C2, I8 | 4 | 19 | 23 |  |  | 4 | 5 | 7 |  | Go-live | bar: W4 to W5
B2 | Branding and brand pack | Client brand pack applied only in that client's environments under its contract with iorta TechNXT (for example the Toyota Insurance Services pack) | iorta TechNXT | iorta TechNXT consultant | Pack enabled with the engagement confirmation; contract reference on file | B1, R8 | 1 | 23 | 24 |  |  | 5 | 5 |  |  | Feature only | bar: W5
Integrations with partners
N1 | Integrations with partners | E-mail: SMTP set, password reset and approval link tested | iorta TechNXT | iorta TechNXT DevOps lead | Test e-mails received | E6, I4 | 1 | 8 | 9 |  |  | 2 | 2 | 34 |  | Go-live | bar: W2
N2 | Integrations with partners | Bank statement formats: one statement per bank account imported with a balancing preview | iorta TechNXT | iorta TechNXT consultant with Accounting | Import preview per account | C2, I5 | 4 | 19 | 23 |  |  | 4 | 5 | 20 |  | Go-live | bar: W4 to W5
N7 | Integrations with partners | Payment gateway: sandbox payment receipted, then one live test payment | Partner | Payment gateway, with Accounting | Receipt of the sandbox payment | C2, I6 | 5 | 19 | 24 |  |  | 4 | 5 |  |  | Feature only | bar: W4 to W5
N4 | Integrations with partners | SMS or Viber connector: provider account, sender name, live test message | Partner | SMS provider, with the broker IT head | Connector Live; test message in the outbox | C2, I6 | 8 | 19 | 27 |  |  | 4 | 6 |  |  | Feature only | bar: W4 to W6
N5 | Integrations with partners | CTPL authentication provider and LTO feed: broker accredited, COC series loaded, live authentication of one COC | Partner | IC-accredited authentication provider, with Operations | Authenticated COC; LTO column result | C2, I6, I7 | 10 | 19 | 29 |  |  | 4 | 6 |  |  | Feature only | bar: W4 to W6
N3 | Integrations with partners | Bank payment files: each layout validated with the bank and a test file accepted by the bank | Partner | Bank, with Accounting and iorta TechNXT | Bank acceptance of the test file | C2, I5 | 15 | 19 | 34 |  |  | 4 | 7 |  |  | Feature only | bar: W4 to W7
N6 | Integrations with partners | Insurer API connectors: mapping per insurer, preview, test issuance and claim status with the insurer | Partner | Insurers, with the Processing Team | Accepted test request per insurer | C3SS+2d, I6 | 15 | 21 | 36 |  |  | 5 | 8 |  |  | Feature only | bar: W5 to W8
N8 | Integrations with partners | BIR EIS connector set in test mode; payloads checked | iorta TechNXT | iorta TechNXT consultant | Accepted test submissions | C3 | 1 | 30 | 31 |  |  | 7 | 7 |  |  | Feature only | bar: W7
N9 | Integrations with partners | BIR EIS connector live (after enrolment); earlier invoices queued | iorta TechNXT | iorta TechNXT consultant with Accounting | Accepted live submission | N8, R2, X6 | 2 | 45 | 47 |  |  | 10 | 10 |  |  | Feature only
Data migration (go-live migration kit)
G1 | Data migration (go-live migration kit) | Extraction and cleansing of the old system data for the first mock load | Broker | Broker data owners | Extract files; data quality notes | M3 | 12 | 1 | 13 |  |  | 1 | 3 | 20 |  | Go-live | bar: W1 to W3
G2 | Data migration (go-live migration kit) | Mapping to the migration kit (clients, policies, open items, open claims, opening balances) | iorta TechNXT | iorta TechNXT migration lead | Mapping sheets | G1SS+5d | 5 | 6 | 11 |  |  | 2 | 3 | 22 |  | Go-live | bar: W2 to W3
G3 | Data migration (go-live migration kit) | Mock load 1: cutover date set, validate, errors workbook, load, reconciliation | iorta TechNXT | iorta TechNXT migration lead | Reconciliation workbook signed | G1, G2, C4, C2 | 4 | 20 | 24 |  |  | 5 | 5 | 13 |  | Go-live | bar: W5
G4 | Data migration (go-live migration kit) | Mock load 2 on a fresh extract, with transaction reset before it | iorta TechNXT | iorta TechNXT migration lead | Reconciliation workbook signed | G3, C5 | 3 | 30 | 33 |  |  | 7 | 7 | 7 |  | Go-live | bar: W7
Training
L2 | Training | Compliance officer, DPO and System Administrator training on the compliance and privacy screens | iorta TechNXT | iorta TechNXT consultant | Attendance and assessment | K1 | 1 | 25 | 26 |  |  | 6 | 6 | 17 |  | Go-live | bar: W6
L1 | Training | Train-the-trainer for key users, with trainer skills and teach-back | iorta TechNXT | iorta TechNXT consultants | Key users passed at 90% | C5 | 5 | 30 | 35 |  |  | 7 | 7 | 0 | Yes | Go-live | bar: W7
L3 | Training | End-user training per role, run by key users | Broker | Broker key users | Every user trained and assessed | L1, T3, I9 | 8 | 35 | 43 |  |  | 8 | 9 | 0 | Yes | Go-live | bar: W8 to W9
SIT and UAT
T1 | SIT and UAT | System integration test in Dev (small, medium) or SIT (large, enterprise): end-to-end flows, uat-scenario.js, connectors in test mode | iorta TechNXT | iorta TechNXT test lead | SIT results; defect log | C3SS+6d, C2 | 9 | 25 | 34 |  |  | 6 | 7 | 0 | Yes | Go-live | bar: W6 to W7
T2 | SIT and UAT | SIT exit | iorta TechNXT | iorta TechNXT test lead | SIT exit report | T1, C5 | 0 | 34 | 34 |  |  | 7 | 7 | 0 | Yes | Go-live | bar: W7
T3 | SIT and UAT | Release candidate and frozen configuration promoted to UAT (Current data workbook, brand pack); comparison report clean | iorta TechNXT | iorta TechNXT delivery lead | Deploy run; comparison workbook | T2, E3 | 1 | 34 | 35 |  |  | 7 | 7 | 0 | Yes | Go-live | bar: W7
T4 | SIT and UAT | UAT cycles with the UAT scripts and broker scenarios, including compliance, BIR and integration scripts | Broker | Broker key users | UAT results per script | T3, I10 | 8 | 35 | 43 |  |  | 8 | 9 | 0 | Yes | Go-live | bar: W8 to W9
T5 | SIT and UAT | UAT sign-off | Broker | Broker sponsor and process owners | UAT Sign-off Certificate (Form 1) | T4, R6 | 0 | 43 | 43 |  |  | 9 | 9 | 0 | Yes | Go-live | bar: W9
Rehearsal and cutover
X1 | Rehearsal and cutover | Release tag and frozen configuration deployed to Production; production smoke test; transaction reset | iorta TechNXT | iorta TechNXT DevOps lead | Deploy run; smoke test record; reset audit entry | T3, E7, R1 | 2 | 35 | 37 |  |  | 8 | 8 | 2 |  | Go-live | bar: W8
X2 | Rehearsal and cutover | Pre-Prod created from a production backup (masked when people without production access take part) | iorta TechNXT | iorta TechNXT DevOps lead | Restore record (counts as a restore test) | X1 | 1 | 37 | 38 |  |  | 8 | 8 | 2 |  | Go-live | bar: W8
X3 | Rehearsal and cutover | Cutover rehearsal in Pre-Prod: reset, migration load of a fresh extract, reconciliation, go-live lock, comparison against Production, timings | iorta TechNXT | iorta TechNXT migration lead | Rehearsal log; reconciliation signed | X2, G4, T4SS+5d | 3 | 40 | 43 |  |  | 9 | 9 | 0 | Yes | Go-live | bar: W9
X4 | Rehearsal and cutover | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | Broker | Steering committee | Minutes | X3, T5, L3, L2, K2, K3, N1, N2, R5, B1 | 0 | 43 | 43 |  |  | 9 | 9 | 0 | Yes | Go-live | bar: W9
X5 | Rehearsal and cutover | Cutover: freeze, final extract, final load, reconciliation, go/no-go 2, golive.locked, mask:data --register-production | Broker | Broker PM with the iorta TechNXT migration lead | Signed reconciliation; go decision; audit entries | X4 | 2 | 43 | 45 |  |  | 9 | 9 | 0 | Yes | Go-live | bar: W9
X6 | Rehearsal and cutover | Go-live | Broker | Broker sponsor | First day of transactions in BrokerVerse | X5 | 0 | 45 | 45 |  |  | 10 | 10 | 0 | Yes | Go-live | bar: W10
Hypercare
H1 | Hypercare | Hypercare: daily check-ins in week 1, then weekly; first receipts, remittances, bank imports and payment files watched | iorta TechNXT | iorta TechNXT PM | Hypercare log | X6 | 15 | 45 | 60 |  |  | 10 | 12 |  |  | Hypercare exit | bar: W10 to W12
H2 | Hypercare | First month-end close and BIR working papers of the first month supported | Broker | Broker Accounting Manager | Approved Month-End Close run | X6+10d | 5 | 55 | 60 |  |  | 12 | 12 |  |  | Hypercare exit | bar: W12
H3 | Hypercare | Knowledge transfer, configuration baseline (Current data workbook of Production), handover; Pre-Prod removed | iorta TechNXT | iorta TechNXT PM and support manager | Hypercare Exit and Handover Certificate | H1, H2 | 0 | 60 | 60 |  |  | 12 | 12 |  |  | Hypercare exit | bar: W12
Formulas:
Start date = WORKDAY(D2,[Start day])
Finish date = IF([Duration (working days)]=0,[Start date],WORKDAY(D2,[Finish day]-1))

## Large
BrokerVerse OOTB implementation plan: Large broker (20 weeks, go-live at the start of week 15)
Kick-off date (a Monday): |  |  | 2026-11-02 |  | Type the kick-off date in the yellow cell: start and finish dates follow (working days, weekends skipped; add holidays as a third WORKDAY argument). Environments: Dev, SIT, UAT, Production (high availability); Pre-Prod temporary. Mock loads 1 and 2 in SIT, mock load 3 in UAT; the cutover rehearsal in Pre-Prod is the fourth load.
Bars: blue iorta TechNXT, green broker, gold partner; red border and red ID = on the critical path to go-live. Float = working days a task can slip before the go-live date moves (empty: the task does not hold the go-live).
ID | Phase | Task | Party | Owner role | Deliverable or evidence | Predecessors | Duration (working days) | Start day | Finish day | Start date | Finish date | Start week | End week | Float to go-live (days) | Critical | Holds back | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
Mobilisation
M1 | Mobilisation | Kick-off | iorta TechNXT | iorta TechNXT PM | Kick-off held; plan and go-live date confirmed |  | 0 | 0 | 0 |  |  | 1 | 1 | 0 | Yes | Go-live | bar: W1
M3 | Mobilisation | Data request list and the go-live kits issued (configuration and migration workbooks, upload templates) | iorta TechNXT | iorta TechNXT PM | Data request list; blank workbooks handed over | M1 | 1 | 0 | 1 |  |  | 1 | 1 | 0 | Yes | Go-live | bar: W1
M4 | Mobilisation | Broker team named: PM, key users, Accounting Manager, System Administrator, compliance officer, DPO | Broker | Broker sponsor | Named team with committed time | M1 | 3 | 0 | 3 |  |  | 1 | 1 | 24 |  | Go-live | bar: W1
M5 | Mobilisation | Hosting option, environment set and data location confirmed; environments ordered | Broker | Broker sponsor and IT head | Order Form hosting fields; transfer decision recorded | M1 | 3 | 0 | 3 |  |  | 1 | 1 | 12 |  | Go-live | bar: W1
M2 | Mobilisation | Project charter, baselined plan, governance calendar, RAID log | iorta TechNXT | iorta TechNXT PM | Charter and plan signed | M1 | 5 | 0 | 5 |  |  | 1 | 1 | 24 |  | Go-live | bar: W1
Environments and pipeline
E1 | Environments and pipeline | Dev provisioned | iorta TechNXT | iorta TechNXT DevOps lead | Environment sheet: Dev | M5 | 4 | 3 | 7 |  |  | 1 | 2 | 12 |  | Go-live | bar: W1 to W2
E3 | Environments and pipeline | UAT provisioned | iorta TechNXT | iorta TechNXT DevOps lead | Environment sheet: UAT | M5 | 4 | 3 | 7 |  |  | 1 | 2 | 16 |  | Go-live | bar: W1 to W2
E5 | Environments and pipeline | Application secrets per environment in the secret store: JWT_SECRET, DATA_ENCRYPTION_KEY, PII_ENCRYPTION_KEY generated; key custody and escrow copy agreed | iorta TechNXT | iorta TechNXT DevOps lead with the broker IT head | Key custody record signed by both | E1 | 2 | 7 | 9 |  |  | 2 | 2 | 14 |  | Go-live | bar: W2
E4 | Environments and pipeline | GitHub Environments (dev, sit, uat, preprod, production): protection rules, reviewers, variables, environment secrets | iorta TechNXT | iorta TechNXT DevOps lead | Settings recorded in the environment sheet | E1 | 3 | 7 | 10 |  |  | 2 | 2 | 13 |  | Go-live | bar: W2
E2 | Environments and pipeline | SIT provisioned (large and enterprise brokers) | iorta TechNXT | iorta TechNXT DevOps lead | Environment sheet: SIT | E1 | 4 | 7 | 11 |  |  | 2 | 3 | 12 |  | Go-live | bar: W2 to W3
E7 | Environments and pipeline | Production provisioned at production topology; backups, monitoring, restore test | iorta TechNXT | iorta TechNXT DevOps lead | Environment sheet; restore test record | E5 | 10 | 9 | 19 |  |  | 2 | 4 | 42 |  | Go-live | bar: W2 to W4
E6 | Environments and pipeline | First deployment through the pipeline (CI, deploy, smoke test) to Dev and UAT (and SIT) | iorta TechNXT | iorta TechNXT DevOps lead | Deploy run summaries; smoke test passed | E4, E5, E3, E2 | 2 | 11 | 13 |  |  | 3 | 3 | 12 |  | Go-live | bar: W3
Discovery and fit-gap
D1 | Discovery and fit-gap | Process workshops on the delivered system: organisation, sales, placement, servicing, claims, billing, remittance, commission, ledger, tax, distribution | iorta TechNXT | iorta TechNXT consultants | Workshop notes; decisions in the configuration workbook | M1 | 20 | 0 | 20 |  |  | 1 | 4 | 7 |  | Go-live | bar: W1 to W4
D4 | Discovery and fit-gap | Branding workshop: theme, logo, sign-in picture, documents, e-signatures, brand pack choice | iorta TechNXT | iorta TechNXT consultant | Branding decisions; client brand pack needed or not, with its contract reference | M4 | 1 | 3 | 4 |  |  | 1 | 1 | 25 |  | Go-live | bar: W1
D2 | Discovery and fit-gap | Compliance workshop: AML/CFT programme, IC registers, complaints, breach procedure, masking by role | iorta TechNXT | iorta TechNXT consultant with the compliance officer and DPO | Compliance decisions recorded | M4 | 2 | 3 | 5 |  |  | 1 | 1 | 24 |  | Go-live | bar: W1
D3 | Discovery and fit-gap | Integration workshop: banks, SMS or Viber, CTPL authentication and LTO, insurers, payment gateway, BIR EIS, AMLC reporting | iorta TechNXT | iorta TechNXT technical lead | Integration list with partner contacts | M4 | 2 | 3 | 5 |  |  | 1 | 1 | 24 |  | Go-live | bar: W1
D5 | Discovery and fit-gap | Configuration decisions and fit-gap register signed | Broker | Broker process owners | Signed fit-gap register | D1, D2, D3, D4, M2 | 0 | 20 | 20 |  |  | 4 | 4 | 9 |  | Go-live | bar: W4
Client inputs
I4 | Client inputs | SMTP mailbox and credentials | Broker | Broker IT head | Mailbox in the secret store | M3 | 5 | 1 | 6 |  |  | 1 | 2 | 60 |  | Go-live | bar: W1 to W2
I3 | Client inputs | User list with roles, branches and reporting lines (My Team follows the reporting line) | Broker | Broker System Administrator | Users sheet | M3 | 10 | 1 | 11 |  |  | 1 | 3 | 2 |  | Go-live | bar: W1 to W3
I5 | Client inputs | Bank accounts, one statement export per account, bank contacts for payment files, payee bank accounts | Broker | Broker Accounting | Statement samples; Payee Bank Accounts sheet | M3 | 10 | 1 | 11 |  |  | 1 | 3 | 51 |  | Feature only | bar: W1 to W3
I7 | Client inputs | COC number series from each insurer | Broker | Broker Operations | COC Series sheet | M3 | 10 | 1 | 11 |  |  | 1 | 3 |  |  | Feature only | bar: W1 to W3
I1 | Client inputs | Insurer list and agreements, commission and referrer rates, product list | Broker | Broker key users | Filled sheets of the configuration kit | M3 | 12 | 1 | 13 |  |  | 1 | 3 | 0 | Yes | Go-live | bar: W1 to W3
I2 | Client inputs | Chart of accounts and the accountant's mapping decisions | Broker | Broker Accounting Manager | Chart of Accounts sheet; mapping decisions | M3 | 12 | 1 | 13 |  |  | 1 | 3 | 0 | Yes | Go-live | bar: W1 to W3
I10 | Client inputs | UAT testers and sign-off authority named | Broker | Broker PM | UAT roster | M4 | 3 | 3 | 6 |  |  | 1 | 2 | 53 |  | Go-live | bar: W1 to W2
I9 | Client inputs | Training rooms, devices and attendance list | Broker | Broker PM | Training schedule | M4 | 5 | 3 | 8 |  |  | 1 | 2 | 52 |  | Go-live | bar: W1 to W2
I8 | Client inputs | Logo, sign-in picture, signatories with e-signature consent | Broker | Broker marketing and signatories | Images; consents on file | D4 | 5 | 4 | 9 |  |  | 1 | 2 | 38 |  | Go-live | bar: W1 to W2
I6 | Client inputs | Partner contracts and credentials: SMS provider, CTPL authentication provider, payment gateway, insurer API access | Broker | Broker IT head and sponsor | Signed contracts; credentials in the secret store | D3 | 15 | 5 | 20 |  |  | 2 | 4 |  |  | Feature only | bar: W2 to W4
Regulatory registrations
R3 | Regulatory registrations | AMLC: registration of the broker as covered person, portal access, institution code | Broker | Broker compliance officer | Portal access; aml.amlc_institution_code | M1 | 20 | 0 | 20 |  |  | 1 | 4 | 46 |  | Go-live | bar: W1 to W4
R1 | Regulatory registrations | BIR: Authority to Print or CAS registration and the invoice serial range confirmed (new or existing); last numbers used | Broker | Broker Accounting Manager with the tax adviser | ATP or CAS acknowledgement; invoice.* settings | M1 | 30 | 0 | 30 |  |  | 1 | 6 | 31 |  | Go-live | bar: W1 to W6
R2 | Regulatory registrations | BIR: EIS enrolment and certification (when the broker is covered) | Broker | Broker Accounting Manager | EIS accreditation id and credentials | M1 | 30 | 0 | 30 |  |  | 1 | 6 |  |  | Feature only | bar: W1 to W6
R5 | Regulatory registrations | NPC: registration of the DPO and the data processing systems confirmed; privacy notice version | Broker | Broker DPO | NPC registration; privacy.notice_version | M1 | 30 | 0 | 30 |  |  | 1 | 6 | 38 |  | Go-live | bar: W1 to W6
R4 | Regulatory registrations | IC: licence data of the firm, officers and agents; certificates of authority of the insurers | Broker | Broker compliance officer | Licence copies; certificate numbers and validity | M4 | 10 | 3 | 13 |  |  | 1 | 3 | 31 |  | Go-live | bar: W1 to W3
R8 | Regulatory registrations | Contract reference covering the use of the client's marks on the engagement file (client brand pack only) | Broker | Broker sponsor | Contract reference on the engagement file | D4 | 5 | 4 | 9 |  |  | 1 | 2 |  |  | Feature only | bar: W1 to W2
R7 | Regulatory registrations | Screening lists: UN and AMLC lists obtained; PEP list licence from a provider (when used) | Broker | Broker compliance officer | List files and licence | D2 | 15 | 5 | 20 |  |  | 2 | 4 | 47 |  | Go-live | bar: W2 to W4
R6 | Regulatory registrations | Tax adviser confirmation: tax codes, ATC, rates, invoice and receipt wording, VAT treatment of commission | Broker | Broker tax adviser | Written confirmation | C3SS+8d | 8 | 37 | 45 |  |  | 8 | 9 | 23 |  | Go-live | bar: W8 to W9
Configuration (go-live configuration kit)
C1 | Configuration (go-live configuration kit) | Configuration kit filled: company, settings, PSGC addresses, branches, users, chart of accounts, banks, insurers, products, commission, taxes, authority limits, numbering | Broker | Broker key users with iorta TechNXT consultants | Filled configuration workbook | D1SS+6d, I1, I2, I3 | 12 | 13 | 25 |  |  | 3 | 5 | 0 | Yes | Go-live | bar: W3 to W5
C2 | Configuration (go-live configuration kit) | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | iorta TechNXT | iorta TechNXT consultant | Batch Loaded; load history | C1, E6 | 4 | 25 | 29 |  |  | 6 | 6 | 0 | Yes | Go-live | bar: W6
C3 | Configuration (go-live configuration kit) | On-screen configuration: Product Configurator (templates, rating factors, acceptance rules, document templates, market mapping), tax codes, posting rules, approvals, roles, schedules | iorta TechNXT | iorta TechNXT consultants | Configuration workbook updated with the values set | C2, D5 | 18 | 29 | 47 |  |  | 6 | 10 | 0 | Yes | Go-live | bar: W6 to W10
C5 | Configuration (go-live configuration kit) | Configuration complete | iorta TechNXT | iorta TechNXT delivery lead | Checklist of GO_LIVE_DATA_SETUP steps 1 to 12 | C3, K1, B1 | 0 | 47 | 47 |  |  | 10 | 10 | 5 |  | Go-live | bar: W10
Compliance set-up
K1 | Compliance set-up | Compliance set-up: AML settings, risk factors, monitoring rules; licence register, fit and proper, insurer authority; complaints and breach settings; view:pii grants and masking | iorta TechNXT | iorta TechNXT consultant with the compliance officer | AML Settings saved; registers filled | C2, D2, R4 | 8 | 29 | 37 |  |  | 6 | 8 | 15 |  | Go-live | bar: W6 to W8
K2 | Compliance set-up | Screening lists loaded (UN, AMLC, PEP, internal); clients rescreened | Broker | Broker compliance officer | Versions on Screening Lists; rescreen result | K1, R7 | 1 | 37 | 38 |  |  | 8 | 8 | 30 |  | Go-live | bar: W8
K3 | Compliance set-up | AMLC report file test: CTR file generated in UAT and checked against the AMLC portal requirements | Broker | Broker compliance officer | Test file; portal access confirmed | K1, R3 | 2 | 37 | 39 |  |  | 8 | 8 | 29 |  | Go-live | bar: W8
Branding and brand pack
B1 | Branding and brand pack | Theme and Branding, letterhead, sign-in page, branded documents and e-mails; e-signatures captured and mapped; brand pack exported | iorta TechNXT | iorta TechNXT consultant with the broker System Administrator | Brand pack file; sample documents approved | C2, I8 | 5 | 29 | 34 |  |  | 6 | 7 | 18 |  | Go-live | bar: W6 to W7
B2 | Branding and brand pack | Client brand pack applied only in that client's environments under its contract with iorta TechNXT (for example the Toyota Insurance Services pack) | iorta TechNXT | iorta TechNXT consultant | Pack enabled with the engagement confirmation; contract reference on file | B1, R8 | 1 | 34 | 35 |  |  | 7 | 7 |  |  | Feature only | bar: W7
Integrations with partners
N1 | Integrations with partners | E-mail: SMTP set, password reset and approval link tested | iorta TechNXT | iorta TechNXT DevOps lead | Test e-mails received | E6, I4 | 2 | 13 | 15 |  |  | 3 | 3 | 53 |  | Go-live | bar: W3
N7 | Integrations with partners | Payment gateway: sandbox payment receipted, then one live test payment | Partner | Payment gateway, with Accounting | Receipt of the sandbox payment | C2, I6 | 5 | 29 | 34 |  |  | 6 | 7 |  |  | Feature only | bar: W6 to W7
N2 | Integrations with partners | Bank statement formats: one statement per bank account imported with a balancing preview | iorta TechNXT | iorta TechNXT consultant with Accounting | Import preview per account | C2, I5 | 6 | 29 | 35 |  |  | 6 | 7 | 33 |  | Go-live | bar: W6 to W7
N4 | Integrations with partners | SMS or Viber connector: provider account, sender name, live test message | Partner | SMS provider, with the broker IT head | Connector Live; test message in the outbox | C2, I6 | 10 | 29 | 39 |  |  | 6 | 8 |  |  | Feature only | bar: W6 to W8
N5 | Integrations with partners | CTPL authentication provider and LTO feed: broker accredited, COC series loaded, live authentication of one COC | Partner | IC-accredited authentication provider, with Operations | Authenticated COC; LTO column result | C2, I6, I7 | 15 | 29 | 44 |  |  | 6 | 9 |  |  | Feature only | bar: W6 to W9
N3 | Integrations with partners | Bank payment files: each layout validated with the bank and a test file accepted by the bank | Partner | Bank, with Accounting and iorta TechNXT | Bank acceptance of the test file | C2, I5 | 20 | 29 | 49 |  |  | 6 | 10 |  |  | Feature only | bar: W6 to W10
N6 | Integrations with partners | Insurer API connectors: mapping per insurer, preview, test issuance and claim status with the insurer | Partner | Insurers, with the Processing Team | Accepted test request per insurer | C3SS+2d, I6 | 20 | 31 | 51 |  |  | 7 | 11 |  |  | Feature only | bar: W7 to W11
N8 | Integrations with partners | BIR EIS connector set in test mode; payloads checked | iorta TechNXT | iorta TechNXT consultant | Accepted test submissions | C3 | 2 | 47 | 49 |  |  | 10 | 10 |  |  | Feature only | bar: W10
N9 | Integrations with partners | BIR EIS connector live (after enrolment); earlier invoices queued | iorta TechNXT | iorta TechNXT consultant with Accounting | Accepted live submission | N8, R2, X6 | 2 | 70 | 72 |  |  | 15 | 15 |  |  | Feature only
Data migration (go-live migration kit)
G1 | Data migration (go-live migration kit) | Extraction and cleansing of the old system data for the first mock load | Broker | Broker data owners | Extract files; data quality notes | M3 | 20 | 1 | 21 |  |  | 1 | 5 | 31 |  | Go-live | bar: W1 to W5
G2 | Data migration (go-live migration kit) | Mapping to the migration kit (clients, policies, open items, open claims, opening balances) | iorta TechNXT | iorta TechNXT migration lead | Mapping sheets | G1SS+8d | 8 | 9 | 17 |  |  | 2 | 4 | 35 |  | Go-live | bar: W2 to W4
G3 | Data migration (go-live migration kit) | Mock load 1: cutover date set, validate, errors workbook, load, reconciliation | iorta TechNXT | iorta TechNXT migration lead | Reconciliation workbook signed | G1, G2, C2 | 5 | 29 | 34 |  |  | 6 | 7 | 23 |  | Go-live | bar: W6 to W7
G4 | Data migration (go-live migration kit) | Mock load 2 on a fresh extract, with transaction reset before it | iorta TechNXT | iorta TechNXT migration lead | Reconciliation workbook signed | G3, C5 | 4 | 47 | 51 |  |  | 10 | 11 | 10 |  | Go-live | bar: W10 to W11
G5 | Data migration (go-live migration kit) | Mock load 3 in UAT (large, enterprise) | iorta TechNXT | iorta TechNXT migration lead | Reconciliation workbook signed | G4, T3 | 4 | 59 | 63 |  |  | 12 | 13 | 2 |  | Go-live | bar: W12 to W13
Training
L2 | Training | Compliance officer, DPO and System Administrator training on the compliance and privacy screens | iorta TechNXT | iorta TechNXT consultant | Attendance and assessment | K1 | 2 | 37 | 39 |  |  | 8 | 8 | 29 |  | Go-live | bar: W8
L1 | Training | Train-the-trainer for key users, with trainer skills and teach-back | iorta TechNXT | iorta TechNXT consultants | Key users passed at 90% | C5 | 8 | 47 | 55 |  |  | 10 | 11 | 5 |  | Go-live | bar: W10 to W11
L3 | Training | End-user training per role, run by key users | Broker | Broker key users | Every user trained and assessed | L1, T3, I9 | 8 | 59 | 67 |  |  | 12 | 14 | 1 |  | Go-live | bar: W12 to W14
SIT and UAT
T1 | SIT and UAT | System integration test in Dev (small, medium) or SIT (large, enterprise): end-to-end flows, uat-scenario.js, connectors in test mode | iorta TechNXT | iorta TechNXT test lead | SIT results; defect log | C3SS+18d, C2 | 10 | 47 | 57 |  |  | 10 | 12 | 0 | Yes | Go-live | bar: W10 to W12
T2 | SIT and UAT | SIT exit | iorta TechNXT | iorta TechNXT test lead | SIT exit report | T1, C5 | 0 | 57 | 57 |  |  | 12 | 12 | 0 | Yes | Go-live | bar: W12
T3 | SIT and UAT | Release candidate and frozen configuration promoted to UAT (Current data workbook, brand pack); comparison report clean | iorta TechNXT | iorta TechNXT delivery lead | Deploy run; comparison workbook | T2, E3 | 2 | 57 | 59 |  |  | 12 | 12 | 0 | Yes | Go-live | bar: W12
T4 | SIT and UAT | UAT cycles with the UAT scripts and broker scenarios, including compliance, BIR and integration scripts | Broker | Broker key users | UAT results per script | T3, I10 | 9 | 59 | 68 |  |  | 12 | 14 | 0 | Yes | Go-live | bar: W12 to W14
T5 | SIT and UAT | UAT sign-off | Broker | Broker sponsor and process owners | UAT Sign-off Certificate (Form 1) | T4, R6 | 0 | 68 | 68 |  |  | 14 | 14 | 0 | Yes | Go-live | bar: W14
Rehearsal and cutover
X1 | Rehearsal and cutover | Release tag and frozen configuration deployed to Production; production smoke test; transaction reset | iorta TechNXT | iorta TechNXT DevOps lead | Deploy run; smoke test record; reset audit entry | T3, E7, R1 | 2 | 59 | 61 |  |  | 12 | 13 | 2 |  | Go-live | bar: W12 to W13
X2 | Rehearsal and cutover | Pre-Prod created from a production backup (masked when people without production access take part) | iorta TechNXT | iorta TechNXT DevOps lead | Restore record (counts as a restore test) | X1 | 2 | 61 | 63 |  |  | 13 | 13 | 2 |  | Go-live | bar: W13
X3 | Rehearsal and cutover | Cutover rehearsal in Pre-Prod: reset, migration load of a fresh extract, reconciliation, go-live lock, comparison against Production, timings | iorta TechNXT | iorta TechNXT migration lead | Rehearsal log; reconciliation signed | X2, G4, G5, T4SS+6d | 3 | 65 | 68 |  |  | 14 | 14 | 0 | Yes | Go-live | bar: W14
X4 | Rehearsal and cutover | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | Broker | Steering committee | Minutes | X3, T5, L3, L2, K2, K3, N1, N2, R5, B1 | 0 | 68 | 68 |  |  | 14 | 14 | 0 | Yes | Go-live | bar: W14
X5 | Rehearsal and cutover | Cutover: freeze, final extract, final load, reconciliation, go/no-go 2, golive.locked, mask:data --register-production | Broker | Broker PM with the iorta TechNXT migration lead | Signed reconciliation; go decision; audit entries | X4 | 2 | 68 | 70 |  |  | 14 | 14 | 0 | Yes | Go-live | bar: W14
X6 | Rehearsal and cutover | Go-live | Broker | Broker sponsor | First day of transactions in BrokerVerse | X5 | 0 | 70 | 70 |  |  | 15 | 15 | 0 | Yes | Go-live | bar: W15
Hypercare
H1 | Hypercare | Hypercare: daily check-ins in week 1, then weekly; first receipts, remittances, bank imports and payment files watched | iorta TechNXT | iorta TechNXT PM | Hypercare log | X6 | 30 | 70 | 100 |  |  | 15 | 20 |  |  | Hypercare exit | bar: W15 to W20
H2 | Hypercare | First month-end close and BIR working papers of the first month supported | Broker | Broker Accounting Manager | Approved Month-End Close run | X6+15d | 10 | 85 | 95 |  |  | 18 | 19 |  |  | Hypercare exit | bar: W18 to W19
H3 | Hypercare | Knowledge transfer, configuration baseline (Current data workbook of Production), handover; Pre-Prod removed | iorta TechNXT | iorta TechNXT PM and support manager | Hypercare Exit and Handover Certificate | H1, H2 | 0 | 100 | 100 |  |  | 20 | 20 |  |  | Hypercare exit | bar: W20
Formulas:
Start date = WORKDAY(D2,[Start day])
Finish date = IF([Duration (working days)]=0,[Start date],WORKDAY(D2,[Finish day]-1))

## Enterprise
BrokerVerse OOTB implementation plan: Enterprise broker (26 weeks, go-live at the start of week 21)
Kick-off date (a Monday): |  |  | 2026-11-02 |  | Type the kick-off date in the yellow cell: start and finish dates follow (working days, weekends skipped; add holidays as a third WORKDAY argument). Environments: Dev, SIT, UAT, Production (high availability, cross-region backup copy); Pre-Prod temporary. Mock loads 1 and 2 in SIT, mock loads 3 and 4 in UAT; the cutover rehearsal in Pre-Prod is the fifth load.
Bars: blue iorta TechNXT, green broker, gold partner; red border and red ID = on the critical path to go-live. Float = working days a task can slip before the go-live date moves (empty: the task does not hold the go-live).
ID | Phase | Task | Party | Owner role | Deliverable or evidence | Predecessors | Duration (working days) | Start day | Finish day | Start date | Finish date | Start week | End week | Float to go-live (days) | Critical | Holds back | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
Mobilisation
M1 | Mobilisation | Kick-off | iorta TechNXT | iorta TechNXT PM | Kick-off held; plan and go-live date confirmed |  | 0 | 0 | 0 |  |  | 1 | 1 | 0 | Yes | Go-live | bar: W1
M3 | Mobilisation | Data request list and the go-live kits issued (configuration and migration workbooks, upload templates) | iorta TechNXT | iorta TechNXT PM | Data request list; blank workbooks handed over | M1 | 1 | 0 | 1 |  |  | 1 | 1 | 0 | Yes | Go-live | bar: W1
M4 | Mobilisation | Broker team named: PM, key users, Accounting Manager, System Administrator, compliance officer, DPO | Broker | Broker sponsor | Named team with committed time | M1 | 3 | 0 | 3 |  |  | 1 | 1 | 30 |  | Go-live | bar: W1
M5 | Mobilisation | Hosting option, environment set and data location confirmed; environments ordered | Broker | Broker sponsor and IT head | Order Form hosting fields; transfer decision recorded | M1 | 3 | 0 | 3 |  |  | 1 | 1 | 17 |  | Go-live | bar: W1
M2 | Mobilisation | Project charter, baselined plan, governance calendar, RAID log | iorta TechNXT | iorta TechNXT PM | Charter and plan signed | M1 | 5 | 0 | 5 |  |  | 1 | 1 | 31 |  | Go-live | bar: W1
Environments and pipeline
E1 | Environments and pipeline | Dev provisioned | iorta TechNXT | iorta TechNXT DevOps lead | Environment sheet: Dev | M5 | 4 | 3 | 7 |  |  | 1 | 2 | 17 |  | Go-live | bar: W1 to W2
E3 | Environments and pipeline | UAT provisioned | iorta TechNXT | iorta TechNXT DevOps lead | Environment sheet: UAT | M5 | 5 | 3 | 8 |  |  | 1 | 2 | 21 |  | Go-live | bar: W1 to W2
E5 | Environments and pipeline | Application secrets per environment in the secret store: JWT_SECRET, DATA_ENCRYPTION_KEY, PII_ENCRYPTION_KEY generated; key custody and escrow copy agreed | iorta TechNXT | iorta TechNXT DevOps lead with the broker IT head | Key custody record signed by both | E1 | 2 | 7 | 9 |  |  | 2 | 2 | 20 |  | Go-live | bar: W2
E4 | Environments and pipeline | GitHub Environments (dev, sit, uat, preprod, production): protection rules, reviewers, variables, environment secrets | iorta TechNXT | iorta TechNXT DevOps lead | Settings recorded in the environment sheet | E1 | 3 | 7 | 10 |  |  | 2 | 2 | 19 |  | Go-live | bar: W2
E2 | Environments and pipeline | SIT provisioned (large and enterprise brokers) | iorta TechNXT | iorta TechNXT DevOps lead | Environment sheet: SIT | E1 | 5 | 7 | 12 |  |  | 2 | 3 | 17 |  | Go-live | bar: W2 to W3
E7 | Environments and pipeline | Production provisioned at production topology; backups, monitoring, restore test | iorta TechNXT | iorta TechNXT DevOps lead | Environment sheet; restore test record | E5 | 12 | 9 | 21 |  |  | 2 | 5 | 67 |  | Go-live | bar: W2 to W5
E6 | Environments and pipeline | First deployment through the pipeline (CI, deploy, smoke test) to Dev and UAT (and SIT) | iorta TechNXT | iorta TechNXT DevOps lead | Deploy run summaries; smoke test passed | E4, E5, E3, E2 | 2 | 12 | 14 |  |  | 3 | 3 | 17 |  | Go-live | bar: W3
Discovery and fit-gap
D1 | Discovery and fit-gap | Process workshops on the delivered system: organisation, sales, placement, servicing, claims, billing, remittance, commission, ledger, tax, distribution | iorta TechNXT | iorta TechNXT consultants | Workshop notes; decisions in the configuration workbook | M1 | 28 | 0 | 28 |  |  | 1 | 6 | 6 |  | Go-live | bar: W1 to W6
D4 | Discovery and fit-gap | Branding workshop: theme, logo, sign-in picture, documents, e-signatures, brand pack choice | iorta TechNXT | iorta TechNXT consultant | Branding decisions; client brand pack needed or not, with its contract reference | M4 | 2 | 3 | 5 |  |  | 1 | 1 | 31 |  | Go-live | bar: W1
D2 | Discovery and fit-gap | Compliance workshop: AML/CFT programme, IC registers, complaints, breach procedure, masking by role | iorta TechNXT | iorta TechNXT consultant with the compliance officer and DPO | Compliance decisions recorded | M4 | 3 | 3 | 6 |  |  | 1 | 2 | 30 |  | Go-live | bar: W1 to W2
D3 | Discovery and fit-gap | Integration workshop: banks, SMS or Viber, CTPL authentication and LTO, insurers, payment gateway, BIR EIS, AMLC reporting | iorta TechNXT | iorta TechNXT technical lead | Integration list with partner contacts | M4 | 3 | 3 | 6 |  |  | 1 | 2 | 30 |  | Go-live | bar: W1 to W2
D5 | Discovery and fit-gap | Configuration decisions and fit-gap register signed | Broker | Broker process owners | Signed fit-gap register | D1, D2, D3, D4, M2 | 0 | 28 | 28 |  |  | 6 | 6 | 8 |  | Go-live | bar: W6
Client inputs
I4 | Client inputs | SMTP mailbox and credentials | Broker | Broker IT head | Mailbox in the secret store | M3 | 5 | 1 | 6 |  |  | 1 | 2 | 90 |  | Go-live | bar: W1 to W2
I7 | Client inputs | COC number series from each insurer | Broker | Broker Operations | COC Series sheet | M3 | 10 | 1 | 11 |  |  | 1 | 3 |  |  | Feature only | bar: W1 to W3
I3 | Client inputs | User list with roles, branches and reporting lines (My Team follows the reporting line) | Broker | Broker System Administrator | Users sheet | M3 | 12 | 1 | 13 |  |  | 1 | 3 | 3 |  | Go-live | bar: W1 to W3
I5 | Client inputs | Bank accounts, one statement export per account, bank contacts for payment files, payee bank accounts | Broker | Broker Accounting | Statement samples; Payee Bank Accounts sheet | M3 | 12 | 1 | 13 |  |  | 1 | 3 | 77 |  | Feature only | bar: W1 to W3
I1 | Client inputs | Insurer list and agreements, commission and referrer rates, product list | Broker | Broker key users | Filled sheets of the configuration kit | M3 | 15 | 1 | 16 |  |  | 1 | 4 | 0 | Yes | Go-live | bar: W1 to W4
I2 | Client inputs | Chart of accounts and the accountant's mapping decisions | Broker | Broker Accounting Manager | Chart of Accounts sheet; mapping decisions | M3 | 15 | 1 | 16 |  |  | 1 | 4 | 0 | Yes | Go-live | bar: W1 to W4
I10 | Client inputs | UAT testers and sign-off authority named | Broker | Broker PM | UAT roster | M4 | 3 | 3 | 6 |  |  | 1 | 2 | 72 |  | Go-live | bar: W1 to W2
I9 | Client inputs | Training rooms, devices and attendance list | Broker | Broker PM | Training schedule | M4 | 5 | 3 | 8 |  |  | 1 | 2 | 75 |  | Go-live | bar: W1 to W2
I8 | Client inputs | Logo, sign-in picture, signatories with e-signature consent | Broker | Broker marketing and signatories | Images; consents on file | D4 | 8 | 5 | 13 |  |  | 2 | 3 | 54 |  | Go-live | bar: W2 to W3
I6 | Client inputs | Partner contracts and credentials: SMS provider, CTPL authentication provider, payment gateway, insurer API access | Broker | Broker IT head and sponsor | Signed contracts; credentials in the secret store | D3 | 20 | 6 | 26 |  |  | 2 | 6 |  |  | Feature only | bar: W2 to W6
Regulatory registrations
R3 | Regulatory registrations | AMLC: registration of the broker as covered person, portal access, institution code | Broker | Broker compliance officer | Portal access; aml.amlc_institution_code | M1 | 20 | 0 | 20 |  |  | 1 | 4 | 76 |  | Go-live | bar: W1 to W4
R1 | Regulatory registrations | BIR: Authority to Print or CAS registration and the invoice serial range confirmed (new or existing); last numbers used | Broker | Broker Accounting Manager with the tax adviser | ATP or CAS acknowledgement; invoice.* settings | M1 | 30 | 0 | 30 |  |  | 1 | 6 | 58 |  | Go-live | bar: W1 to W6
R2 | Regulatory registrations | BIR: EIS enrolment and certification (when the broker is covered) | Broker | Broker Accounting Manager | EIS accreditation id and credentials | M1 | 30 | 0 | 30 |  |  | 1 | 6 |  |  | Feature only | bar: W1 to W6
R5 | Regulatory registrations | NPC: registration of the DPO and the data processing systems confirmed; privacy notice version | Broker | Broker DPO | NPC registration; privacy.notice_version | M1 | 30 | 0 | 30 |  |  | 1 | 6 | 68 |  | Go-live | bar: W1 to W6
R4 | Regulatory registrations | IC: licence data of the firm, officers and agents; certificates of authority of the insurers | Broker | Broker compliance officer | Licence copies; certificate numbers and validity | M4 | 12 | 3 | 15 |  |  | 1 | 3 | 48 |  | Go-live | bar: W1 to W3
R8 | Regulatory registrations | Contract reference covering the use of the client's marks on the engagement file (client brand pack only) | Broker | Broker sponsor | Contract reference on the engagement file | D4 | 5 | 5 | 10 |  |  | 2 | 2 |  |  | Feature only | bar: W2
R7 | Regulatory registrations | Screening lists: UN and AMLC lists obtained; PEP list licence from a provider (when used) | Broker | Broker compliance officer | List files and licence | D2 | 15 | 6 | 21 |  |  | 2 | 5 | 76 |  | Go-live | bar: W2 to W5
R6 | Regulatory registrations | Tax adviser confirmation: tax codes, ATC, rates, invoice and receipt wording, VAT treatment of commission | Broker | Broker tax adviser | Written confirmation | C3SS+10d | 10 | 46 | 56 |  |  | 10 | 12 | 42 |  | Go-live | bar: W10 to W12
Configuration (go-live configuration kit)
C1 | Configuration (go-live configuration kit) | Configuration kit filled: company, settings, PSGC addresses, branches, users, chart of accounts, banks, insurers, products, commission, taxes, authority limits, numbering | Broker | Broker key users with iorta TechNXT consultants | Filled configuration workbook | D1SS+10d, I1, I2, I3 | 15 | 16 | 31 |  |  | 4 | 7 | 0 | Yes | Go-live | bar: W4 to W7
C2 | Configuration (go-live configuration kit) | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | iorta TechNXT | iorta TechNXT consultant | Batch Loaded; load history | C1, E6 | 5 | 31 | 36 |  |  | 7 | 8 | 0 | Yes | Go-live | bar: W7 to W8
C3 | Configuration (go-live configuration kit) | On-screen configuration: Product Configurator (templates, rating factors, acceptance rules, document templates, market mapping), tax codes, posting rules, approvals, roles, schedules | iorta TechNXT | iorta TechNXT consultants | Configuration workbook updated with the values set | C2, D5 | 25 | 36 | 61 |  |  | 8 | 13 | 0 | Yes | Go-live | bar: W8 to W13
C5 | Configuration (go-live configuration kit) | Configuration complete | iorta TechNXT | iorta TechNXT delivery lead | Checklist of GO_LIVE_DATA_SETUP steps 1 to 12 | C3, K1, B1 | 0 | 61 | 61 |  |  | 13 | 13 | 12 |  | Go-live | bar: W13
Compliance set-up
K1 | Compliance set-up | Compliance set-up: AML settings, risk factors, monitoring rules; licence register, fit and proper, insurer authority; complaints and breach settings; view:pii grants and masking | iorta TechNXT | iorta TechNXT consultant with the compliance officer | AML Settings saved; registers filled | C2, D2, R4 | 10 | 36 | 46 |  |  | 8 | 10 | 27 |  | Go-live | bar: W8 to W10
K2 | Compliance set-up | Screening lists loaded (UN, AMLC, PEP, internal); clients rescreened | Broker | Broker compliance officer | Versions on Screening Lists; rescreen result | K1, R7 | 1 | 46 | 47 |  |  | 10 | 10 | 51 |  | Go-live | bar: W10
K3 | Compliance set-up | AMLC report file test: CTR file generated in UAT and checked against the AMLC portal requirements | Broker | Broker compliance officer | Test file; portal access confirmed | K1, R3 | 2 | 46 | 48 |  |  | 10 | 10 | 50 |  | Go-live | bar: W10
Branding and brand pack
B1 | Branding and brand pack | Theme and Branding, letterhead, sign-in page, branded documents and e-mails; e-signatures captured and mapped; brand pack exported | iorta TechNXT | iorta TechNXT consultant with the broker System Administrator | Brand pack file; sample documents approved | C2, I8 | 6 | 36 | 42 |  |  | 8 | 9 | 31 |  | Go-live | bar: W8 to W9
B2 | Branding and brand pack | Client brand pack applied only in that client's environments under its contract with iorta TechNXT (for example the Toyota Insurance Services pack) | iorta TechNXT | iorta TechNXT consultant | Pack enabled with the engagement confirmation; contract reference on file | B1, R8 | 1 | 42 | 43 |  |  | 9 | 9 |  |  | Feature only | bar: W9
Integrations with partners
N1 | Integrations with partners | E-mail: SMTP set, password reset and approval link tested | iorta TechNXT | iorta TechNXT DevOps lead | Test e-mails received | E6, I4 | 2 | 14 | 16 |  |  | 3 | 4 | 82 |  | Go-live | bar: W3 to W4
N7 | Integrations with partners | Payment gateway: sandbox payment receipted, then one live test payment | Partner | Payment gateway, with Accounting | Receipt of the sandbox payment | C2, I6 | 5 | 36 | 41 |  |  | 8 | 9 |  |  | Feature only | bar: W8 to W9
N2 | Integrations with partners | Bank statement formats: one statement per bank account imported with a balancing preview | iorta TechNXT | iorta TechNXT consultant with Accounting | Import preview per account | C2, I5 | 8 | 36 | 44 |  |  | 8 | 9 | 54 |  | Go-live | bar: W8 to W9
N4 | Integrations with partners | SMS or Viber connector: provider account, sender name, live test message | Partner | SMS provider, with the broker IT head | Connector Live; test message in the outbox | C2, I6 | 10 | 36 | 46 |  |  | 8 | 10 |  |  | Feature only | bar: W8 to W10
N5 | Integrations with partners | CTPL authentication provider and LTO feed: broker accredited, COC series loaded, live authentication of one COC | Partner | IC-accredited authentication provider, with Operations | Authenticated COC; LTO column result | C2, I6, I7 | 15 | 36 | 51 |  |  | 8 | 11 |  |  | Feature only | bar: W8 to W11
N3 | Integrations with partners | Bank payment files: each layout validated with the bank and a test file accepted by the bank | Partner | Bank, with Accounting and iorta TechNXT | Bank acceptance of the test file | C2, I5 | 25 | 36 | 61 |  |  | 8 | 13 |  |  | Feature only | bar: W8 to W13
N6 | Integrations with partners | Insurer API connectors: mapping per insurer, preview, test issuance and claim status with the insurer | Partner | Insurers, with the Processing Team | Accepted test request per insurer | C3SS+2d, I6 | 25 | 38 | 63 |  |  | 8 | 13 |  |  | Feature only | bar: W8 to W13
N8 | Integrations with partners | BIR EIS connector set in test mode; payloads checked | iorta TechNXT | iorta TechNXT consultant | Accepted test submissions | C3 | 2 | 61 | 63 |  |  | 13 | 13 |  |  | Feature only | bar: W13
N9 | Integrations with partners | BIR EIS connector live (after enrolment); earlier invoices queued | iorta TechNXT | iorta TechNXT consultant with Accounting | Accepted live submission | N8, R2, X6 | 2 | 100 | 102 |  |  | 21 | 21 |  |  | Feature only
Data migration (go-live migration kit)
G1 | Data migration (go-live migration kit) | Extraction and cleansing of the old system data for the first mock load | Broker | Broker data owners | Extract files; data quality notes | M3 | 25 | 1 | 26 |  |  | 1 | 6 | 47 |  | Go-live | bar: W1 to W6
G2 | Data migration (go-live migration kit) | Mapping to the migration kit (clients, policies, open items, open claims, opening balances) | iorta TechNXT | iorta TechNXT migration lead | Mapping sheets | G1SS+10d | 10 | 11 | 21 |  |  | 3 | 5 | 52 |  | Go-live | bar: W3 to W5
G3 | Data migration (go-live migration kit) | Mock load 1: cutover date set, validate, errors workbook, load, reconciliation | iorta TechNXT | iorta TechNXT migration lead | Reconciliation workbook signed | G1, G2, C2 | 5 | 36 | 41 |  |  | 8 | 9 | 37 |  | Go-live | bar: W8 to W9
G4 | Data migration (go-live migration kit) | Mock load 2 on a fresh extract, with transaction reset before it | iorta TechNXT | iorta TechNXT migration lead | Reconciliation workbook signed | G3, C5 | 5 | 61 | 66 |  |  | 13 | 14 | 17 |  | Go-live | bar: W13 to W14
G5 | Data migration (go-live migration kit) | Mock load 3 in UAT (large, enterprise) | iorta TechNXT | iorta TechNXT migration lead | Reconciliation workbook signed | G4, T3 | 5 | 78 | 83 |  |  | 16 | 17 | 5 |  | Go-live | bar: W16 to W17
G6 | Data migration (go-live migration kit) | Mock load 4 in UAT (enterprise) | iorta TechNXT | iorta TechNXT migration lead | Reconciliation workbook signed | G5 | 5 | 83 | 88 |  |  | 17 | 18 | 5 |  | Go-live | bar: W17 to W18
Training
L2 | Training | Compliance officer, DPO and System Administrator training on the compliance and privacy screens | iorta TechNXT | iorta TechNXT consultant | Attendance and assessment | K1 | 2 | 46 | 48 |  |  | 10 | 10 | 50 |  | Go-live | bar: W10
L1 | Training | Train-the-trainer for key users, with trainer skills and teach-back | iorta TechNXT | iorta TechNXT consultants | Key users passed at 90% | C5 | 10 | 61 | 71 |  |  | 13 | 15 | 12 |  | Go-live | bar: W13 to W15
L3 | Training | End-user training per role, run by key users | Broker | Broker key users | Every user trained and assessed | L1, T3, I9 | 15 | 78 | 93 |  |  | 16 | 19 | 5 |  | Go-live | bar: W16 to W19
SIT and UAT
T1 | SIT and UAT | System integration test in Dev (small, medium) or SIT (large, enterprise): end-to-end flows, uat-scenario.js, connectors in test mode | iorta TechNXT | iorta TechNXT test lead | SIT results; defect log | C3SS+25d, C2 | 15 | 61 | 76 |  |  | 13 | 16 | 0 | Yes | Go-live | bar: W13 to W16
T2 | SIT and UAT | SIT exit | iorta TechNXT | iorta TechNXT test lead | SIT exit report | T1, C5 | 0 | 76 | 76 |  |  | 16 | 16 | 0 | Yes | Go-live | bar: W16
T3 | SIT and UAT | Release candidate and frozen configuration promoted to UAT (Current data workbook, brand pack); comparison report clean | iorta TechNXT | iorta TechNXT delivery lead | Deploy run; comparison workbook | T2, E3 | 2 | 76 | 78 |  |  | 16 | 16 | 0 | Yes | Go-live | bar: W16
T4 | SIT and UAT | UAT cycles with the UAT scripts and broker scenarios, including compliance, BIR and integration scripts | Broker | Broker key users | UAT results per script | T3, I10 | 20 | 78 | 98 |  |  | 16 | 20 | 0 | Yes | Go-live | bar: W16 to W20
T5 | SIT and UAT | UAT sign-off | Broker | Broker sponsor and process owners | UAT Sign-off Certificate (Form 1) | T4, R6 | 0 | 98 | 98 |  |  | 20 | 20 | 0 | Yes | Go-live | bar: W20
Rehearsal and cutover
X1 | Rehearsal and cutover | Release tag and frozen configuration deployed to Production; production smoke test; transaction reset | iorta TechNXT | iorta TechNXT DevOps lead | Deploy run; smoke test record; reset audit entry | T3, E7, R1 | 3 | 78 | 81 |  |  | 16 | 17 | 10 |  | Go-live | bar: W16 to W17
X2 | Rehearsal and cutover | Pre-Prod created from a production backup (masked when people without production access take part) | iorta TechNXT | iorta TechNXT DevOps lead | Restore record (counts as a restore test) | X1 | 2 | 81 | 83 |  |  | 17 | 17 | 10 |  | Go-live | bar: W17
X3 | Rehearsal and cutover | Cutover rehearsal in Pre-Prod: reset, migration load of a fresh extract, reconciliation, go-live lock, comparison against Production, timings | iorta TechNXT | iorta TechNXT migration lead | Rehearsal log; reconciliation signed | X2, G4, G5, G6, T4SS+15d | 5 | 93 | 98 |  |  | 19 | 20 | 0 | Yes | Go-live | bar: W19 to W20
X4 | Rehearsal and cutover | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | Broker | Steering committee | Minutes | X3, T5, L3, L2, K2, K3, N1, N2, R5, B1 | 0 | 98 | 98 |  |  | 20 | 20 | 0 | Yes | Go-live | bar: W20
X5 | Rehearsal and cutover | Cutover: freeze, final extract, final load, reconciliation, go/no-go 2, golive.locked, mask:data --register-production | Broker | Broker PM with the iorta TechNXT migration lead | Signed reconciliation; go decision; audit entries | X4 | 2 | 98 | 100 |  |  | 20 | 20 | 0 | Yes | Go-live | bar: W20
X6 | Rehearsal and cutover | Go-live | Broker | Broker sponsor | First day of transactions in BrokerVerse | X5 | 0 | 100 | 100 |  |  | 21 | 21 | 0 | Yes | Go-live | bar: W21
Hypercare
H1 | Hypercare | Hypercare: daily check-ins in week 1, then weekly; first receipts, remittances, bank imports and payment files watched | iorta TechNXT | iorta TechNXT PM | Hypercare log | X6 | 30 | 100 | 130 |  |  | 21 | 26 |  |  | Hypercare exit | bar: W21 to W26
H2 | Hypercare | First month-end close and BIR working papers of the first month supported | Broker | Broker Accounting Manager | Approved Month-End Close run | X6+15d | 10 | 115 | 125 |  |  | 24 | 25 |  |  | Hypercare exit | bar: W24 to W25
H3 | Hypercare | Knowledge transfer, configuration baseline (Current data workbook of Production), handover; Pre-Prod removed | iorta TechNXT | iorta TechNXT PM and support manager | Hypercare Exit and Handover Certificate | H1, H2 | 0 | 130 | 130 |  |  | 26 | 26 |  |  | Hypercare exit | bar: W26
Formulas:
Start date = WORKDAY(D2,[Start day])
Finish date = IF([Duration (working days)]=0,[Start date],WORKDAY(D2,[Finish day]-1))

## Milestones
Milestones and their evidence
ID | Milestone | Evidence | Accountable | Small week | Medium week | Large week | Enterprise week
M1 | Kick-off | Kick-off held; plan and go-live date confirmed | iorta TechNXT PM | W1 | W1 | W1 | W1
D5 | Configuration decisions and fit-gap register signed | Signed fit-gap register | Broker process owners | W2 | W3 | W4 | W6
C5 | Configuration complete | Checklist of GO_LIVE_DATA_SETUP steps 1 to 12 | iorta TechNXT delivery lead | W4 | W6 | W10 | W13
T2 | SIT exit | SIT exit report | iorta TechNXT test lead | W4 | W7 | W12 | W16
T5 | UAT sign-off | UAT Sign-off Certificate (Form 1) | Broker sponsor and process owners | W6 | W9 | W14 | W20
X4 | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | Minutes | Steering committee | W6 | W9 | W14 | W20
X6 | Go-live | First day of transactions in BrokerVerse | Broker sponsor | W7 | W10 | W15 | W21
H3 | Knowledge transfer, configuration baseline (Current data workbook of Production), handover; Pre-Prod removed | Hypercare Exit and Handover Certificate | iorta TechNXT PM and support manager | W8 | W12 | W20 | W26

## Dependencies
Dependencies: every link of the plan
FS = the task starts when the predecessor finishes; SS = the task starts when the predecessor has started (plus the lag). Lags in working days, by size.
Predecessor | Predecessor task | Successor | Successor task | Type | Lag S / M / L / E (days) | Holds back
M1 | Kick-off | M2 | Project charter, baselined plan, governance calendar, RAID log | FS | 0 / 0 / 0 / 0 | Go-live
M1 | Kick-off | M3 | Data request list and the go-live kits issued (configuration and migration workbooks, upload templates) | FS | 0 / 0 / 0 / 0 | Go-live
M1 | Kick-off | M4 | Broker team named: PM, key users, Accounting Manager, System Administrator, compliance officer, DPO | FS | 0 / 0 / 0 / 0 | Go-live
M1 | Kick-off | M5 | Hosting option, environment set and data location confirmed; environments ordered | FS | 0 / 0 / 0 / 0 | Go-live
M5 | Hosting option, environment set and data location confirmed; environments ordered | E1 | Dev provisioned | FS | 0 / 0 / 0 / 0 | Go-live
E1 | Dev provisioned | E2 | SIT provisioned (large and enterprise brokers) | FS | 0 / 0 / 0 / 0 | Go-live
M5 | Hosting option, environment set and data location confirmed; environments ordered | E3 | UAT provisioned | FS | 0 / 0 / 0 / 0 | Go-live
E1 | Dev provisioned | E4 | GitHub Environments (dev, sit, uat, preprod, production): protection rules, reviewers, variables, environment secrets | FS | 0 / 0 / 0 / 0 | Go-live
E1 | Dev provisioned | E5 | Application secrets per environment in the secret store: JWT_SECRET, DATA_ENCRYPTION_KEY, PII_ENCRYPTION_KEY generated; key custody and escrow copy agreed | FS | 0 / 0 / 0 / 0 | Go-live
E4 | GitHub Environments (dev, sit, uat, preprod, production): protection rules, reviewers, variables, environment secrets | E6 | First deployment through the pipeline (CI, deploy, smoke test) to Dev and UAT (and SIT) | FS | 0 / 0 / 0 / 0 | Go-live
E5 | Application secrets per environment in the secret store: JWT_SECRET, DATA_ENCRYPTION_KEY, PII_ENCRYPTION_KEY generated; key custody and escrow copy agreed | E6 | First deployment through the pipeline (CI, deploy, smoke test) to Dev and UAT (and SIT) | FS | 0 / 0 / 0 / 0 | Go-live
E3 | UAT provisioned | E6 | First deployment through the pipeline (CI, deploy, smoke test) to Dev and UAT (and SIT) | FS | 0 / 0 / 0 / 0 | Go-live
E2 | SIT provisioned (large and enterprise brokers) | E6 | First deployment through the pipeline (CI, deploy, smoke test) to Dev and UAT (and SIT) | FS | 0 / 0 / 0 / 0 | Go-live
E5 | Application secrets per environment in the secret store: JWT_SECRET, DATA_ENCRYPTION_KEY, PII_ENCRYPTION_KEY generated; key custody and escrow copy agreed | E7 | Production provisioned at production topology; backups, monitoring, restore test | FS | 0 / 0 / 0 / 0 | Go-live
M1 | Kick-off | D1 | Process workshops on the delivered system: organisation, sales, placement, servicing, claims, billing, remittance, commission, ledger, tax, distribution | FS | 0 / 0 / 0 / 0 | Go-live
M4 | Broker team named: PM, key users, Accounting Manager, System Administrator, compliance officer, DPO | D2 | Compliance workshop: AML/CFT programme, IC registers, complaints, breach procedure, masking by role | FS | 0 / 0 / 0 / 0 | Go-live
M4 | Broker team named: PM, key users, Accounting Manager, System Administrator, compliance officer, DPO | D3 | Integration workshop: banks, SMS or Viber, CTPL authentication and LTO, insurers, payment gateway, BIR EIS, AMLC reporting | FS | 0 / 0 / 0 / 0 | Go-live
M4 | Broker team named: PM, key users, Accounting Manager, System Administrator, compliance officer, DPO | D4 | Branding workshop: theme, logo, sign-in picture, documents, e-signatures, brand pack choice | FS | 0 / 0 / 0 / 0 | Go-live
D1 | Process workshops on the delivered system: organisation, sales, placement, servicing, claims, billing, remittance, commission, ledger, tax, distribution | D5 | Configuration decisions and fit-gap register signed | FS | 0 / 0 / 0 / 0 | Go-live
D2 | Compliance workshop: AML/CFT programme, IC registers, complaints, breach procedure, masking by role | D5 | Configuration decisions and fit-gap register signed | FS | 0 / 0 / 0 / 0 | Go-live
D3 | Integration workshop: banks, SMS or Viber, CTPL authentication and LTO, insurers, payment gateway, BIR EIS, AMLC reporting | D5 | Configuration decisions and fit-gap register signed | FS | 0 / 0 / 0 / 0 | Go-live
D4 | Branding workshop: theme, logo, sign-in picture, documents, e-signatures, brand pack choice | D5 | Configuration decisions and fit-gap register signed | FS | 0 / 0 / 0 / 0 | Go-live
M2 | Project charter, baselined plan, governance calendar, RAID log | D5 | Configuration decisions and fit-gap register signed | FS | 0 / 0 / 0 / 0 | Go-live
M3 | Data request list and the go-live kits issued (configuration and migration workbooks, upload templates) | I1 | Insurer list and agreements, commission and referrer rates, product list | FS | 0 / 0 / 0 / 0 | Go-live
M3 | Data request list and the go-live kits issued (configuration and migration workbooks, upload templates) | I2 | Chart of accounts and the accountant's mapping decisions | FS | 0 / 0 / 0 / 0 | Go-live
M3 | Data request list and the go-live kits issued (configuration and migration workbooks, upload templates) | I3 | User list with roles, branches and reporting lines (My Team follows the reporting line) | FS | 0 / 0 / 0 / 0 | Go-live
M3 | Data request list and the go-live kits issued (configuration and migration workbooks, upload templates) | I4 | SMTP mailbox and credentials | FS | 0 / 0 / 0 / 0 | Go-live
M3 | Data request list and the go-live kits issued (configuration and migration workbooks, upload templates) | I5 | Bank accounts, one statement export per account, bank contacts for payment files, payee bank accounts | FS | 0 / 0 / 0 / 0 | Feature only
D3 | Integration workshop: banks, SMS or Viber, CTPL authentication and LTO, insurers, payment gateway, BIR EIS, AMLC reporting | I6 | Partner contracts and credentials: SMS provider, CTPL authentication provider, payment gateway, insurer API access | FS | 0 / 0 / 0 / 0 | Feature only
M3 | Data request list and the go-live kits issued (configuration and migration workbooks, upload templates) | I7 | COC number series from each insurer | FS | 0 / 0 / 0 / 0 | Feature only
D4 | Branding workshop: theme, logo, sign-in picture, documents, e-signatures, brand pack choice | I8 | Logo, sign-in picture, signatories with e-signature consent | FS | 0 / 0 / 0 / 0 | Go-live
M4 | Broker team named: PM, key users, Accounting Manager, System Administrator, compliance officer, DPO | I9 | Training rooms, devices and attendance list | FS | 0 / 0 / 0 / 0 | Go-live
M4 | Broker team named: PM, key users, Accounting Manager, System Administrator, compliance officer, DPO | I10 | UAT testers and sign-off authority named | FS | 0 / 0 / 0 / 0 | Go-live
M1 | Kick-off | R1 | BIR: Authority to Print or CAS registration and the invoice serial range confirmed (new or existing); last numbers used | FS | 0 / 0 / 0 / 0 | Go-live
M1 | Kick-off | R2 | BIR: EIS enrolment and certification (when the broker is covered) | FS | 0 / 0 / 0 / 0 | Feature only
M1 | Kick-off | R3 | AMLC: registration of the broker as covered person, portal access, institution code | FS | 0 / 0 / 0 / 0 | Go-live
M4 | Broker team named: PM, key users, Accounting Manager, System Administrator, compliance officer, DPO | R4 | IC: licence data of the firm, officers and agents; certificates of authority of the insurers | FS | 0 / 0 / 0 / 0 | Go-live
M1 | Kick-off | R5 | NPC: registration of the DPO and the data processing systems confirmed; privacy notice version | FS | 0 / 0 / 0 / 0 | Go-live
C3 | On-screen configuration: Product Configurator (templates, rating factors, acceptance rules, document templates, market mapping), tax codes, posting rules, approvals, roles, schedules | R6 | Tax adviser confirmation: tax codes, ATC, rates, invoice and receipt wording, VAT treatment of commission | SS | 3 / 5 / 8 / 10 | Go-live
D2 | Compliance workshop: AML/CFT programme, IC registers, complaints, breach procedure, masking by role | R7 | Screening lists: UN and AMLC lists obtained; PEP list licence from a provider (when used) | FS | 0 / 0 / 0 / 0 | Go-live
D4 | Branding workshop: theme, logo, sign-in picture, documents, e-signatures, brand pack choice | R8 | Contract reference covering the use of the client's marks on the engagement file (client brand pack only) | FS | 0 / 0 / 0 / 0 | Feature only
D1 | Process workshops on the delivered system: organisation, sales, placement, servicing, claims, billing, remittance, commission, ledger, tax, distribution | C1 | Configuration kit filled: company, settings, PSGC addresses, branches, users, chart of accounts, banks, insurers, products, commission, taxes, authority limits, numbering | SS | 3 / 5 / 6 / 10 | Go-live
I1 | Insurer list and agreements, commission and referrer rates, product list | C1 | Configuration kit filled: company, settings, PSGC addresses, branches, users, chart of accounts, banks, insurers, products, commission, taxes, authority limits, numbering | FS | 0 / 0 / 0 / 0 | Go-live
I2 | Chart of accounts and the accountant's mapping decisions | C1 | Configuration kit filled: company, settings, PSGC addresses, branches, users, chart of accounts, banks, insurers, products, commission, taxes, authority limits, numbering | FS | 0 / 0 / 0 / 0 | Go-live
I3 | User list with roles, branches and reporting lines (My Team follows the reporting line) | C1 | Configuration kit filled: company, settings, PSGC addresses, branches, users, chart of accounts, banks, insurers, products, commission, taxes, authority limits, numbering | FS | 0 / 0 / 0 / 0 | Go-live
C1 | Configuration kit filled: company, settings, PSGC addresses, branches, users, chart of accounts, banks, insurers, products, commission, taxes, authority limits, numbering | C2 | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | FS | 0 / 0 / 0 / 0 | Go-live
E6 | First deployment through the pipeline (CI, deploy, smoke test) to Dev and UAT (and SIT) | C2 | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | FS | 0 / 0 / 0 / 0 | Go-live
C2 | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | C3 | On-screen configuration: Product Configurator (templates, rating factors, acceptance rules, document templates, market mapping), tax codes, posting rules, approvals, roles, schedules | FS | 0 / 0 / 0 / 0 | Go-live
D5 | Configuration decisions and fit-gap register signed | C3 | On-screen configuration: Product Configurator (templates, rating factors, acceptance rules, document templates, market mapping), tax codes, posting rules, approvals, roles, schedules | FS | 0 / 0 / 0 / 0 | Go-live
C2 | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | C4 | Configuration promoted to UAT for the first mock load (Current data workbook) | FS | 0 / 0 / 0 / 0 | Go-live
C3 | On-screen configuration: Product Configurator (templates, rating factors, acceptance rules, document templates, market mapping), tax codes, posting rules, approvals, roles, schedules | C5 | Configuration complete | FS | 0 / 0 / 0 / 0 | Go-live
K1 | Compliance set-up: AML settings, risk factors, monitoring rules; licence register, fit and proper, insurer authority; complaints and breach settings; view:pii grants and masking | C5 | Configuration complete | FS | 0 / 0 / 0 / 0 | Go-live
B1 | Theme and Branding, letterhead, sign-in page, branded documents and e-mails; e-signatures captured and mapped; brand pack exported | C5 | Configuration complete | FS | 0 / 0 / 0 / 0 | Go-live
C2 | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | K1 | Compliance set-up: AML settings, risk factors, monitoring rules; licence register, fit and proper, insurer authority; complaints and breach settings; view:pii grants and masking | FS | 0 / 0 / 0 / 0 | Go-live
D2 | Compliance workshop: AML/CFT programme, IC registers, complaints, breach procedure, masking by role | K1 | Compliance set-up: AML settings, risk factors, monitoring rules; licence register, fit and proper, insurer authority; complaints and breach settings; view:pii grants and masking | FS | 0 / 0 / 0 / 0 | Go-live
R4 | IC: licence data of the firm, officers and agents; certificates of authority of the insurers | K1 | Compliance set-up: AML settings, risk factors, monitoring rules; licence register, fit and proper, insurer authority; complaints and breach settings; view:pii grants and masking | FS | 0 / 0 / 0 / 0 | Go-live
K1 | Compliance set-up: AML settings, risk factors, monitoring rules; licence register, fit and proper, insurer authority; complaints and breach settings; view:pii grants and masking | K2 | Screening lists loaded (UN, AMLC, PEP, internal); clients rescreened | FS | 0 / 0 / 0 / 0 | Go-live
R7 | Screening lists: UN and AMLC lists obtained; PEP list licence from a provider (when used) | K2 | Screening lists loaded (UN, AMLC, PEP, internal); clients rescreened | FS | 0 / 0 / 0 / 0 | Go-live
K1 | Compliance set-up: AML settings, risk factors, monitoring rules; licence register, fit and proper, insurer authority; complaints and breach settings; view:pii grants and masking | K3 | AMLC report file test: CTR file generated in UAT and checked against the AMLC portal requirements | FS | 0 / 0 / 0 / 0 | Go-live
R3 | AMLC: registration of the broker as covered person, portal access, institution code | K3 | AMLC report file test: CTR file generated in UAT and checked against the AMLC portal requirements | FS | 0 / 0 / 0 / 0 | Go-live
C2 | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | B1 | Theme and Branding, letterhead, sign-in page, branded documents and e-mails; e-signatures captured and mapped; brand pack exported | FS | 0 / 0 / 0 / 0 | Go-live
I8 | Logo, sign-in picture, signatories with e-signature consent | B1 | Theme and Branding, letterhead, sign-in page, branded documents and e-mails; e-signatures captured and mapped; brand pack exported | FS | 0 / 0 / 0 / 0 | Go-live
B1 | Theme and Branding, letterhead, sign-in page, branded documents and e-mails; e-signatures captured and mapped; brand pack exported | B2 | Client brand pack applied only in that client's environments under its contract with iorta TechNXT (for example the Toyota Insurance Services pack) | FS | 0 / 0 / 0 / 0 | Feature only
R8 | Contract reference covering the use of the client's marks on the engagement file (client brand pack only) | B2 | Client brand pack applied only in that client's environments under its contract with iorta TechNXT (for example the Toyota Insurance Services pack) | FS | 0 / 0 / 0 / 0 | Feature only
E6 | First deployment through the pipeline (CI, deploy, smoke test) to Dev and UAT (and SIT) | N1 | E-mail: SMTP set, password reset and approval link tested | FS | 0 / 0 / 0 / 0 | Go-live
I4 | SMTP mailbox and credentials | N1 | E-mail: SMTP set, password reset and approval link tested | FS | 0 / 0 / 0 / 0 | Go-live
C2 | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | N2 | Bank statement formats: one statement per bank account imported with a balancing preview | FS | 0 / 0 / 0 / 0 | Go-live
I5 | Bank accounts, one statement export per account, bank contacts for payment files, payee bank accounts | N2 | Bank statement formats: one statement per bank account imported with a balancing preview | FS | 0 / 0 / 0 / 0 | Go-live
C2 | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | N3 | Bank payment files: each layout validated with the bank and a test file accepted by the bank | FS | 0 / 0 / 0 / 0 | Feature only
I5 | Bank accounts, one statement export per account, bank contacts for payment files, payee bank accounts | N3 | Bank payment files: each layout validated with the bank and a test file accepted by the bank | FS | 0 / 0 / 0 / 0 | Feature only
C2 | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | N4 | SMS or Viber connector: provider account, sender name, live test message | FS | 0 / 0 / 0 / 0 | Feature only
I6 | Partner contracts and credentials: SMS provider, CTPL authentication provider, payment gateway, insurer API access | N4 | SMS or Viber connector: provider account, sender name, live test message | FS | 0 / 0 / 0 / 0 | Feature only
C2 | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | N5 | CTPL authentication provider and LTO feed: broker accredited, COC series loaded, live authentication of one COC | FS | 0 / 0 / 0 / 0 | Feature only
I6 | Partner contracts and credentials: SMS provider, CTPL authentication provider, payment gateway, insurer API access | N5 | CTPL authentication provider and LTO feed: broker accredited, COC series loaded, live authentication of one COC | FS | 0 / 0 / 0 / 0 | Feature only
I7 | COC number series from each insurer | N5 | CTPL authentication provider and LTO feed: broker accredited, COC series loaded, live authentication of one COC | FS | 0 / 0 / 0 / 0 | Feature only
C3 | On-screen configuration: Product Configurator (templates, rating factors, acceptance rules, document templates, market mapping), tax codes, posting rules, approvals, roles, schedules | N6 | Insurer API connectors: mapping per insurer, preview, test issuance and claim status with the insurer | SS | 2 / 2 / 2 / 2 | Feature only
I6 | Partner contracts and credentials: SMS provider, CTPL authentication provider, payment gateway, insurer API access | N6 | Insurer API connectors: mapping per insurer, preview, test issuance and claim status with the insurer | FS | 0 / 0 / 0 / 0 | Feature only
C2 | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | N7 | Payment gateway: sandbox payment receipted, then one live test payment | FS | 0 / 0 / 0 / 0 | Feature only
I6 | Partner contracts and credentials: SMS provider, CTPL authentication provider, payment gateway, insurer API access | N7 | Payment gateway: sandbox payment receipted, then one live test payment | FS | 0 / 0 / 0 / 0 | Feature only
C3 | On-screen configuration: Product Configurator (templates, rating factors, acceptance rules, document templates, market mapping), tax codes, posting rules, approvals, roles, schedules | N8 | BIR EIS connector set in test mode; payloads checked | FS | 0 / 0 / 0 / 0 | Feature only
N8 | BIR EIS connector set in test mode; payloads checked | N9 | BIR EIS connector live (after enrolment); earlier invoices queued | FS | 0 / 0 / 0 / 0 | Feature only
R2 | BIR: EIS enrolment and certification (when the broker is covered) | N9 | BIR EIS connector live (after enrolment); earlier invoices queued | FS | 0 / 0 / 0 / 0 | Feature only
X6 | Go-live | N9 | BIR EIS connector live (after enrolment); earlier invoices queued | FS | 0 / 0 / 0 / 0 | Feature only
M3 | Data request list and the go-live kits issued (configuration and migration workbooks, upload templates) | G1 | Extraction and cleansing of the old system data for the first mock load | FS | 0 / 0 / 0 / 0 | Go-live
G1 | Extraction and cleansing of the old system data for the first mock load | G2 | Mapping to the migration kit (clients, policies, open items, open claims, opening balances) | SS | 3 / 5 / 8 / 10 | Go-live
G1 | Extraction and cleansing of the old system data for the first mock load | G3 | Mock load 1: cutover date set, validate, errors workbook, load, reconciliation | FS | 0 / 0 / 0 / 0 | Go-live
G2 | Mapping to the migration kit (clients, policies, open items, open claims, opening balances) | G3 | Mock load 1: cutover date set, validate, errors workbook, load, reconciliation | FS | 0 / 0 / 0 / 0 | Go-live
C4 | Configuration promoted to UAT for the first mock load (Current data workbook) | G3 | Mock load 1: cutover date set, validate, errors workbook, load, reconciliation | FS | 0 / 0 / 0 / 0 | Go-live
C2 | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | G3 | Mock load 1: cutover date set, validate, errors workbook, load, reconciliation | FS | 0 / 0 / 0 / 0 | Go-live
G3 | Mock load 1: cutover date set, validate, errors workbook, load, reconciliation | G4 | Mock load 2 on a fresh extract, with transaction reset before it | FS | 0 / 0 / 0 / 0 | Go-live
C5 | Configuration complete | G4 | Mock load 2 on a fresh extract, with transaction reset before it | FS | 0 / 0 / 0 / 0 | Go-live
G4 | Mock load 2 on a fresh extract, with transaction reset before it | G5 | Mock load 3 in UAT (large, enterprise) | FS | 0 / 0 / 0 / 0 | Go-live
T3 | Release candidate and frozen configuration promoted to UAT (Current data workbook, brand pack); comparison report clean | G5 | Mock load 3 in UAT (large, enterprise) | FS | 0 / 0 / 0 / 0 | Go-live
G5 | Mock load 3 in UAT (large, enterprise) | G6 | Mock load 4 in UAT (enterprise) | FS | 0 / 0 / 0 / 0 | Go-live
C5 | Configuration complete | L1 | Train-the-trainer for key users, with trainer skills and teach-back | FS | 0 / 0 / 0 / 0 | Go-live
K1 | Compliance set-up: AML settings, risk factors, monitoring rules; licence register, fit and proper, insurer authority; complaints and breach settings; view:pii grants and masking | L2 | Compliance officer, DPO and System Administrator training on the compliance and privacy screens | FS | 0 / 0 / 0 / 0 | Go-live
L1 | Train-the-trainer for key users, with trainer skills and teach-back | L3 | End-user training per role, run by key users | FS | 0 / 0 / 0 / 0 | Go-live
T3 | Release candidate and frozen configuration promoted to UAT (Current data workbook, brand pack); comparison report clean | L3 | End-user training per role, run by key users | FS | 0 / 0 / 0 / 0 | Go-live
I9 | Training rooms, devices and attendance list | L3 | End-user training per role, run by key users | FS | 0 / 0 / 0 / 0 | Go-live
C3 | On-screen configuration: Product Configurator (templates, rating factors, acceptance rules, document templates, market mapping), tax codes, posting rules, approvals, roles, schedules | T1 | System integration test in Dev (small, medium) or SIT (large, enterprise): end-to-end flows, uat-scenario.js, connectors in test mode | SS | 4 / 6 / 18 / 25 | Go-live
C2 | Configuration kit uploaded, validated, errors workbook corrected and loaded in Dev (small, medium) or SIT (large, enterprise) | T1 | System integration test in Dev (small, medium) or SIT (large, enterprise): end-to-end flows, uat-scenario.js, connectors in test mode | FS | 0 / 0 / 0 / 0 | Go-live
T1 | System integration test in Dev (small, medium) or SIT (large, enterprise): end-to-end flows, uat-scenario.js, connectors in test mode | T2 | SIT exit | FS | 0 / 0 / 0 / 0 | Go-live
C5 | Configuration complete | T2 | SIT exit | FS | 0 / 0 / 0 / 0 | Go-live
T2 | SIT exit | T3 | Release candidate and frozen configuration promoted to UAT (Current data workbook, brand pack); comparison report clean | FS | 0 / 0 / 0 / 0 | Go-live
E3 | UAT provisioned | T3 | Release candidate and frozen configuration promoted to UAT (Current data workbook, brand pack); comparison report clean | FS | 0 / 0 / 0 / 0 | Go-live
T3 | Release candidate and frozen configuration promoted to UAT (Current data workbook, brand pack); comparison report clean | T4 | UAT cycles with the UAT scripts and broker scenarios, including compliance, BIR and integration scripts | FS | 0 / 0 / 0 / 0 | Go-live
I10 | UAT testers and sign-off authority named | T4 | UAT cycles with the UAT scripts and broker scenarios, including compliance, BIR and integration scripts | FS | 0 / 0 / 0 / 0 | Go-live
T4 | UAT cycles with the UAT scripts and broker scenarios, including compliance, BIR and integration scripts | T5 | UAT sign-off | FS | 0 / 0 / 0 / 0 | Go-live
R6 | Tax adviser confirmation: tax codes, ATC, rates, invoice and receipt wording, VAT treatment of commission | T5 | UAT sign-off | FS | 0 / 0 / 0 / 0 | Go-live
T3 | Release candidate and frozen configuration promoted to UAT (Current data workbook, brand pack); comparison report clean | X1 | Release tag and frozen configuration deployed to Production; production smoke test; transaction reset | FS | 0 / 0 / 0 / 0 | Go-live
E7 | Production provisioned at production topology; backups, monitoring, restore test | X1 | Release tag and frozen configuration deployed to Production; production smoke test; transaction reset | FS | 0 / 0 / 0 / 0 | Go-live
R1 | BIR: Authority to Print or CAS registration and the invoice serial range confirmed (new or existing); last numbers used | X1 | Release tag and frozen configuration deployed to Production; production smoke test; transaction reset | FS | 0 / 0 / 0 / 0 | Go-live
X1 | Release tag and frozen configuration deployed to Production; production smoke test; transaction reset | X2 | Pre-Prod created from a production backup (masked when people without production access take part) | FS | 0 / 0 / 0 / 0 | Go-live
X2 | Pre-Prod created from a production backup (masked when people without production access take part) | X3 | Cutover rehearsal in Pre-Prod: reset, migration load of a fresh extract, reconciliation, go-live lock, comparison against Production, timings | FS | 0 / 0 / 0 / 0 | Go-live
G4 | Mock load 2 on a fresh extract, with transaction reset before it | X3 | Cutover rehearsal in Pre-Prod: reset, migration load of a fresh extract, reconciliation, go-live lock, comparison against Production, timings | FS | 0 / 0 / 0 / 0 | Go-live
G5 | Mock load 3 in UAT (large, enterprise) | X3 | Cutover rehearsal in Pre-Prod: reset, migration load of a fresh extract, reconciliation, go-live lock, comparison against Production, timings | FS | 0 / 0 / 0 / 0 | Go-live
G6 | Mock load 4 in UAT (enterprise) | X3 | Cutover rehearsal in Pre-Prod: reset, migration load of a fresh extract, reconciliation, go-live lock, comparison against Production, timings | FS | 0 / 0 / 0 / 0 | Go-live
T4 | UAT cycles with the UAT scripts and broker scenarios, including compliance, BIR and integration scripts | X3 | Cutover rehearsal in Pre-Prod: reset, migration load of a fresh extract, reconciliation, go-live lock, comparison against Production, timings | SS | 4 / 5 / 6 / 15 | Go-live
X3 | Cutover rehearsal in Pre-Prod: reset, migration load of a fresh extract, reconciliation, go-live lock, comparison against Production, timings | X4 | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | FS | 0 / 0 / 0 / 0 | Go-live
T5 | UAT sign-off | X4 | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | FS | 0 / 0 / 0 / 0 | Go-live
L3 | End-user training per role, run by key users | X4 | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | FS | 0 / 0 / 0 / 0 | Go-live
L2 | Compliance officer, DPO and System Administrator training on the compliance and privacy screens | X4 | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | FS | 0 / 0 / 0 / 0 | Go-live
K2 | Screening lists loaded (UN, AMLC, PEP, internal); clients rescreened | X4 | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | FS | 0 / 0 / 0 / 0 | Go-live
K3 | AMLC report file test: CTR file generated in UAT and checked against the AMLC portal requirements | X4 | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | FS | 0 / 0 / 0 / 0 | Go-live
N1 | E-mail: SMTP set, password reset and approval link tested | X4 | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | FS | 0 / 0 / 0 / 0 | Go-live
N2 | Bank statement formats: one statement per bank account imported with a balancing preview | X4 | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | FS | 0 / 0 / 0 / 0 | Go-live
R5 | NPC: registration of the DPO and the data processing systems confirmed; privacy notice version | X4 | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | FS | 0 / 0 / 0 / 0 | Go-live
B1 | Theme and Branding, letterhead, sign-in page, branded documents and e-mails; e-signatures captured and mapped; brand pack exported | X4 | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | FS | 0 / 0 / 0 / 0 | Go-live
X4 | Go/no-go 1: UAT signed, rehearsal reconciled, users trained, registrations and partner states confirmed | X5 | Cutover: freeze, final extract, final load, reconciliation, go/no-go 2, golive.locked, mask:data --register-production | FS | 0 / 0 / 0 / 0 | Go-live
X5 | Cutover: freeze, final extract, final load, reconciliation, go/no-go 2, golive.locked, mask:data --register-production | X6 | Go-live | FS | 0 / 0 / 0 / 0 | Go-live
X6 | Go-live | H1 | Hypercare: daily check-ins in week 1, then weekly; first receipts, remittances, bank imports and payment files watched | FS | 0 / 0 / 0 / 0 | Hypercare exit
X6 | Go-live | H2 | First month-end close and BIR working papers of the first month supported | FS | 5 / 10 / 15 / 15 | Hypercare exit
H1 | Hypercare: daily check-ins in week 1, then weekly; first receipts, remittances, bank imports and payment files watched | H3 | Knowledge transfer, configuration baseline (Current data workbook of Production), handover; Pre-Prod removed | FS | 0 / 0 / 0 / 0 | Hypercare exit
H2 | First month-end close and BIR working papers of the first month supported | H3 | Knowledge transfer, configuration baseline (Current data workbook of Production), handover; Pre-Prod removed | FS | 0 / 0 / 0 / 0 | Hypercare exit

## RACI
RACI: iorta TechNXT, the broker and the partners
R = Responsible, A = Accountable (one per activity), C = Consulted, I = Informed.
Phase | Activity | iorta TechNXT PM | iorta TechNXT consultants | iorta TechNXT technical / DevOps | Broker sponsor | Broker PM | Broker key users / process owners | Broker IT / System Administrator | Broker Accounting Manager | Broker compliance officer / DPO | Partners (banks, SMS, CTPL provider, insurers, gateway)
Mobilisation | Project charter and baselined plan | R | C | C | A | R | I | I | I | I | I
Mobilisation | Governance set-up (steering committee, status, RAID log) | R | I | I | A | R | I | I | I | I | I
Mobilisation | Data request list and go-live kits issued and tracked | R | C | C | I | A | C | C | C | C | I
Mobilisation | Hosting option, environment set and data location decision | C | I | C | A | R | I | R | I | C | I
Environments and pipeline | Dev, SIT, UAT and Production provisioned; Pre-Prod when needed | A | I | R | I | I | I | C | I | I | I
Environments and pipeline | GitHub Environments, protection rules, reviewers, variables and secrets | C | I | A | I | I | I | C | I | I | I
Environments and pipeline | Encryption keys (DATA_ENCRYPTION_KEY, PII_ENCRYPTION_KEY): generation, custody, escrow copy, rotation | I | I | R | I | I | I | A | I | C | I
Environments and pipeline | Backups, restore test, monitoring | A | I | R | I | I | I | C | I | I | I
Discovery and fit-gap | Discovery workshops | A | R | I | I | R | R | C | R | C | I
Discovery and fit-gap | Configuration decisions and fit-gap register sign-off | C | R | I | I | A | R | C | R | C | I
Configuration | Configuration kit filled (masters, users, chart of accounts, insurers, products, taxes, numbering) | C | R | I | I | A | R | R | R | I | I
Configuration | Configuration kit validated and loaded; errors workbook | A | R | C | I | I | C | R | I | I | I
Configuration | Product Configurator: templates, rating factors, acceptance rules, document templates, market mapping | A | R | I | I | C | R | C | I | I | I
Configuration | Tax codes, premium taxes, LGU rates, posting rules, account determination | A | R | I | I | C | C | I | R | I | I
Configuration | Document numbering and invoice serial range (ATP or CAS) | A | R | I | I | C | C | C | R | I | I
Configuration | Approvals, maker-checker, authority matrix, roles and view:pii grants | A | R | C | I | C | R | R | R | C | I
Compliance set-up | AML settings, risk factors, monitoring rules | C | R | I | I | I | I | C | I | A | I
Compliance set-up | Screening lists obtained, licensed and loaded | I | C | I | I | C | I | C | I | A | R
Compliance set-up | IC licence register, fit and proper records, insurer certificates of authority | I | R | I | I | C | C | C | I | A | I
Compliance set-up | Complaints and breach register settings; DPO and NPC registration confirmed | I | R | I | C | C | C | C | I | A | I
Branding and brand pack | Theme, letterhead, branded documents and e-mails, e-signatures mapped, brand pack | A | R | C | C | C | C | R | I | I | I
Branding and brand pack | Contract reference covering the use of client marks (client brand pack) | C | I | I | A | R | I | I | I | I | C
Data migration | Extraction and cleansing of the old system data | I | C | I | I | A | R | R | R | I | I
Data migration | Mapping to the migration kit | A | R | C | I | C | R | C | C | I | I
Data migration | Mock loads and reconciliation | A | R | R | I | C | R | C | R | I | I
Data migration | Sign-off of opening balances and open items | C | C | I | I | C | C | I | A | I | I
Integrations | SMTP mailbox and credentials | I | I | R | I | C | I | A | I | I | I
Integrations | Bank statement formats and bank payment file layouts | A | R | C | I | I | R | C | C | I | R
Integrations | SMS or Viber, CTPL authentication and LTO, insurer API connectors, payment gateway | C | R | R | I | A | C | R | I | I | R
Integrations | BIR EIS connector and enrolment | I | R | C | I | C | I | C | A | I | I
Regulatory registrations | BIR ATP or CAS, EIS enrolment; AMLC registration; NPC registration; IC licences | I | C | I | A | R | I | I | R | R | I
Training | Train-the-trainer | A | R | I | I | C | R | C | C | C | I
Training | End-user training and assessment | C | C | I | I | A | R | C | C | C | I
Training | Compliance officer and DPO training | C | R | I | I | C | I | C | I | A | I
SIT and UAT | SIT execution and defect fixing | A | R | R | I | I | C | I | I | I | C
SIT and UAT | UAT execution | C | C | I | I | A | R | R | R | R | I
SIT and UAT | UAT sign-off | C | C | I | A | R | R | C | R | R | I
Rehearsal and cutover | Release and frozen configuration to Production; comparison report | A | R | R | I | C | I | C | I | I | I
Rehearsal and cutover | Pre-Prod from a production backup; masking approval | C | I | R | I | C | I | C | I | A | I
Rehearsal and cutover | Cutover rehearsal, final loads and reconciliation | A | R | R | I | C | R | C | R | I | I
Rehearsal and cutover | Go/no-go decision | C | C | C | A | R | C | C | C | C | I
Go-live and hypercare | Go-live communication to users, insurers, banks and partners | C | I | I | A | R | C | C | I | I | I
Go-live and hypercare | Hypercare issue handling | A | R | R | I | R | C | R | C | C | C
Go-live and hypercare | First month-end close and first BIR and AMLC filings | C | R | C | I | I | R | I | A | R | I
Go-live and hypercare | Handover to production support | A | R | R | I | C | I | R | I | I | I
Change control | Change request impact assessment | A | R | R | I | C | C | C | C | C | I
Change control | Change request approval | C | I | I | A | R | C | C | C | C | I