Prepared by – iorta TechNXT

Version - 1.0

Date - 04 October 2026

Environment Strategy

and Production Rollout Plan

TABLE OF CONTENTS

1. Document Control	4

2. Acronyms	4

3. Introduction	5

3.1 Purpose	5

3.2 Sources and labels	5

3.3 Related documents	6

4. Environments	7

4.1 The five environment roles	7

4.2 Environment sets by broker size	7

4.3 Pre-Prod lifecycle	8

4.4 Hosting by option	8

4.5 Sizing and hosting cost	9

4.6 Access control	10

4.7 Refresh policy	10

4.8 Pre-Prod: what must be identical to Production	11

4.9 Data masking	12

5. Moving code and database scripts	13

5.1 Git branching and release tagging	13

5.2 What CI checks	13

5.3 Release pipeline and approval gates	13

5.4 Build once, promote the same artefact	13

5.5 Front-end build and runtime configuration	14

5.6 Schema migrations	14

5.7 Reference seeds	15

5.8 Environment variables and secrets	15

5.9 Promotion steps	16

5.10 Change and release management	17

5.11 Rollback	17

6. Moving configuration	18

6.1 The configuration workbook	18

6.2 Promotion procedure	18

6.3 Not in the workbook	19

6.4 Configuration freeze	20

6.5 Comparing environments	20

6.6 Comparison report	20

7. Client data flow	21

7.1 The two workbooks the broker fills	21

7.2 Mock loads and the final load	21

7.3 Keeping migrated and new business apart and in step	22

8. Smoke test and go-live	24

8.1 Order of events	24

8.2 Hypercare	24

9. Cutover runbook	26

9.1 Conventions	26

9.2 T-30 to T-1	26

9.3 T to T+30	28

10. RACI and checklists	30

10.1 RACI for environment and release activities	30

10.2 Checklist: system integration test (Dev or SIT)	30

10.3 Checklist: Dev or SIT to UAT	31

10.4 Checklist: UAT to Production and the Pre-Prod rehearsal	31

10.5 Checklist: go-live in Production	31

10.6 Checklist: release after go-live	31

11. Decisions and sections to complete	33

12. Document Sign-Off	34

# 1.  Document Control

| Date | Version | Author & Business Unit Info | Reviewed By & Business Unit Info | Approved By & Business Unit Info | Change History |
| --- | --- | --- | --- | --- | --- |
| 04 October 2026 | 1.0 | iorta TechNXT |  |  | Initial issue |

# 2.  Acronyms

| Acronym / Symbol | Definition / Meaning |
| --- | --- |
| OOTB | Out of the box |
| Dev | Development environment |
| DR | Disaster recovery |
| SIT | System integration test |
| UAT | User acceptance test |
| Pre-Prod | Pre-production |
| CI | Continuous integration |
| CAB | Change advisory board |
| RACI | Responsible, Accountable, Consulted, Informed |
| GL | General ledger |
| TB | Trial balance |
| PITR | Point-in-time restore |
| PM | Project manager |
| PHT | Philippine time (UTC+8) |
| API | Application programming interface |
| XLSX | Excel workbook |
| DPA | Data Privacy Act of 2012 |
| P1, P2 | Incident priorities 1 and 2 |

# 3.  Introduction

## 3.1  Purpose

This document answers the product owner's questions on how BrokerVerse OOTB is run across environments and taken into production for a broker:

- which environments exist, what each is for, who uses it, which data it holds, how it is hosted and sized, who may access it and how it is refreshed;

- how code and database scripts move from one environment to the next, with the checks, sign-offs and rollback at each step;

- how configuration moves between environments with the Go-Live Data Workbench, and what has to be entered or scripted separately;

- how the broker's own data flows in, how migrated business and new business are kept apart and in step;

- how the smoke test, the transaction reset, the final migration and the go-live lock fit together;

- the cutover runbook from 30 days before to 30 days after go-live, the RACI and the checklists for each promotion.

## 3.2  Sources and labels

Facts come from the code and the deployment files of the repository (IortaTexhNXT-DEV/BDOI-OOTB, branch brokerverse-platform, release tag v1.0.0): deploy/README.md, deploy/REFERENCE.md, deploy/RAILWAY.md, deploy/ec2/, .github/workflows/, backend/src/db/ (migrations and seeds), backend/scripts/ and backend/src/modules/data-load (the Go-Live Data Workbench). Text marked Recommended is iorta TechNXT practice, not something the code enforces. Text marked Decision is a product owner decision of 04 October 2026: the environment set by broker size, the temporary Pre-Prod, hosting per environment, one front-end build for all environments, a release pipeline with approval gates, a comparison report between environments and a data masking tool. Sections marked Section to be completed with the release describe deliveries still being built and are completed when they are released.

## 3.3  Related documents

| Document | Use with this document |
| --- | --- |
| Data Migration and Cutover Plan | Data objects, control figures, mock loads, cutover checklist, go/no-go criteria, rollback of the data |
| Implementation Approach and Plan | Phases, timelines by broker size, project RACI, deliverables |
| UAT and Go-Live Acceptance Certificates | Form 1 (UAT Sign-off) and Form 2 (Go-live Acceptance) signed at the checkpoints of chapter 9 |
| Hypercare Exit and Handover Certificate | End of hypercare and handover to support |
| Production Support Approach and Standards | Change types, CAB, release management, patching, regression testing |
| Release Notes Template | One copy per release or patch, attached to the CAB record |
| Business Continuity and Disaster Recovery Plan | Backups, restore procedures, recovery objectives |
| Architecture, Infrastructure, Security and Privacy | Hosting options A, B and C, sizing, CI/CD, secrets |
| Commercials and pricing workbook (BrokerVerse_Commercials_and_Pricing.xlsx) and Rate Card | Hosting price of each environment by broker size and provider |
| docs/onboarding/GO_LIVE_DATA_WORKBENCH.md | Go-Live Data Workbench: workbooks, validation, load, reconciliation |
| docs/onboarding/SMOKE_TEST_AND_RESET.md | Smoke test, transaction reset and go-live lock |
| docs/onboarding/GO_LIVE_DATA_SETUP.md | Step-by-step business set-up of a new installation |

# 4.  Environments

## 4.1  The five environment roles

|  | Dev | SIT | UAT | Pre-Prod | Production |
| --- | --- | --- | --- | --- | --- |
| Purpose | Development and integration of changes; first run of every migration; for small and medium brokers also the configuration build and the system integration test | Large brokers only: end-to-end test of a release with all roles; configuration build; mock loads | Business acceptance by the broker's key users; training; mock loads (all mock loads for small and medium brokers) | Temporary: dress rehearsal of the cutover; production smoke test; rehearsal of each major release after go-live | Live operations |
| Main users | iorta TechNXT developers and consultants | iorta TechNXT consultants and testers; migration lead | Broker key users, trainers, broker System Administrator; iorta TechNXT consultants | iorta TechNXT DevOps and migration lead; broker System Administrator, Accounting Manager and key users for the smoke test | All broker users; iorta TechNXT support by ticket |
| Data | Demo data (SEED_SAMPLE_DATA=true), synthetic UAT data (backend/scripts/uat-scenario.js) and the broker's configuration | Reference data, synthetic UAT data, the broker's configuration, mock-load data | Reference data, the broker's configuration, mock-load data from the broker's extracts | A restored production backup; before go-live it holds the production configuration and the rehearsal loads a fresh extract | Reference data, the broker's configuration, the final migration, then live business |
| Personal data | None (fictional) | Synthetic; client data during mock loads | Client data from the extracts | Client data; masked when used by people without production access | Client data |
| Release deployed | Any commit of a feature or fix branch | Release candidate tag | Release candidate tag that passed the system integration test | The tag to go to Production | Tag approved by the CAB |

Decision: The broker's own data appears from the first mock load onwards. From that point the environment holding it is protected as Production is (section 4.6). A copy of production data used by people who have no production access is masked first, with the data masking tool (section 4.9). The privacy module anonymises one data subject at a time and is not used for bulk masking.

## 4.2  Environment sets by broker size

Decision: the environment set follows the broker size. Small and medium brokers have three standing environments: integration is done in the Dev instance and the release is pushed to UAT for testing, then to Production. Large brokers have four: SIT and UAT are separate. Pre-Prod is temporary for every size.

| Role | Small broker | Medium broker | Large broker (and Enterprise) |
| --- | --- | --- | --- |
| Dev | Own Dev instance, small size: development, configuration build, integration and system integration test | As small | Own Dev instance, small size: development and integration |
| SIT | Not separate: done in Dev | Not separate: done in Dev | Own environment, medium size, separate from UAT |
| UAT | Own environment, small size | Own environment, small size | Own environment, medium size |
| Pre-Prod | Temporary | Temporary | Temporary |
| Production | Own environment, sized by tier | Own environment, sized by tier | Own environment with high availability; Enterprise adds a cross-region copy of the backups |

The set is recorded in the Order Form (hosting fields) and in the environment sheet. A broker that hosts BrokerVerse itself provides the same set.

## 4.3  Pre-Prod lifecycle

Decision: Pre-Prod is temporary for every broker size.

| Step | Rule |
| --- | --- |
| When it is created | For the go-live rehearsal (from about T-18 to the end of hypercare) and for each major release (about one month around the release) |
| Source | A backup of Production, restored at production topology and size. Before go-live, Production holds the production configuration promoted from UAT and no business; the rehearsal loads a fresh extract |
| Masking | Required before people without production access use it, with the data masking tool (section 4.9). People with production access may use the unmasked copy under the Production access rules |
| On restore | Own secrets, e-mail off, scheduler stopped, go-live lock handled as in section 4.8 |
| Removal | After hypercare exit, or after the release: database, file store, backups and secrets deleted; the deletion recorded in the environment sheet |
| Hosting | Billed per month of use (section 3.5) |

Each creation of Pre-Prod restores a Production backup in full and is recorded as a restore test of the Business Continuity and Disaster Recovery Plan.

Minor and patch releases do not use Pre-Prod: they are rehearsed in UAT (and in SIT for a large broker), and a snapshot of Production is taken before deploying.

## 4.4  Hosting by option

Every environment needs the same building blocks: the web build, the API (container from backend/Dockerfile or Node.js 22 under PM2), PostgreSQL 16 with the Asia/Manila time zone, a persistent file store at UPLOAD_DIR and a secret store. The hosting options are those of the Architecture document.

| Environment | Option A: AWS Singapore | Option B: Azure Southeast Asia | Option C: Philippine partner or on-premise | Railway |
| --- | --- | --- | --- | --- |
| Dev | One API task or one EC2 host (Docker Compose, or PM2 as in deploy/ec2), small RDS single-AZ | One VM or Container Apps replica, small Flexible Server without HA | One VM with Docker Compose | Suitable (deploy/RAILWAY.md) |
| SIT (large broker) | One API task (ECS Fargate or EC2), RDS single-AZ, EFS | One Container Apps replica, Flexible Server without HA, Azure Files | One API VM, one PostgreSQL VM, NFS share | Suitable for SIT and demo |
| UAT | As SIT, sized for the UAT performance test | As SIT | As SIT | Suitable when no performance test is needed |
| Pre-Prod (temporary) | Same topology as Production, restored from a Production backup: two API tasks behind a load balancer, RDS Multi-AZ, EFS, CloudFront | Same topology as Production | Same topology as Production | Not suitable |
| Production | Two or more API tasks, ALB, RDS Multi-AZ, EFS, CloudFront and WAF | Two or more replicas across zones, zone-redundant Flexible Server | Two API VMs, primary and standby PostgreSQL, redundant NFS | Not suitable: one API instance, volume attached to one instance |

The demo deployment of the repository (.github/workflows/deploy-frontend.yml with deploy/ec2/deploy.sh: one PM2 process on port 8001 behind nginx) is a single instance without redundancy. It is fit for Dev, SIT or a demonstration, not for Production.

## 4.5  Sizing and hosting cost

Production sizes are those of the Architecture document and must be confirmed with the UAT performance test. Sizes for the other environments are those priced in the commercials and pricing workbook.

| Item | Dev (every size) | UAT (small, medium) | SIT and UAT (large) | Pre-Prod | Production small / medium / large |
| --- | --- | --- | --- | --- | --- |
| API | 1 x 1 vCPU, 2 GB | 1 x 1 vCPU, 2 GB | 1 x 1 vCPU, 2 GB (2 instances in UAT for the performance test) | As Production | 2 x 1 vCPU, 2 GB / 2 x 1 vCPU, 2 GB / 3 to 4 x 2 vCPU, 4 GB |
| Database | 2 vCPU, 4 GB, no standby | 2 vCPU, 4 GB, no standby | 2 vCPU, 8 GB, no standby | As Production | 2 vCPU, 4 GB / 2 vCPU, 8 GB / 4 vCPU, 16 GB, each with standby |
| Database storage | 20 GB | 50 GB | 100 GB | As Production | 50 / 100 / 250 GB |
| File store | 10 GB | 25 GB | 25 GB | As Production | 25 / 60 / 150 GB (year 1) |
| Backups | Weekly | Daily, 14 days | Daily, 7 days (SIT), 14 days (UAT) | Daily while it exists | Daily with PITR, 35 days |

Hosting price per month when iorta TechNXT hosts on AWS (Singapore), PHP excluding VAT, from the pricing workbook (Infrastructure sheet) and the Rate Card. Azure and the local partner are priced on the same sheet.

| Broker size | Dev | SIT | UAT | Production | Standing set per month | Pre-Prod per month of use |
| --- | --- | --- | --- | --- | --- | --- |
| Small | 11,000.00 | Not used | 11,000.00 | 21,000.00 | 43,000.00 | 21,000.00 |
| Medium | 11,000.00 | Not used | 11,000.00 | 47,000.00 | 69,000.00 | 47,000.00 |
| Large | 11,000.00 | 23,000.00 | 23,000.00 | 86,000.00 | 143,000.00 | 86,000.00 |
| Enterprise | 11,000.00 | 23,000.00 | 23,000.00 | 199,000.00 | 256,000.00 | 169,000.00 |

Pre-Prod runs at production size and is billed only for the months it exists. The workbook budgets 2 months around go-live and 1 month for each major release. Hosting fees do not increase yearly; provider price changes are passed through at cost (Hosting and Infrastructure Services Agreement).

## 4.6  Access control

| Environment | Application sign-in | Server, database and secret store | Rule |
| --- | --- | --- | --- |
| Dev | iorta TechNXT developers and consultants; demo users and UAT personas | iorta TechNXT developers | No client data, ever |
| SIT (large broker) | iorta TechNXT consultants and testers; UAT personas created by uat-scenario.js (uat.maria.sales and others) | iorta TechNXT DevOps | Client data only during mock loads; named accounts only |
| UAT | Broker key users and trainers with one role each; iorta TechNXT consultants | iorta TechNXT DevOps | Access list approved by the broker PM; two-step verification for system-admin, accounting and accounting-manager |
| Pre-Prod | Named people of the rehearsal and smoke test | iorta TechNXT DevOps; database access logged | Same controls as Production; masked first if anyone without production access uses it |
| Production | Broker users with their role; System Administrator role held by few people | iorta TechNXT DevOps under ticket and change approval | deploy/README.md section 5; Production Support change rules |

Rules for every environment:

- Each environment has its own secrets. JWT_SECRET and DATA_ENCRYPTION_KEY differ between environments and are never reused from development (Architecture document).

- The BrokerVerse administrator password from ADMIN_PASSWORD is changed at the first sign-in, in every environment.

- The permissions of the Go-Live Data Workbench (read:data-load, write:data-load) are held by the System Administrator only.

- E-mail: in Dev, SIT and UAT, either keep "Send e-mails" off (Master > Configuration > Notification) or give test clients and insurers internal addresses, so that no client or insurer receives a test document.

- Payment gateways use sandbox credentials outside Production.

## 4.7  Refresh policy

| Environment | When refreshed | How |
| --- | --- | --- |
| Dev | At will | npm run db:reset (drops and recreates the schema, then seeds). Never run outside Dev |
| SIT (large broker) | Before each SIT cycle and before each mock load | Transaction reset (CONFIRM_RESET=yes npm run reset:transactions -- --execute): masters and configuration stay, business records and opening balances go; then the next mock load. A full rebuild restores the configured baseline snapshot instead |
| UAT | Start of each UAT cycle; before each mock load | Configuration promoted from Dev (small, medium) or SIT (large) with the configuration workbook; transaction reset; migration workbook of the latest extract |
| Pre-Prod | Never refreshed in place | Created from a Production backup for the go-live rehearsal or a major release, then removed (section 4.3) |
| Production | Never refreshed | Only releases, CAB-approved configuration changes and live business |

The transaction reset refuses to run while golive.locked is on. Lower environments keep the lock off. Each refresh is recorded in the environment sheet with the date, the source and the person who ran it.

## 4.8  Pre-Prod: what must be identical to Production

| Must be identical | Why |
| --- | --- |
| Release tag, backend image or commit, front-end build of the same tag | The rehearsal proves the exact code that goes live |
| Node.js 22, PostgreSQL 16 (same minor version), database time zone Asia/Manila | Reports, cut-off times and scheduled jobs use the database date |
| Topology: number of API instances, load balancer, file store type, CDN rules (/api/* not cached, single-page fallback) | Behaviour of the scheduler lock, file links and health checks |
| Non-secret environment values: NODE_ENV=production, SEED_SAMPLE_DATA=false, SCHEDULER_ENABLED, upload and import limits, token lifetimes, LOG_LEVEL | The production start-up check runs; limits behave the same |
| Configuration: everything in the configuration workbook and every on-screen item of section 6.3 | The smoke test and rehearsal run on the production set-up |
| Document numbering series (prefix, pattern, reset rule) | Numbers look as they will in Production |
| Migration list of the database (schema_migrations) | No pending migration on either side before a release |

What differs, by design: secrets (JWT_SECRET, DATA_ENCRYPTION_KEY, ADMIN_PASSWORD, database password, SMTP password), addresses (CORS_ORIGINS, PUBLIC_BASE_URL, REACT_APP_BASE_URL), payment gateway credentials (sandbox), e-mail recipients, and APP_ENVIRONMENT, which names the environment on the Instructions sheet of an exported workbook.

Pre-Prod is always restored from a Production backup. At each restore:

- Users with two-step verification sign in only if Pre-Prod uses the same DATA_ENCRYPTION_KEY as the backup. Recommended: keep Pre-Prod's own key and have an administrator turn two-step verification off for the rehearsal users, who enrol again (deploy/REFERENCE.md).

- The restored database has golive.locked on. A System Administrator switches it off in Master > Configuration > Go-live before any reset; the change is recorded in the audit trail. This is never done in Production.

- Turn "Send e-mails" off and stop the scheduler (SCHEDULER_ENABLED=false) before the first start, so that reminders and renewal notices are not sent to real clients from Pre-Prod.

- Mask the copy with the data masking tool before anyone without production access signs in (section 4.9).

## 4.9  Data masking

Decision: a data masking tool is required. It masks the personal data of a restored production copy before it is used by people who have no access to Production, for example a Pre-Prod copy for a release rehearsal with testers, or a training copy.

Section to be completed with the release. The tool, what it masks, how it is run and how a masked copy is checked are described when the tool is released.

# 5.  Moving code and database scripts

## 5.1  Git branching and release tagging

| Branch or tag | Use |
| --- | --- |
| brokerverse-platform | Release branch of BrokerVerse OOTB; what is deployed comes from here |
| feature/<ticket>-<short-name> | Recommended for changes; merged by pull request |
| fix/<ticket>-<short-name> | Fixes, started from the release tag running in Production (Production Support, code fix standards) |
| vX.Y.Z tag | One per release: patch (1.0.z), minor (1.y.0), major (x.0.0), as in the Release Notes Template. v1.0.0 is the first release |

Every change reaches brokerverse-platform through a pull request reviewed by an engineer other than the author. A fix merged to the release branch is also merged into the main development line so it is not lost in the next release.

## 5.2  What CI checks

.github/workflows/ci.yml runs on every pull request:

| Job | Steps |
| --- | --- |
| Backend | Node.js 22; npm ci; npm run lint (ESLint on src, test, scripts); npm test (vitest) against a postgres:16 service database brokerverse_test |
| Frontend | Node.js 22; npm ci --legacy-peer-deps; npx craco test --watchAll=false |

The backend tests build the schema from the migrations, so a migration that does not apply on an empty database fails CI.

.github/workflows/deploy-frontend.yml (CI/CD Pipeline) runs on a push to brokerverse-platform: it builds the front end, publishes it to S3 and CloudFront, and reloads the API on the EC2 host through deploy/ec2/deploy.sh, which waits for /api/health to answer 200. Its lint and test jobs are commented out, so a push deploys without tests, and it serves one environment.

Decision: the manual deployment is replaced by a release pipeline built to current practice: changes arrive on brokerverse-platform only by pull request with a green CI run, the tests run before any deployment, and each environment has its own deployment step started from a tag, with an approval gate per environment. Until the pipeline is released, each deployment to SIT, UAT, Pre-Prod and Production is started by the DevOps lead from the approved tag.

## 5.3  Release pipeline and approval gates

Section to be completed with the release. The pipeline stages, the approval gate and approver of each environment, and how a deployment is recorded are described when the pipeline is released.

## 5.4  Build once, promote the same artefact

| Part | Built | Promoted |
| --- | --- | --- |
| Backend | Recommended: one container image from backend/Dockerfile per tag, with GIT_COMMIT set so GET /api/version shows it; pushed to the registry (ECR, Azure Container Registry or the partner registry) | The same image digest is deployed to SIT, UAT, Pre-Prod and Production. Only environment variables differ |
| Front end | Today: npm run build of the same tag, with REACT_APP_BASE_URL compiled into the build, so each environment gets its own build of the same commit. Decision: one build per tag, with the environment values read at runtime (section 5.5) | Today: rebuilt per environment from the tag, the build log and file hashes kept with the release record. After the change: the same build promoted to every environment |
| Database | Migration files inside the image (backend/src/db/migrations) | Applied by the image itself on start (section 5.6) |
| Configuration | Configuration workbook (chapter 6) | Downloaded from the source environment, loaded into the target |

Today the EC2 script deploys a Git checkout (npm ci --omit=dev) rather than an image. Deploying a tag, not a branch head, gives the same result: every environment runs the same commit.

## 5.5  Front-end build and runtime configuration

Decision: one front-end build is promoted through all environments, and the API address and the other environment values are read at runtime instead of being compiled into the build.

Section to be completed with the release. How the runtime values are supplied in each environment, and how the build is checked before promotion, are described when the change is released.

## 5.6  Schema migrations

- Migrations are numbered SQL files in backend/src/db/migrations (98 files in v1.0.0, from 0001_core.sql to 0245_user_profile_details.sql).

- On every API start, backend/src/db/migrate.js takes a PostgreSQL advisory lock (other instances wait up to 10 minutes, MIGRATION_LOCK_TIMEOUT_MS), applies each file not yet recorded in schema_migrations in file-name order, each in its own transaction, and records it. A failing migration is rolled back and stops the start-up. /api/health answers 503 until the migrations and the seed have finished.

- By command: npm run migrate applies the pending migrations without starting the API (same lock). GET /api/health and GET /api/version report pendingMigrations.

- npm run db:reset (migrate.js --reset) drops the whole schema. It is for Dev only.

Rules (project convention and Recommended practice):

- A migration file is never edited after it has left Dev. The runner identifies a migration by its file name only: an edited file is not run again where it was already applied, so environments would differ silently. A correction is a new migration with a higher number.

- Forward only. Migrations add tables, columns and indexes; existing data is changed only by a reviewed migration or a data correction under change control. There are no down-migrations: the previous release runs on the newer schema.

- Every migration runs in Dev, then SIT (large broker) and UAT, in that order, before it reaches Production. For a major release it also runs in Pre-Prod, the rehearsal on a copy of production data.

- Before each Production deployment that contains a migration, take a manual database snapshot (the restore point), deploy one API instance first, wait for /api/health ready with pendingMigrations: 0, then roll the other instances.

- A new table must be classified in backend/scripts/lib/table-classification.js (transaction, system, or master and configuration). A test fails otherwise, and the transaction reset refuses to run on a database with an unclassified table.

## 5.7  Reference seeds

backend/src/db/seed.js runs after the migrations on every start, and by command with npm run seed. It is idempotent: rows are inserted by natural key or fixed id, existing rows and administrator edits are kept.

| Part | Content | When |
| --- | --- | --- |
| In code | Roles, permissions and role grants; the BrokerVerse administrator | Always |
| settings.json, jobs.json | Configuration keys of Master > Configuration; scheduled jobs | Always |
| seeds/*.sql | Reference data: geography, currencies, banks, insurers, products, covers, chart of accounts, product templates and motor tariff, report catalogue, security and direct-bill configuration | Always |
| seeds/sample/*.sql | Demo leads, clients, policies, claims, users | Only with SEED_SAMPLE_DATA on (default off with NODE_ENV=production) |

A new setting has its code fallback equal to the seeded value; npm run check:settings checks it. A database started with sample data by mistake is cleaned with npm run purge:sample before real business is entered.

## 5.8  Environment variables and secrets

Secrets are never in the repository, a ticket or a chat: they live in the secret store of each environment (AWS Secrets Manager or SSM Parameter Store, Azure Key Vault, HashiCorp Vault, or Railway variables). deploy/backend.env.example holds the names with placeholders only.

| Variable | Dev | SIT / UAT | Pre-Prod | Production |
| --- | --- | --- | --- | --- |
| NODE_ENV | development | production | production | production |
| DATABASE_URL | Local | Own database | Own database | Own database, TLS |
| JWT_SECRET, DATA_ENCRYPTION_KEY | Own values | Own values per environment | Own values | Own values, escrow copy under dual control |
| ADMIN_PASSWORD | Own | Own | Own | Own, changed at first sign-in |
| CORS_ORIGINS, PUBLIC_BASE_URL | Local addresses | Environment addresses | Environment addresses | Production addresses |
| SEED_SAMPLE_DATA | true | false | false | false |
| SCHEDULER_ENABLED | true | true | false until the rehearsal needs it | true |
| SMTP_URL | Test mailbox or none | Test mailbox | Test mailbox | Production mailbox |
| Payment gateway (<prefix>_SECRET_KEY and others) | None | Sandbox | Sandbox | Live |
| APP_ENVIRONMENT | Dev | SIT / UAT | Pre-Prod | Production |
| REACT_APP_BASE_URL (front-end build today; read at runtime after the change of section 5.5) | Local API | Environment API | Environment API | Production API |

With NODE_ENV=production the API refuses to start when JWT_SECRET or DATA_ENCRYPTION_KEY is missing, short or a placeholder, when the two are equal, when CORS_ORIGINS is *, or when PUBLIC_BASE_URL is localhost (deploy/REFERENCE.md).

## 5.9  Promotion steps

| Step | Entry criteria | Activities | Exit criteria | Sign-off |
| --- | --- | --- | --- | --- |
| System integration test in Dev (small and medium broker) | Pull requests merged with green CI; release candidate tagged | Deploy the tag to Dev; migrations and seed apply on start; smoke test (deploy/README.md section 4); uat-scenario.js on a fresh database; end-to-end plan; configuration built | Smoke test passed; uat-scenario.js all steps passed; no open P1 or P2 defect | iorta TechNXT delivery lead (SIT exit report) |
| Dev to SIT (large broker) | Pull requests merged with green CI; release candidate tagged | Deploy the tag; migrations and seed apply on start; smoke test; uat-scenario.js on a fresh database; end-to-end plan; configuration built | Smoke test passed; uat-scenario.js all steps passed; no open P1 or P2 defect from SIT | iorta TechNXT delivery lead (SIT exit report) |
| Dev or SIT to UAT | SIT exit report; release notes drafted; configuration workbook downloaded from Dev (small, medium) or SIT (large) | Deploy the same tag; promote the configuration (chapter 6); transaction reset; load the latest mock migration; key users run the UAT scripts | UAT scripts passed or accepted with a workaround; mock load reconciled | Broker process owners and sponsor: UAT Sign-off Certificate (Form 1) |
| UAT to Production (release and configuration) | UAT Sign-off; configuration frozen; CAB approval of the release | Deploy the same tag to Production; production secrets; promote the configuration from UAT; on-screen items; technical smoke test | Configuration comparison UAT against Production shows no change | iorta TechNXT DevOps lead; broker System Administrator |
| Pre-Prod rehearsal | Production configured; Production backup taken | Create Pre-Prod from the backup (section 4.3); cutover rehearsal: smoke test, reset, migration load, reconciliation, timings | Rehearsal inside the cutover window; reconciliation agrees | iorta TechNXT DevOps lead and migration lead; broker PM |
| Go-live in Production | Go/no-go checkpoint 1 passed; CAB approval; restore point taken | Final migration at cutover; reconciliation; go-live lock | Final reconciliation signed; go decision | Steering committee; Accounting Manager for the reconciliation; Go-live Acceptance Certificate (Form 2) |

After go-live, every release follows the same path to UAT. A major release is then rehearsed in a Pre-Prod created from a Production backup, which is removed after the release. A minor or patch release goes from UAT to Production with a manual snapshot of Production taken before deploying.

## 5.10  Change and release management

| Item | Rule (Production Support Approach and Standards) |
| --- | --- |
| Change types | Standard (pre-approved, done by the broker's System Administrator), Normal (release, tax rate, posting rule, numbering series, data correction script: CAB approval), Emergency (P1 fix or security patch: approved by the support manager and the broker's IT head, reviewed at the next CAB) |
| CAB | The broker's change owner and the iorta TechNXT support manager; approves Normal changes with impact, test evidence and rollback |
| Release types | Planned release (monthly, when there are fixes or changes); emergency release |
| Notice | Release notes to the broker's System Administrator and IT head at least 5 business days before deployment |
| Window | Maintenance window, default Saturday 20:00 to Sunday 06:00 PHT |
| Evidence | Regression of Production Support chapter 19: backend and front-end tests, uat-scenario.js on a fresh database, the UAT scripts of the changed area, the document and report sweep for print changes |
| After deploying | Smoke test; GET /api/version shows the expected commit and no pending migration |

The release notes use the Release Notes Template: release identification (tag, commit, previous release, window, downtime, CAB reference), changes by module, migrations included, actions an administrator must take by hand (including on-screen configuration items), known issues, and rollback.

## 5.11  Rollback

| What | How |
| --- | --- |
| Front end | Re-run the build of the previous tag, or restore the previous S3 object versions (bucket versioning on), then invalidate CloudFront |
| Backend | Redeploy the previous image or tag. Migrations only add, so the previous version runs on the newer schema |
| Database | Restore the pre-release snapshot only when data written by the new release must be undone; transactions entered since the snapshot are re-entered |
| Configuration | Load the configuration workbook downloaded before the change (Current data). The workbook updates and creates but never deletes: records created by the change are set inactive on their screen |
| Go-live data | Before go-live: restore the snapshot taken before the loads. After go-live: rollback window and procedure of the Data Migration and Cutover Plan |

# 6.  Moving configuration

## 6.1  The configuration workbook

The configuration kit of Master > Go-Live Data Load (GoLive_Configuration_Workbook.xlsx) carries what is needed to run new business: company, settings, location masters, branches, departments, hierarchy, designations, users, currencies, exchange rates, chart of accounts, banks, bank accounts, signatories, transaction codes, write-off reasons, insurers, lines of business, products, policy types, covers, vehicle brands, models, variants and vehicles, commission rate matrix, premium taxes and charges, LGU tax rates, authority limits and document numbering.

Each sheet is matched on a natural key (code, username, setting key, account code, series code). Loading the same or a corrected workbook again updates and never duplicates; rows equal to the stored data are reported as unchanged and not written.

## 6.2  Promotion procedure

- Source environment. Master > Go-Live Data Load > Download Template > Current data (GET /api/data-load/kits/configuration/template?prefill=true). The export is recorded in the audit trail. The file name carries the date; the Instructions sheet names the environment (APP_ENVIRONMENT).

- Review before loading. Edit the workbook for the target where needed:

  - Users: delete test personas (uat.*), trainers' test accounts and anyone who must not have access to the target. Passwords are never in the workbook: each new user gets a temporary password shown once to the administrator after the load.

  - Numbering: Next Number is exported from the source counters, which testing has advanced. For Production, set it to the last number used in the old system plus one. It cannot go backwards once loaded.

  - Settings: check golive.cutover_date and any environment-specific setting. Settings of other screens, settings under second-user approval, secret-like keys and golive.locked are never exported or loaded.

- Target environment. Master > Go-Live Data Load > upload the workbook (POST /api/data-load/batches, kit configuration). Validation is a dry run: all sheets run in load order inside one database transaction that is rolled back.

- Read the result. Per sheet: rows read, valid, with errors, and new, changed, unchanged or for approval.

- Fix. Download errors (GET /api/data-load/batches/:id/errors): only the rows in error, with an Errors column. Correct and upload again.

- Load (POST /api/data-load/batches/:id/load). For the configuration workbook, Load valid rows only is ticked by default. The load is one transaction, written to the audit trail, and the administrator is notified.

- Approve. Authority limits load as proposals: another administrator approves them on Master > Generals > User Management > Authority Matrix in the target.

- Complete the on-screen items of section 6.3 and record them on the promotion checklist.

## 6.3  Not in the workbook

These items are entered on their screen in each environment, or applied by a scripted procedure agreed with the DevOps lead. The list is the one on the Instructions sheet of the workbook.

| Item | Where | How it moves |
| --- | --- | --- |
| Roles and their permissions | Master > Generals > User Management > Role | Roles and permissions are seeded; changes repeated on screen |
| Segregation of duties rules, delegations, access reviews | Master > Generals > User Management | On screen |
| Approval of the loaded authority limits | Master > Generals > User Management > Authority Matrix | Second administrator approves in the target |
| Tax codes (VAT, withholding, BIR ATC) | Master > Finance > Taxation | On screen, confirmed by the broker's tax adviser |
| Account determination and posting rules | Master > Finance > Account Determination / Posting Rules / Configuration Approvals | On screen, proposed by one user and approved by another |
| Bank statement formats, bank transaction types, insurer statement formats, close checklist | Master > Finance | On screen |
| Product templates, rating, acceptance rules, motor tariff, documents | Product Configurator > Product Templates | On screen |
| Package bundles and insurer rate tables | Master > Packaged Products | On screen |
| Payment gateway credentials | Master > Finance > Payment Gateways; secret store | Secrets set per environment in the secret store; sandbox outside Production |
| Application name, logo, colours, display currency, language | Master > System Settings | On screen |
| Company logo and letterhead images | Master > Generals > Organization > Company | Uploaded on screen |
| Scheduled jobs | Master > Configuration > Schedules | On screen; switched on at go-live |
| Fiscal years and accounting periods | Accounts > Period End > Period Management | On screen; periods before the cutover date closed |
| Remittance masters, reinsurance treaties and reinsurers, incentive programmes | Master > Finance > Remittance Master; Reinsurance; Incentive | On screen |
| Referrers and agents with their commission accounts | Commission > Agents/Referrer Accounts | On screen |
| Petty cash funds | Accounts > Petty Cash > Initiate | On screen |
| Users' passwords | Master > Generals > User Management > User | Temporary password at load; named administrators with provision-users.js |
| Go-live lock (golive.locked) | Master > Configuration > Go-live | Switched on in Production only, after the migration is signed off |
| Environment variables and secrets | Secret store | Per environment, never copied |

Recommended: Keep a promotion checklist with one line per on-screen item, the value set in UAT and the tick in each target environment. It is the evidence for item 5 of the cutover checklist (configuration copied and compared item by item).

## 6.4  Configuration freeze

- Freeze for UAT: configuration is frozen at the end of the system integration test, in Dev (small and medium broker) or SIT (large broker) (Implementation Approach). Changes after that are logged and repeated in UAT.

- Freeze for cutover: from UAT sign-off (about T-21), no configuration change is made unless it is a Normal change approved by the CAB. An approved change is made in UAT first and promoted to Production with the workbook or the on-screen procedure (and repeated in Pre-Prod while it exists), never made directly in Production.

- After go-live: configuration changes in Production follow the change types of Production Support. Settings changes are recorded in the audit trail with the old and new value.

## 6.5  Comparing environments

The validation of a Current data workbook is also the comparison report between two environments:

- Download Current data from environment A.

- Upload it into environment B and stop after validation (do not load).

- The result per sheet gives new, changed and unchanged rows. Two environments with the same configuration show every row unchanged and nothing new or changed.

Run it UAT against Production after the configuration is promoted, and Production against Pre-Prod after the rehearsal, to show that no configuration was changed during the rehearsal. The validation result is kept in the load history (status validated or failed) as evidence. On-screen items are compared with the promotion checklist.

## 6.6  Comparison report

Decision: a comparison report between two environments is added, listing the differences row by row. Until it is released, the detail is found by comparing the two Current data workbooks in Excel.

Section to be completed with the release. What the report compares, how it is run and how its result is kept as evidence are described when the report is released.

# 7.  Client data flow

## 7.1  The two workbooks the broker fills

| Workbook | Content | Filled by | Used in |
| --- | --- | --- | --- |
| Configuration workbook (masters for new business) | Organisation, users, insurers, products, chart of accounts, banks, commission rates, taxes and charges, numbering, settings | Broker process owners with iorta TechNXT consultants, from the discovery decisions | Built in Dev (small, medium) or SIT (large), then promoted to UAT and Production; Pre-Prod receives it with the Production backup |
| Migration workbook (existing business) | Clients, in-force policies with legacy numbers, open premium receivables, open claims, GL opening balances | Broker data owners, from extracts of the old system; Accounting Manager for the financial sheets | Mock loads in UAT (small, medium) or SIT and UAT (large); rehearsal in Pre-Prod; final load in Production |

Blank workbooks come from Master > Go-Live Data Load (Blank template) or from docs/package/05_Delivery/Upload_Templates (generated by backend/scripts/build-upload-templates.js). Each has an Instructions sheet, a Lists sheet with the allowed values and one sheet per object in load order.

## 7.2  Mock loads and the final load

| Load | Environment | Data | Exit |
| --- | --- | --- | --- |
| Mock 1 | UAT (small, medium); SIT (large) | Full extract at a recent date | All sheets validate; failures listed and assigned for cleansing |
| Mock 2 | UAT (small, medium); SIT or UAT (large) | Fresh extract after cleansing | Failures below 1% of rows and explained; control figures reconcile |
| Mock 3 (medium and large) | UAT | Fresh extract at a month-end | All control figures reconcile; UAT on migrated data passes |
| Rehearsal | Pre-Prod (every size) | Fresh extract, with the cutover timetable | Done inside the cutover window; reconciliation signed |
| Final load | Production, at cutover | Extract at the close of the day before the cutover date | Reconciliation signed by the data owners and the Accounting Manager |

Each mock load follows the same cycle:

- Set golive.cutover_date for the mock (the first day after the extract date).

- Transaction reset of the environment (the earlier mock goes, masters and configuration stay).

- Upload the migration workbook; read the errors; fix in the old system or the workbook; upload again.

- Load (for the migration workbook Load valid rows only is not ticked by default: a clean, complete load is the goal).

- Download the reconciliation (GET /api/data-load/batches/:id/reconciliation) and compare it with the control figures of the old system.

- Record the timings and the sign-off in the reconciliation report of the Data Migration and Cutover Plan.

The reconciliation gives, per sheet, the rows and totals of the workbook (gross and net premium, sum insured, open balance, claim estimate, debits and credits) and the records and totals in BrokerVerse after the load, plus two checks: TB debits equal credits; the premiums receivable control account opening balance equals the total open balance of the open items.

## 7.3  Keeping migrated and new business apart and in step

| Topic | How BrokerVerse handles it |
| --- | --- |
| Flags | Migrated clients carry source = 'go-live-migration' and load_batch_id; policies doc.source = 'go-live-migration' and load_batch_id; open items are receivables with source = 'opening', go_live_date and load_batch_id; open claims details.source = 'go-live-migration' and load_batch_id |
| Legacy numbers | Migrated records keep the client code, policy number and claim number of the old system |
| No postings | A migrated policy creates no bill, booking journal or commission accrual; an open item posts no journal; an open claim sends no acknowledgement and posts nothing. The GL opening balances carry the money |
| Opening balances | The TB of the old system at the close of the day before the cutover date (cutover minus one day). Debits equal credits; the sheet loads all or nothing (the rows in error show their errors, the others are held, one message for the sheet); a row with no debit or credit is ignored; loading again replaces the earlier load. The fiscal year must have no journal posted before the cutover |
| Dates | Policy issue dates, claim loss and reported dates and client birth dates must be before the cutover date. Policies must be in force at cutover. Every new transaction is dated on or after the cutover date |
| Numbering | New business takes the next number of its Document Numbering series. The Numbering sheet sets the next number above the migrated range. Both workbooks refuse a collision: a series whose next number would issue a number a migrated record already has, or a legacy number in the range a series has still to issue |
| Renewals | Migrated in-force policies are ordinary active policies: the renewal queue picks them up as they near expiry. The renewal is a new BrokerVerse policy with its own number, bill and journals |
| Receipts | Open items age, are chased by the collection reminders and are paid with normal official receipts |
| Amounts due to insurers and referrers | In the opening balances (Due to Insurers, Commission Payable) and paid with payment vouchers (Accounts > Disbursement), not through the remittance run |
| Executive dashboard | Premium written and new business exclude migrated policies (doc.source = 'go-live-migration' or a load_batch_id); migrated policies count as policies in force |
| Month-end checks | The check "policies without accounting" ignores migrated policies, which were billed by the old system |
| Lists and reports | Policy lists filter on the source (GET /api/policies?source=go-live-migration). The Production Register shows a Source column (Migrated or BrokerVerse), counts migrated policies in its summary and groups by source with the Report Criteria Source, so business written in BrokerVerse is reported apart from the migrated book. The executive dashboard leaves migrated policies out of premium written and new business |
| Audit | load_batch_id ties every migrated record to its batch; the load history keeps who loaded what and when |

After the go-live lock, the migration workbook is refused. A record missed by the final load is entered on its screen as an exception, agreed with the Accounting Manager.

# 8.  Smoke test and go-live

## 8.1  Order of events

- Smoke test, preferably in Pre-Prod with the production configuration: a quotation to policy, bill, receipt, remittance, commission and journals, a claim and a renewal (deploy/README.md section 4 and docs/onboarding/SMOKE_TEST_AND_RESET.md).

- If the smoke test must run in Production (for example to prove the production e-mail, printer or payment gateway set-up): agree it in the cutover plan, take a database snapshot, use clearly named test data (a test branch such as TST, a test insurer and clients named ZZ TEST ...), and send nothing to real clients or insurers.

- Transaction reset after a smoke test in Production (or before each rehearsal in Pre-Prod):

  - stop the API instances; dry run CONFIRM_RESET=yes npm run reset:transactions;

  - execute with CONFIRM_RESET=yes RESET_ACTOR=<username> npm run reset:transactions -- --execute, adding --purge-files to delete the files of the test transactions;

  - masters, configuration, users and settings are kept; transaction document series restart at the next number the Numbering sheet set (else their start number); the TB is empty and every period is open again; the reset is recorded in the audit trail;

  - masters created only for the test (test branch, insurer, product) are set inactive or deleted on their screen.

- Final migration load of the migration workbook in Production at cutover, then the reconciliation and its sign-off.

- Go-live lock: a System Administrator switches on golive.locked (Master > Configuration > Go-live). From then on the transaction reset refuses to run (exit code 3) and the migration workbook is refused (upload, validation and load). The configuration workbook stays available for new masters. There is no option of the command that bypasses the lock; switching it off is audited and is never done on the live Production database.

- Hypercare starts on the go-live day.

## 8.2  Hypercare

| Item | Rule |
| --- | --- |
| Length | Default 2 weeks (small), 3 weeks (medium), 4 to 6 weeks (large); extended to cover the first month-end close |
| Rhythm | Daily check-in in the first week, then weekly |
| Rollback window | Until the end of the first business week; afterwards fix forward |
| Evidence during the window | Transactions entered in BrokerVerse listed daily (Receipts Register, Production Register, Journal) so a rollback could be carried out |
| Exit | Hypercare Exit and Handover Certificate when the criteria of Production Support chapter 16 are met: no open P1 or P2, first month-end close approved, configuration baseline recorded (a Current data configuration workbook of Production), environment sheet current |

# 9.  Cutover runbook

## 9.1  Conventions

T is the go-live day: the first day of transactions in BrokerVerse and the value of golive.cutover_date. The example assumes T is a Monday. Days are calendar days. Hours are indicative and are replaced with the times measured in the rehearsal. Checkpoints GNG-1 and GNG-2 are the go/no-go checkpoints 1 and 2 of the Data Migration and Cutover Plan.

## 9.2  T-30 to T-1

| When | Step | Owner | Evidence |
| --- | --- | --- | --- |
| T-30 | Production provisioned at production topology; secrets created in the secret store; backups running; one restore test done | iorta TechNXT DevOps lead | Environment sheet; restore test record |
| T-30 | Release candidate tag fixed; from now only P1 and P2 fixes enter it | iorta TechNXT release manager | Tag and release notes draft |
| T-30 | Go-live date confirmed; golive.cutover_date set in UAT for the last mock load | Broker PM, Accounting Manager | Steering committee minutes |
| T-28 | Last mock load in UAT on a fresh extract; reconciliation compared with the control figures | iorta TechNXT migration lead; broker data owners | Reconciliation workbook; sign-off |
| T-21 | UAT completed and signed: UAT Sign-off Certificate (Form 1) | Broker process owners and sponsor | Form 1 |
| T-21 | Configuration freeze declared; changes only by CAB | Broker PM; iorta TechNXT delivery lead | Freeze notice |
| T-20 | Release deployed to Production; technical smoke test of deploy/README.md section 4; administrator password changed; two-step verification on for the required roles | iorta TechNXT DevOps lead; broker System Administrator | Smoke test record |
| T-19 | Configuration promoted from UAT to Production: Users sheet without test personas, Numbering sheet set from the old system's last numbers plus one; authority limits approved; on-screen items entered; comparison UAT against Production shows no change | Broker System Administrator; iorta TechNXT consultant | Load history; validation result; promotion checklist |
| T-18 | Production backup taken; Pre-Prod created from it at production topology (section 4.3); own secrets, e-mail off, scheduler stopped; masked first if anyone without production access takes part | iorta TechNXT DevOps lead | Environment sheet; restore record (counts as a restore test) |
| T-17 to T-15 | Cutover rehearsal in Pre-Prod: smoke test, transaction reset, migration load of a fresh extract, reconciliation, go-live lock switched on and off again; each step timed | iorta TechNXT migration lead; broker Accounting Manager and key users | Rehearsal log with timings; reconciliation signed |
| T-14 | CAB approves the Production deployment and the cutover plan | Broker change owner; iorta TechNXT support manager | CAB record |
| T-14 | GNG-1: UAT signed, rehearsal reconciled, training on track, configuration ready in Production | Steering committee | Minutes |
| T-12 | Live payment gateway credentials and SMTP in the secret store; any configuration change found in the rehearsal made in UAT and promoted to Production | Broker System Administrator; iorta TechNXT DevOps lead | Promotion checklist; CAB record of any change |
| T-11 | Comparison Production against Pre-Prod shows no configuration change other than those approved; tax codes, premium taxes and LGU rates confirmed by the tax adviser | iorta TechNXT consultant; broker Accounting Manager | Validation result; adviser confirmation |
| T-10 | Smoke test in Production only if not done in Pre-Prod: snapshot, test data, then transaction reset and check that Leads, Clients, Policies and the TB are empty | iorta TechNXT DevOps lead; broker key users | Snapshot id; reset audit entry |
| T-7 | Users signed in once in Production; communication sent to users, insurers and banks; hypercare roster published | Broker PM; broker System Administrator | Sign-in history; communication log |
| T-5 | Masters reconciled in Production; document numbering checked on the screen preview; fiscal year and periods set, periods before T closed | Broker System Administrator; Accounting | Cutover checklist items 3 to 12 |
| T-3 (Friday) 17:00 | Old system frozen for new transactions; last receipts and vouchers of the day posted there | Broker PM | Freeze notice |
| T-3 (Friday) 18:00 to 22:00 | Day-end in the old system; extracts of clients, in-force policies, open receivables, open claims and TB; control figures produced and signed | Broker data owners; Accounting Manager | Signed control figures |
| T-2 (Saturday) 08:00 | Production snapshot before the loads; golive.cutover_date = T checked in Production | iorta TechNXT DevOps lead | Snapshot id |
| T-2 (Saturday) 09:00 | Migration workbook uploaded and validated; errors downloaded and fixed; validated again | iorta TechNXT migration lead; broker data owners | Load history |
| T-2 (Saturday) 13:00 | Migration workbook loaded | iorta TechNXT migration lead | Batch status loaded |
| T-2 (Saturday) 14:00 to 18:00 | Reconciliation downloaded and compared with the control figures; differences explained | Migration lead; Accounting Manager | Reconciliation workbook |
| T-1 (Sunday) 09:00 | Key user sample checks (20 policies per line, 20 open items, TB line by line) | Broker key users; Accounting Manager | Sample check sheet |
| T-1 (Sunday) 12:00 | Reconciliation report signed | Broker data owners; Accounting Manager | Signed report |
| T-1 (Sunday) 14:00 | GNG-2 (final): criteria of the Data Migration and Cutover Plan | Steering committee | Minutes; go decision |
| T-1 (Sunday) 15:00 | golive.locked switched on; snapshot of the go-live baseline | Broker System Administrator; iorta TechNXT DevOps lead | Audit entry; snapshot id |
| T-1 (Sunday) 16:00 | Scheduled jobs and "Send e-mails" switched on; old system set to read-only | Broker System Administrator; iorta TechNXT DevOps lead | Schedules screen; E-mail Outbox |

## 9.3  T to T+30

| When | Step | Owner | Evidence |
| --- | --- | --- | --- |
| T 07:30 | Health checks (/api/health ready, /api/version shows the tag); floor support in place | iorta TechNXT DevOps lead; hypercare team | Monitoring |
| T | First policies, receipts and bank imports watched; daily list of BrokerVerse transactions for the rollback window | Hypercare team; broker key users | Daily list |
| T 17:00 | Daily hypercare call: issues, decisions, rollback status | Broker PM; iorta TechNXT PM | Hypercare log |
| T+1 to T+4 | Daily check-ins; first remittance to insurers; first bank statement per account | Accounting; hypercare team | Remittance reference; bank reconciliation |
| T+4 (Friday) | Rollback window ends; decision recorded (continue, or roll back as in the Data Migration and Cutover Plan) | Steering committee | Minutes |
| T+7 | Go-live criteria checked; Go-live Acceptance Certificate (Form 2) signed | Broker sponsor; iorta TechNXT PM | Form 2 |
| T+7 to T+30 | Weekly hypercare meetings; known issues and workarounds recorded | iorta TechNXT PM; broker PM | Hypercare log; knowledge base |
| T+7 to T+30 | Pre-Prod kept to rehearse hypercare fixes on the go-live data | iorta TechNXT DevOps lead | Environment sheet |
| First month-end | Month-End Close prepared by Accounting and approved by the Accounting Manager; TB compared with the opening balances plus the month's activity | Accounting; Accounting Manager | Approved Month-End Close run |
| T+30 (or after the first close) | Hypercare exit: configuration baseline (Current data workbook of Production) and environment sheet handed over; Hypercare Exit and Handover Certificate | iorta TechNXT PM and support manager; broker IT head | Certificate |
| After hypercare exit | Pre-Prod removed: database, file store, backups and secrets deleted; hosting of Pre-Prod stops | iorta TechNXT DevOps lead | Environment sheet; deletion record |

# 10.  RACI and checklists

## 10.1  RACI for environment and release activities

R responsible, A accountable, C consulted, I informed. iorta TechNXT roles: DevOps lead (Ops), delivery team with the migration lead (Dlv), release and support manager (Sup). Broker roles: project manager (PM), System Administrator (SA), Accounting Manager (AM), key users and process owners (KU), IT head and change owner (IT).

| Activity | Ops | Dlv | Sup | PM | SA | AM | KU | IT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Provision and size environments | A, R | C | I | I | I |  |  | C |
| Secrets and secret store | A, R |  | I |  |  |  |  | C |
| Branching, CI, release tag | A, R | C | C |  |  |  |  | I |
| Deploy to Dev and SIT | A, R | C |  |  |  |  |  |  |
| System integration test (Dev or SIT) and SIT exit report | C | A, R | I | I |  |  |  |  |
| Promote configuration from Dev or SIT to UAT | C | A, R |  | I | C | C |  |  |
| UAT and UAT sign-off | C | R |  | A | R | R | R | I |
| Mock loads and reconciliation | C | A, R |  | I | C | R | R |  |
| Configuration freeze |  | R | C | A | C | C | I | I |
| CAB approval of the release | C | C | R | I |  |  |  | A |
| Deploy to Production | A, R | C | C | I | I |  |  | C |
| Create, mask and remove Pre-Prod | A, R | C | I | I | C |  |  | C |
| Promote configuration to Production; on-screen items | C | R |  | I | A, R | C |  |  |
| Smoke test and transaction reset | R | R |  | I | A | C | R | I |
| Final migration load | C | R |  | I | C | A | R |  |
| Go-live lock | C | C |  | I | A, R | C |  | I |
| Go/no-go checkpoints | C | R | C | A | C | C | C | C |
| Rollback decision | R | C | C | A | C | C | I | C |
| Release after go-live | R | C | A | I | C |  | C | C |

The steering committee holds the go/no-go and rollback decisions; the PM column shows the broker's accountable member of it.

## 10.2  Checklist: system integration test (Dev or SIT)

| # | Check |
| --- | --- |
| 1 | Pull requests merged; CI green on the last one; release candidate tagged |
| 2 | New tables classified in table-classification.js; upload templates regenerated if an importer changed |
| 3 | Release notes drafted, with migrations and manual actions listed |
| 4 | Deployed to Dev (small, medium) or SIT (large); /api/health ready with pendingMigrations: 0; /api/version shows the tag |
| 5 | Smoke test of deploy/README.md section 4 passed |
| 6 | uat-scenario.js on a fresh database: all steps passed |

## 10.3  Checklist: Dev or SIT to UAT

| # | Check |
| --- | --- |
| 1 | SIT exit report: end-to-end flows passed, no open P1 or P2 |
| 2 | Same tag deployed; migrations applied on start |
| 3 | Configuration workbook (Current data) of Dev or SIT reviewed (users, numbering) and loaded; authority limits approved |
| 4 | On-screen items entered and ticked on the promotion checklist |
| 5 | UAT access list approved; two-step verification on for the required roles; "Send e-mails" off or internal addresses only |
| 6 | Transaction reset; latest mock migration loaded and reconciled |

## 10.4  Checklist: UAT to Production and the Pre-Prod rehearsal

| # | Check |
| --- | --- |
| 1 | UAT Sign-off Certificate (Form 1) signed; configuration freeze declared; CAB approval |
| 2 | Production secrets set; SEED_SAMPLE_DATA=false; production start-up check passed |
| 3 | Same tag deployed to Production; technical smoke test passed; administrator password changed; two-step verification on |
| 4 | Configuration promoted with test personas removed and numbering set from the old system; on-screen items entered; comparison UAT against Production shows no change |
| 5 | Production backup taken; Pre-Prod restored from it at production topology, versions and non-secret settings (section 4.8); masked if people without production access take part |
| 6 | Scheduler and e-mail controlled for the rehearsal |
| 7 | Rehearsal done and timed; reconciliation signed; lock switched off again if a second rehearsal is needed |

## 10.5  Checklist: go-live in Production

| # | Check |
| --- | --- |
| 1 | GNG-1 passed; CAB approval of the cutover; release notes issued 5 business days ahead |
| 2 | Snapshot before the loads; golive.cutover_date checked |
| 3 | Comparison Production against Pre-Prod shows no unapproved configuration change |
| 4 | If a smoke test ran in Production: transaction reset done and checked |
| 5 | Final migration loaded and reconciled; GNG-2 passed; golive.locked on; schedules and e-mail on |
| 6 | Pre-Prod removal planned for hypercare exit and recorded in the environment sheet |

## 10.6  Checklist: release after go-live

| # | Check |
| --- | --- |
| 1 | Change request approved by the CAB, with test evidence and rollback |
| 2 | Release rehearsed on the same tag: major release in a Pre-Prod created from a Production backup (masked if needed) and removed afterwards; minor or patch release in UAT (and SIT for a large broker) |
| 3 | Snapshot taken in the maintenance window before deploying |
| 4 | Deployed one instance first; /api/version shows the tag; no pending migration |
| 5 | Smoke test passed; manual actions of the release notes done |
| 6 | Previous image and front-end build kept for rollback |

# 11.  Decisions and sections to complete

| # | Item | Decision of 04 October 2026 | Where |
| --- | --- | --- | --- |
| 1 | Environment set by broker size | Small and medium: Dev, UAT, Production, with integration in Dev. Large: Dev, SIT, UAT, Production, with SIT and UAT separate | Section 4.2 |
| 2 | Pre-Prod | Temporary for every size: created from a Production backup for the go-live rehearsal and each major release, then removed | Section 4.3 |
| 3 | Hosting cost of SIT and Pre-Prod | Priced per environment in the pricing workbook and the Rate Card; Pre-Prod per month of use | Section 4.5 |
| 4 | Front-end build | One build promoted through all environments, with runtime configuration | Section 5.5: to be completed with the release |
| 5 | Deployment jobs | Release pipeline with an approval gate per environment | Section 5.3: to be completed with the release |
| 6 | Comparison report between environments | Added | Section 6.6: to be completed with the release |
| 7 | Data masking | A masking tool is required | Section 4.9: to be completed with the release |

# 12.  Document Sign-Off

| Serial Number | Description | Owner | Status |
| --- | --- | --- | --- |
| 1 | Sections marked "Section to be completed with the release" (front-end build, release pipeline, comparison report, data masking) are completed when those deliveries are released | iorta TechNXT DevOps lead | Open |

| Sign Off Date | Signature | Approved By | Department & Project Role |
| --- | --- | --- | --- |