## Instructions
BrokerVerse Fit-Gap Register
One line per requirement found in the discovery workshops. Each line is classed, owned and decided. The register is signed by the process owners at the end of discovery (Small week 2, Medium week 3, Large week 5) and is then kept up to date until hypercare exit. Lines marked Example show how a line is filled in; delete them before the first workshop.
Item | Guidance
Requirement ID | FG-<area code>-<number>, for example FG-ACC-012. Never reuse an ID; a dropped line keeps its ID with status Withdrawn.
Area | The process area of the discovery workshops (list on the Lists sheet).
Requirement | What the broker needs, in its own words, with the volume or rule that matters.
Classification | Fit: delivered as it is. Configure: met by a setting or master data. Procedure: the broker changes how it works (workaround). Gap: needs a change to the product.
Solution | For Fit and Configure: the screen, setting or master (for example Master > Configuration > Billing, Collections & Credit). For Procedure: the new way of working, which goes into training. For Gap: the proposed change.
CR reference | For a Gap only: the change request number (Change Request Procedure and Form). A Gap is not in the go-live scope unless the steering committee approves it.
Effort | For Configure: hours of configuration. For Gap: the estimate in person-days from the change request.
Priority | Must have for go-live, Should have, Could have (after go-live).
Owner | One named person of the broker or of iorta TechNXT who closes the line.
Status | Open, Under analysis, Decided, Configured, Closed, Withdrawn.
Decision date | The date the class and solution were agreed (workshop or steering committee).
Decided by | The process owner, or the steering committee for a Gap.
Summary | The counts at the top of the Register sheet update themselves; report them in the weekly status report.
Product Gaps Closed | The gaps of the product found in the PH process fit assessment (IDs of the PH Fit and ASEAN Rollout Assessment catalogue), with the module that now closes each one, or In development. Use it in discovery: a requirement on this sheet is Fit or Configure, not Gap. The BR column points to the Business Requirements Document.

## Register
Lines by classification: | Fit |  | Configure |  | Procedure |  | Gap
Requirement ID | Area | Requirement | Classification | Solution | CR reference | Effort | Priority | Owner | Status | Decision date | Decided by | Remarks
FG-ACC-001 | Accounting and tax | Example. VAT-registered broker: output VAT on commission debit notes at 12%. | Fit | Delivered: direct bill debit notes add VAT at the tax code direct_bill.commission_vat_code (VAT12-OUT). |  |  | Must have | [Accounting Manager] | Decided |  | [name] | Example: delete
FG-BIL-002 | Billing and collection | Example. Official receipts e-mailed to the client with the PDF when recorded. | Configure | Switch on receipts.email_on_record (Master > Configuration > Billing, Collections & Credit > Receipts); SMTP mailbox set. |  | 1 hour | Should have | [System Administrator] | Decided |  | [name] | Example: delete
FG-REG-003 | Regulatory reporting | Example. BIR returns filed from the system straight into eFPS. | Gap | BrokerVerse prepares the returns, DAT files and filing records; direct filing to eFPS or eBIRForms needs a change request. | CR-[number] | [days] | Could have | [Accounting Manager] | Under analysis |  | Steering committee | Example: delete
FG-REM-004 | Remittance | Example. Remittances above PHP 1,000,000.00 approved by the Accounting Manager. | Configure | Authority Matrix, transaction type Remittance approval: Accounting PHP 1,000,000.00, Accounting Manager without limit (delivered default). |  | 0.5 hour | Must have | [Accounting Manager] | Decided |  | [name] | Example: delete
FG-POL-005 | Policy and servicing | Example. Brokers send the policy schedule by courier only. | Procedure | Print from Operations > Policy > Policy detail > Policy schedule; procedure added to the Operations training. |  |  | Should have | [Operations head] | Decided |  | [name] | Example: delete

## Product Gaps Closed
Product gaps closed in the release of 04 October 2026
54 of 54 gaps of the PH process fit assessment are closed; in development: 0. Module names in brackets are the backend modules.
Fit ID | Area | Requirement | Gap as assessed | Status | Closed by (screen and module) | BR reference
1.01 | Client onboarding, KYC and AML | Individual client record with Philippine address, mobile and TIN | Client created only at first policy; location masters not the full PSGC list | Closed | Operations > Clients > Onboard client; PSGC masters (Master > Location) | BR-01-001, BR-15-011
1.02 | Client onboarding, KYC and AML | Corporate client with authorised signatories | No signatory or board resolution record | Closed | Onboard client > Add signatory (aml) | BR-01-002
1.04 | Client onboarding, KYC and AML | Risk-based CDD rating and EDD | No risk rating, EDD or KYC refresh | Closed | Compliance > Client Due Diligence, EDD Reviews, KYC Refresh (aml) | BR-01-005, BR-01-006, BR-01-011
1.05 | Client onboarding, KYC and AML | Beneficial ownership of juridical clients | No beneficial owner capture | Closed | Onboard client > Add beneficial owner (aml) | BR-01-004
1.06 | Client onboarding, KYC and AML | Sanctions, PEP and negative list screening | No screening | Closed | Compliance > Screening Lists, Screening Hits; provider adapter (aml) | BR-01-007, BR-01-008
1.07 | Client onboarding, KYC and AML | Covered and suspicious transaction monitoring and AMLC reporting | No rules, alerts or AMLC file | Closed | Compliance > Transaction Alerts, AML Cases, AMLC Reports (aml) | BR-01-009, BR-01-010
2.04 | Prospecting and sales pipeline | Sales activities on prospects | No activity log | Closed | Operations > Sales & Marketing > Sales Activities: calls, meetings, e-mails and visits with follow-up tasks in My Work and an activity report (sales-activities) | BR-02-010
2.05 | Prospecting and sales pipeline | Lead assignment and team view | No assignment rules, queue or team view | Closed | Operations > Sales & Marketing > Lead Assignment (leads) | BR-02-004, BR-02-005
2.07 | Prospecting and sales pipeline | Dealer, bank and affinity channels | No channel master or dealer report | Closed | Master > Insurance > Distribution Channels; Dealer Production report (channels) | BR-02-006
2.08 | Prospecting and sales pipeline | Marketing campaigns to consenting clients | No campaign module | Closed | Operations > Sales & Marketing > Campaigns (campaigns) | BR-02-007
3.03 | Quotation and insurer comparison | Client comparison and recommendation report | In development at assessment | Closed | Operations > Sales & Marketing > Comparison Reports (comparison-reports) | BR-03-008
3.10 | Quotation and insurer comparison | Electronic signature on documents | In development at assessment | Closed | E-signatures mapped to documents (e-signatures); client acceptance by approval link | BR-15-010, BR-03-006
3.11 | Quotation and insurer comparison | Product Configurator rules drive the quotation | Only the motor tariff fed quotations | Closed | Governing template, acceptance rules, rating factors, market mapping, document templates (product-configurator); quote wizard covers and risk details from the governing template | BR-03-004, BR-03-009, BR-03-010
4.07 | RFQ, placement and reinsurance | Cover note while the policy is pending | No cover note | Closed | Operations > Cover Notes (cover-notes) | BR-04-007
4.08 | RFQ, placement and reinsurance | Placement only with IC-authorised insurers | No certificate of authority check | Closed | Compliance > Insurance Commission > Insurer Authority; check at RFQ, firm order and issue (ic-compliance) | BR-04-008
4.10 | RFQ, placement and reinsurance | Facultative reinsurance placement | No facultative slip workflow | Closed | Reinsurance > Facultative Placements (reinsurance) | BR-04-010
5.07 | Policy issuance and motor | CTPL COC authentication and LTO | No provider or LTO integration | Closed | Operations > CTPL Authentication; connectors CTPL_AUTH, LTO_FEED (integrations) | BR-05-005
5.08 | Policy issuance and motor | Brand-new vehicle programme with dealers and banks | No programme, dealer upload or bank letter | Closed | Operations > Sales & Marketing > Dealer Programmes (motor-programmes) | BR-05-008
5.09 | Policy issuance and motor | Fleet schedules | No per-vehicle fleet policy | Closed | Operations > Fleet Schedules (fleet) | BR-05-009
5.12 | Policy issuance and motor | Marine open cover | No open cover or declarations | Closed | Operations > Marine Open Covers (marine) | BR-05-010
6.04 | Endorsements and cancellations | Computed return premium on cancellation | Return premium typed by the user | Closed | Operations > Policy Cancellation (cancellations) | BR-06-004, BR-06-005
6.05 | Endorsements and cancellations | Short-period rate scale | No short-period table | Closed | Master > Insurance > Short-Period Rates (cancellations) | BR-06-004
7.07 | Renewals and retention | Renewal notices by SMS or messaging app | No SMS or Viber gateway | Closed | Message Templates; SMS and Viber connectors (integrations) | BR-07-002
8.09 | Billing, collection and receipts | Separate instalment invoices | No invoice per instalment | Closed | Accounts > Credit Control > Instalment Plans > Issue instalment invoices (credit-control) | BR-08-007
8.12 | Billing, collection and receipts | Post-dated cheque register | PDCs not tracked | Closed | Accounts > Post-Dated Cheques (pdc) | BR-08-008
9.05 | Remittance and direct bill | Bank payment files | No bank upload file | Closed | Accounts > Bank Payment Files; Master > Finance > Bank File Layouts (integrations) | BR-09-004
9.09 | Remittance and direct bill | Insurer system integration by API | No insurer API connector | Closed | Master > System > Insurer Integration (integrations) | BR-09-008
10.09 | Commission and incentives | Licence check before paying commission | Commission payable without a licence | Closed | Compliance > Insurance Commission > Licence Register; referrer licence check (ic-compliance) | BR-10-005
10.10 | Commission and incentives | Overriding, profit and contingent commission | Booked by journal voucher | Closed | Commission > Insurer Overrides (insurer-overrides) | BR-10-007
11.03 | Claims assistance | Claim document checklist and reminders | No checklist or reminders | Closed | Operations > Claim Documents; Master > Insurance > Claim Document Checklist (claim-documents) | BR-11-003
11.06 | Claims assistance | Claims paid through the broker from the Accounting menu | Panel only on the claim screens | Closed | Accounts > Claims Settlements (claim-payments) | BR-11-007
11.08 | Claims assistance | Motor repair estimates and letters of authority | No estimate or LOA workflow | Closed | Operations > Motor Claim Repairs; Master > Insurance > Repair Shops (motor-claims) | BR-11-006
12.10 | Accounting and period end | Supplier invoices, input VAT and fixed assets | No AP sub-ledger or asset register | Closed | Accounts > Payables; Accounts > Fixed Assets (payables, fixed-assets); Accounts > Fixed Assets > Disposals; Accounts > Payables > Supplier 2307 | BR-12-006, BR-12-007
13.04 | Taxes and BIR | Percentage tax 2551Q | No working paper | Closed | Accounts > Tax > Percentage Tax 2551Q (bir) | BR-13-003
13.07 | Taxes and BIR | 0619-E and 1601-EQ returns | Not laid out as the BIR forms | Closed | Accounts > Tax > Withholding Returns (bir) | BR-13-005
13.08 | Taxes and BIR | Annual information return 1604-E | No 1604-E alphalist | Closed | Accounts > Tax > Annual Alphalist 1604-E (bir) | BR-13-006
13.10 | Taxes and BIR | Invoices under the EOPT Act | Registered invoice not fixed in the product | Closed | Accounts > Tax > Sales Invoices (bir) | BR-13-008
13.11 | Taxes and BIR | CAS registration support | No books print set or CAS pack | Closed | Accounts > Tax > CAS Books and Documents (bir) | BR-13-009
13.12 | Taxes and BIR | Electronic invoicing (EIS) | No EIS connector | Closed | Accounts > Tax > E-Invoicing (EIS) (bir); live after BIR certification | BR-13-010
13.13 | Taxes and BIR | BIR DAT files | No DAT file | Closed | Accounts > Tax > BIR DAT Files (bir) | BR-13-007
14.02 | IC and Data Privacy compliance | Licence renewal tracking | No licence calendar | Closed | Compliance > Insurance Commission > Licence Register (ic-compliance) | BR-14-001
14.03 | IC and Data Privacy compliance | Fit and proper records | Kept outside the system | Closed | Compliance > Insurance Commission > Fit and Proper (ic-compliance) | BR-14-002
14.04 | IC and Data Privacy compliance | IC annual statement in the IC format | No IC-format report | Closed | Compliance > Insurance Commission > IC Annual Statement (ic-compliance) | BR-14-003
14.05 | IC and Data Privacy compliance | IC production report | IC layout not produced | Closed | Compliance > Insurance Commission > IC Production Report (ic-compliance) | BR-14-004
14.08 | IC and Data Privacy compliance | Complaints handling (RA 11765) | No complaints register | Closed | Compliance > Insurance Commission > Complaints (ic-compliance) | BR-14-005
14.11 | IC and Data Privacy compliance | Breach register and 72-hour tracker | No breach register | Closed | Compliance > Data Privacy (NPC) > Breach Register (privacy) | BR-14-009
14.12 | IC and Data Privacy compliance | Masking of personal data by role | Identifiers shown in full | Closed | view:pii permission, privacy.masking_enabled; mask:data tool for copies | BR-14-010, BR-14-012
14.13 | IC and Data Privacy compliance | Encryption of personal identifiers | No field-level encryption | Closed | Field encryption of TIN, ID and bank numbers (PII_ENCRYPTION_KEY) | BR-14-011
15.03 | Reporting, administration and go-live | Ad hoc reporting and BI extract | No report designer or extract | Closed | Reports > Report Builder; BI extract (report-builder) | BR-15-003
15.07 | Reporting, administration and go-live | Audit trail screen | Audit log without a search screen | Closed | Master > System > Audit Trail (audit) | BR-15-007
15.08 | Reporting, administration and go-live | Menu by role and task | Menu grouped by legacy screens | Closed | Enterprise side menu with Master sections; Help panel (F1) | BR-15-008
15.09 | Reporting, administration and go-live | My Work inbox | In development at assessment | Closed | Operations > My Work (my-work) | BR-02-009
15.11 | Reporting, administration and go-live | Branding, letterhead and e-signature | In development at assessment | Closed | Master > System Settings > Theme and Branding; e-signatures (branding, e-signatures) | BR-15-010
15.12 | Reporting, administration and go-live | Philippine reference masters | In development at assessment | Closed | PSGC geography, banks, ID types, salutations, holidays, IC insurer list (migration 0250, seeds 12 and 69) | BR-15-011

## Lists
Area | Classification | Priority | Status
Organisation and users | Fit | Must have | Open
Sales and quotation | Configure | Should have | Under analysis
Placement | Procedure | Could have | Decided
Policy and servicing | Gap |  | Configured
Claims |  |  | Closed
Renewals |  |  | Withdrawn
Billing and collection
Remittance
Commission and incentives
Accounting and tax
Period end
Bank and insurer reconciliation
Reinsurance
Reports and dashboards
Regulatory reporting
Data privacy
Integrations
Data migration
Security and access
Hosting and operations