Prepared by – iorta TechNXT Corp.

Version - 1.1

Date - 04 October 2026

OOTB Strategy and Playbook

iNXT BrokerVerse

TABLE OF CONTENTS

1. Document Control	4

2. Acronyms	4

3. Purpose and how to use this playbook	6

3.1 Purpose	6

3.2 Sources and assumptions	6

4. What OOTB means	7

4.1 Definition	7

4.2 The product at a glance	7

4.3 The product boundary	8

4.4 Standard integrations in OOTB	9

5. Target market and segments	10

5.1 The Philippine broker market	10

5.2 Segments	10

5.3 Buyers and triggers	10

5.4 Qualification	11

5.5 Positioning	11

6. The offer	12

6.1 Modules	12

6.2 Commercial models	12

6.3 Implementation fee	13

6.4 Hosting options	13

6.5 Packages	13

6.6 Optional services	13

7. Sales process	15

7.1 Stages, collateral and exit criteria	15

7.2 Rules for the sales team	16

7.3 Approval gates	16

7.4 Discount limits	16

7.5 Legal review triggers	17

8. Delivery model	18

8.1 Phases	18

8.2 Timelines by size	18

8.3 Team size by implementation	18

8.4 Data migration	19

8.5 Training	19

8.6 Acceptance	19

8.7 Hypercare	20

8.8 Delivery governance	20

9. Support model	21

9.1 Levels	21

9.2 Service levels	21

9.3 Release and patch policy	21

9.4 AMC and the subscription	22

9.5 Service management	22

10. Product lifecycle	23

10.1 Versioning	23

10.2 From change request to product feature	23

10.3 Roadmap themes	23

10.4 Development standards	24

11. Team and roles at iorta TechNXT	25

11.1 Roles by stage	25

11.2 Capacity	26

12. KPIs by function	27

12.1 Sales	27

12.2 Delivery	27

12.3 Support	27

12.4 Product and development	28

12.5 Finance and management	28

13. Governance	29

13.1 Internal forums	29

13.2 Client-facing forums	29

13.3 Document control	29

14. 30/60/90-day launch plan	30

14.1 Days 1 to 30: ready to sell	30

14.2 Days 31 to 60: first conversations	30

14.3 Days 61 to 90: first commitments	30

15. Risks	32

16. Decisions for the owner	33

17. Document Sign-Off	34

# 1.  Document Control

| Date | Version | Author & Business Unit Info | Reviewed By & Business Unit Info | Approved By & Business Unit Info | Change History |
| --- | --- | --- | --- | --- | --- |
| 04 October 2026 | 1.1 | iorta TechNXT Corp. | To be completed | To be completed | Product at a glance, boundary, standard integrations, modules, optional services and roadmap updated for AML/CFT, the IC and NPC registers, BIR forms and EOPT, the integration framework, dealer programmes, branding, My Work and the Report Builder; new decisions on pricing of the new modules |

# 2.  Acronyms

| Acronym / Symbol | Definition / Meaning |
| --- | --- |
| AM | Account manager |
| AMLC | Anti-Money Laundering Council |
| CTPL | Compulsory third party liability |
| EIS | Electronic Invoicing System |
| EOPT | Ease of Paying Taxes Act |
| LTO | Land Transportation Office |
| AMC | Annual Maintenance Contract |
| AML | Anti-money laundering |
| API | Application programming interface |
| ARR | Annual recurring revenue |
| BIR | Bureau of Internal Revenue |
| CAB | Change advisory board |
| CEO | Chief executive officer |
| CR | Change request |
| DPA | Data Processing Agreement |
| Dev | Development environment |
| DPO | Data protection officer |
| DSO | Days sales outstanding |
| eFPS | Electronic Filing and Payment System |
| IC | Insurance Commission |
| KPI | Key performance indicator |
| L1/L2/L3 | Support levels 1, 2 and 3 |
| LOB | Line of business |
| LoA | Letter of Award |
| MSA | Master Services Agreement |
| NDA | Non-disclosure agreement |
| NPC | National Privacy Commission |
| OOTB | Out of the box |
| PHP | Philippine peso |
| PM | Project manager |
| RACI | Responsible, Accountable, Consulted, Informed |
| RCA | Root-cause analysis |
| SaaS | Software as a service |
| SH | Sales head |
| Pre-Prod | Pre-production environment |
| SIT | System integration test |
| SLA | Service level agreement |
| SMS | Short message service |
| SOW | Statement of work |
| UAT | User acceptance testing |
| USD | United States dollar |
| VAT | Value-added tax |

# 3.  Purpose and how to use this playbook

## 3.1  Purpose

This playbook sets out how iorta TechNXT Corp. (iorta TechNXT) takes iNXT BrokerVerse OOTB to market in the Philippines and runs it as a product: what OOTB means, who we sell to, what we offer, how we sell, deliver and support it, how the product evolves, who does what, how we measure it and how we launch it in the next 90 days.

It is one document for five functions:

| Function | Read first |
| --- | --- |
| Management | Chapters on OOTB, market, offer, governance, KPIs, launch plan and decisions |
| Sales and presales | Offer, sales process, approval gates |
| Delivery | Delivery model, team and roles |
| Development and product | Product boundary, product lifecycle |
| Support | Support model, handover from delivery |

## 3.2  Sources and assumptions

The facts in this playbook come from the iorta TechNXT documentation package of 04 October 2026: the price book and Rate Card, the Commercial Proposal Note, the Negotiation Playbook, the contract pack, the Implementation Approach and Plan, the Data Migration and Cutover Plan, the Training Plan, the Production Support Approach and Standards, the Architecture, Infrastructure, Security and Privacy document, the Product Functionality document, the Test Summary Report and the sales collateral.

Where this playbook makes a recommendation or an assumption that is not stated in those documents, it is marked Assumption or Proposed. Targets marked Proposed are starting values for management to confirm.

All amounts are in PHP and exclude 12% VAT. USD figures are for reference only, at PHP 62.75 per USD (25 September 2026).

# 4.  What OOTB means

## 4.1  Definition

iNXT BrokerVerse OOTB is the out-of-the-box version of the iNXT BrokerVerse insurance broking platform: one product line, the same code for every client, fitted to each broker by configuration and master data, not by code changes.

Five rules follow from that definition:

- Configure, do not customise. A requirement is met by configuration, master data or a change in the broker's procedure. What cannot be met that way is a gap, recorded in the fit-gap register and handled as a change request.

- One code line. There is no client-specific branch of the product. A change request is either merged into the product line, and then supported under the AMC or the subscription, or it is supported at day rates.

- Go-live first, changes after. Approved change requests may be scheduled after go-live so that the OOTB go-live date holds.

- Data drives the timeline. Most implementation effort sits with the broker's data. Requests for data go out in week 1.

- Priced as delivered. The price list prices the product as delivered. Changes are priced at published day rates.

## 4.2  The product at a glance

| Item | iNXT BrokerVerse OOTB, current build |
| --- | --- |
| Scope | Full broking cycle and broker accounting: prospects to renewals, billing to month-end close; BIR forms and returns with DAT files, EOPT sales invoices and the CAS books pack; AML/CFT programme; IC and NPC compliance registers; distribution (lead assignment, channels, dealer programmes, fleets, marine open covers, facultative placements, campaigns); integrations; My Work; Report Builder and BI extract; broker branding and e-signatures |
| Roles | 8: System Administrator, Sales & Marketing, Processing Team, Operations, Claims, Accounting, Accounting Manager, Compliance Officer (AML/CFT) |
| Philippine masters | Regions, provinces, cities and municipalities, barangays (PSGC 2Q 2026), ZIP codes, banks, ID types, salutations, holidays, the IC list of insurers |
| Reports | Catalogue reports in Excel, CSV and PDF on the broker's letterhead, dashboards, the Report Builder over curated datasets, a nightly BI extract |
| APIs | 1,291 documented API operations (OpenAPI file of the current build) |
| Scheduled jobs | 32 jobs in Asia/Manila time, 35 with the IC and NPC compliance package |
| Connectors | SMS (Semaphore-style, Globe Labs-style, generic), Viber business messages, CTPL authentication and COC series, LTO feed, insurer API with a mapping per insurer, bank payment files (starter layouts for BDO, BPI, Metrobank, Landbank, UnionBank and a generic CSV), BIR EIS, AML screening provider; all delivered in test mode or switched off |
| Release test | Release 1.0: 497 test cases (486 passed, 2 failed, 3 blocked, 6 not run, after the re-test of 03 October 2026); 717 automated business rule tests; a UAT cycle of 371 business steps. The Test Strategy, Test Plan and Test Summary Report give the figures of the current build |
| Technology | React 18 web application, Node.js 22 API, PostgreSQL 16 database |
| Documentation | User manual with a Help panel per screen (F1), role decks, reports book, data dictionary, technical reference, BRD, process flows, test strategy and plan, traceability matrix, dependency map, schedules and support runbooks |
| In progress | Sales activity log, quote wizard covers and risk fields from the Product Configurator, supplier BIR Form 2307 and fixed asset disposal, being completed for the next release |

## 4.3  The product boundary

| Layer | What it contains | Who pays | Who supports |
| --- | --- | --- | --- |
| Product | All delivered modules, screens, workflows, reports, printed documents, upload templates and the standard integrations and connectors | Licence fee or subscription | iorta TechNXT, under the AMC or the subscription |
| Configuration | Company, users and roles, insurers, products and tariff, commission, taxes, chart of accounts, posting rules, number series, approvals, schedules, e-mail and SMS texts, AML risk factors and rules, branding | Implementation fee | The broker's System Administrator, with L2 support |
| Activation of regulatory modules and connector go-live | Workshops and set-up of the AML/CFT toolkit, the IC compliance registers and the BIR pack; going live with each SMS gateway, CTPL provider, insurer, bank or the BIR EIS | Optional service lines of the Rate Card (to confirm by management) | iorta TechNXT; the partner certifies its own side |
| Change requests merged into the product line | Changes that iorta TechNXT decides to add to the product for all clients | Day rates, once, by the client who asked | iorta TechNXT, under the AMC or the subscription |
| Change requests not merged | Client-specific changes | Day rates | iorta TechNXT, at day rates after the 30-day warranty |
| Services | Implementation, data migration, training, hosting, new integrations beyond the delivered connectors, extra environments, exit assistance | Rate Annex | iorta TechNXT |
| Outside the offer | Regulatory filings (BIR, IC, AMLC, NPC), tax and legal advice, partner certifications, screening list subscriptions, hardware and networks, data cleansing | Not applicable | The broker and its partners |

## 4.4  Standard integrations in OOTB

- Outgoing e-mail through the broker's SMTP mailbox.

- Bank statement files: formats for BDO, BPI and Metrobank and a generic layout; a new format is added in Master > Finance > Bank Statement Formats without code.

- Bank payment files (bulk credit, InstaPay, PESONet) with the bank's status file read back; starter layouts for BDO, BPI, Metrobank, Landbank and UnionBank and a generic CSV, each validated with the bank during onboarding.

- Insurer statement files in CSV or Excel, matched in Insurer Reconciliation with a column mapping per insurer.

- The integration framework: one outbox and inbox with retries, an attempt log and signed inbound messages, with the connectors SMS, Viber, CTPL authentication, LTO feed and insurer API.

- The BIR EIS connector for e-invoices (switched off until the broker is enrolled) and the BIR DAT files of the alphalists.

- The AML screening provider connector, besides the screening lists the broker uploads.

- PayMongo and Dragonpay payment links.

Every connector is delivered in test mode or switched off. Going live needs the partner's contract, endpoint and credentials and the partner's acceptance of the interface: iorta TechNXT configures and tests its side, the partner certifies its own. Everything else (core banking, accounting packages, eFPS or eBIRForms e-filing, IC or AMLC portals, other payment gateways, a new kind of connector) is a change request or an optional integration.

# 5.  Target market and segments

## 5.1  The Philippine broker market

The market is small and concentrated. The IC key data for 2024 (preliminary) shows about 67 licensed insurance brokers. A broker needs a minimum paid-up capital of PHP 20,000,000.00, or PHP 50,000,000.00 for an insurance and reinsurance broker. Three brokers earn more than PHP 2 billion each in commission, a handful earn between PHP 250 million and PHP 800 million, and most earn under PHP 100 million.

Non-life gross premiums written reached PHP 149.11 billion in 2025, spread across many insurers. A Philippine broker places with many insurers, so insurer set-up, remittance and reconciliation by insurer are core needs at every size.

## 5.2  Segments

| Segment | Users (tier) | Typical profile (estimate) | IC 2024 position | Lead offer |
| --- | --- | --- | --- | --- |
| Owner-managed broker | Small: 1 to 25 | 10 to 40 staff, one office or a few branches | Rank 30 and below | Subscription: Essentials or Standard |
| Established mid-size broker | Medium: 26 to 100 | 40 to 150 staff, several branches | Rank 10 to 30 | Subscription: Standard; perpetual for a long horizon |
| National or multinational broker | Large: 101 to 300 | 150 to 400 staff, national or multinational | Rank 4 to 10 | Perpetual: Ownership or Ownership Plus |
| Bank-affiliated or global broker | Enterprise: above 300 | Over 400 staff | Top 3 | Perpetual: Ownership Plus |

Assumption: the first wins are most likely in the Small and Medium segments, where most brokers sit, buying cycles are shorter and local tax and BIR features matter most. Large and Enterprise brokers that are part of a global group may already run a group system; with them, lead with the Philippine accounting, BIR working papers and remittance features.

## 5.3  Buyers and triggers

| Buyer | What matters to them |
| --- | --- |
| Owner, president or CEO | Cost against commission income, control, audit findings, growth without hiring |
| Finance head or Accounting Manager | Official receipts, remittance to insurers, bank and insurer reconciliation, month-end close, BIR working papers |
| Operations head | Quotation to policy turnaround, renewals, endorsements, claims follow-up |
| IT head | Hosting, data location, security, support, exit |
| Compliance officer and DPO | AML/CFT programme and AMLC reports, IC licences and complaints, Data Privacy Act and breach notification, audit trail, maker-checker, segregation of duties |
| Head of a captive agency or dealer channel | Dealer programmes, bank endorsement letters, fleets, lead assignment |

Typical triggers (assumption): the end of a contract for the current system, a new BIR requirement (EOPT invoicing, e-invoicing), an AMLC or IC examination finding, a complaints-handling or breach-notification obligation, growth that the spreadsheets cannot carry, a new dealer or bank partnership, or a new licence.

## 5.4  Qualification

A prospect is qualified when the account manager can answer yes to each of these:

- It holds or is applying for an IC certificate of authority as a non-life broker.

- It has a named pain in broking, accounting or BIR reporting that the OOTB product addresses.

- It accepts the OOTB principle: configuration first, changes as change requests.

- A decision maker and a budget range are known; the budget fits the tier price at list.

- A target date exists, or one can be set from a business event.

## 5.5  Positioning

iNXT BrokerVerse OOTB at USD 32 to 51 per user per month sits at about 29% of the median price of the global broker systems found (USD 175), which are not localised for Philippine taxes, BIR returns, EOPT invoicing, AMLC reporting or the IC registers, and at about the per-user price of a generic CRM at its top edition, while including placement, remittance, accounting, reconciliation and BIR working papers. The message is a localised, full broking and accounting platform priced for a market where most brokers earn under PHP 100 million in commission.

# 6.  The offer

## 6.1  Modules

All delivered modules are included in every package, with no module priced as an add-on: dashboards and My Work; prospects and clients with client onboarding; lead assignment, distribution channels, dealer programmes, fleets, marine open covers, comparison reports and campaigns; Quick Quote and Compare Insurers; motor quotation and customer approval; request for quotation and placement; cover notes; policy issuance and servicing; endorsements and computed cancellations; claims with the document checklist, motor repairs and settlements; renewals; billing, instalment invoices, post-dated cheques, payments and official receipts; collections and credit control; disbursement, accounts payable, bank payment files and petty cash; remittance to insurers and direct bill; commission, referrers and overriding commission from insurers; incentives; general ledger and journals; fixed assets; period end; bank reconciliation; insurer reconciliation; BIR forms and returns (2307, 0619-E, 1601-EQ, 1604-E, 2551Q, VAT Summary, SAWT, QAP, SLSP, DAT files), EOPT sales invoices, the EIS connector and the CAS books pack; the AML/CFT toolkit; the IC and NPC compliance registers; reinsurance and facultative placements; Product Configurator; reports, Report Builder and BI extract; notifications, e-mail, SMS and the integration connectors; data privacy; branding and e-signatures; administration, security, the go-live data workbench and configuration.

The effort to activate the regulatory modules and to take each connector live with its partner is not in the base implementation fee, which was sized before these modules. It is priced as optional service lines (Rate Card, to confirm by management): activation of the AML/CFT toolkit, of the IC compliance registers and of the BIR pack, go-live of each connector, set-up of each dealer programme and of a client brand pack.

## 6.2  Commercial models

| Item | Perpetual licence with AMC | Subscription |
| --- | --- | --- |
| Software price | Per named user, one-time, graduated slabs: PHP 90,000.00, 78,000.00, 66,000.00, 54,000.00 | Per named user per month, graduated slabs: PHP 3,200.00, 2,800.00, 2,400.00, 2,000.00 |
| Minimum | None | Minimum billable users: 10, 26, 101, 301; minimum term 12 months |
| Implementation | Implementation fee by size and lines of business | Onboarding fee equal to the implementation fee |
| Support | 12-month warranty, then AMC at 22% of the licence fee a year, plus 5% a year | Included in the Monthly Fee, plus 5% a year |
| Payment | Licence 100% on go-live; implementation 40/40/20 | Monthly in advance from go-live; onboarding 40/40/20 |
| Best for | A horizon of four years or more; capital budget | Lower Year 1 cash; no capital approval |
| Optional escrow | Yes | No |

Subscription costs less in cash for the first three years; for the reference user counts its cumulative cost passes the perpetual model in Year 4. Perpetual costs 13% to 18% less over five years.

## 6.3  Implementation fee

| Size | Base man-days | Lines of business included | Training days included | Fee (PHP) | Duration to hypercare exit |
| --- | --- | --- | --- | --- | --- |
| Small | 70 | 5 | 4 | 1,130,000.00 | 8 weeks |
| Medium | 130 | 8 | 6 | 2,090,000.00 | 12 weeks |
| Large | 230 | 12 | 10 | 3,700,000.00 | 16 to 20 weeks |
| Enterprise | 360 | 16 | 15 | 5,800,000.00 | 20 weeks or more |

Each line of business above the included number adds 6 man-days at the blended rate of PHP 16,100.00.

## 6.4  Hosting options

| Option | Data location | Small | Medium | Large | Enterprise |
| --- | --- | --- | --- | --- | --- |
| Hosted by the broker (cloud account or data centre) | Broker's choice | No fee | No fee | No fee | No fee |
| iorta TechNXT on AWS (ap-southeast-1) | Singapore | 43,000.00 | 69,000.00 | 143,000.00 | 256,000.00 |
| iorta TechNXT on Azure (Southeast Asia) | Singapore | 46,000.00 | 73,000.00 | 150,000.00 | 269,000.00 |
| iorta TechNXT with a local partner | Philippines | 42,000.00 | 67,000.00 | 135,000.00 | 242,000.00 |
| Pre-Prod on AWS, per month of use | Singapore | 21,000.00 | 47,000.00 | 86,000.00 | 169,000.00 |

Per month, the standing environment set of the size: Dev, UAT and Production for Small and Medium brokers (integration in Dev, then UAT, then Production); Dev, SIT, UAT and Production with high availability for Large and Enterprise brokers. Pre-Prod is temporary for every size: created from a production backup (masked when used by people without production access) for the go-live rehearsal and each major release, then removed, and billed per month of use. Hosting fees do not increase yearly (pass-through clause). Hosting in Singapore is a transfer of personal data outside the Philippines that the broker documents under the Data Privacy Act. Hosting is always quoted separately so the software price stays comparable.

## 6.5  Packages

| Package | Model | Hosting | Support | Small, Year 1 (PHP) | Medium, Year 1 (PHP) |
| --- | --- | --- | --- | --- | --- |
| Essentials | Subscription | By the broker | Standard | 1,706,000.00 | 4,226,000.00 |
| Standard | Subscription | AWS Singapore | Standard | 2,264,000.00 | 5,148,000.00 |
| Ownership | Perpetual with AMC | AWS Singapore | Standard | 3,038,000.00 | 7,992,000.00 |
| Ownership Plus | Perpetual with AMC | Local partner, Philippines | Standard and 24x7 Severity 1 | 3,564,000.00 | 8,744,000.00 |

Year 1 at list for the reference users (Small 15 users and 5 lines of business; Medium 60 users and 8 lines), including 2 months of Pre-Prod for hosted packages. The Rate Card gives all four sizes and the 5-year totals.

## 6.6  Optional services

Additional environments (PHP 100,000.00 set-up, PHP 11,000.00 a month hosted), training beyond the included days (PHP 30,000.00 per trainer day), data migration beyond the standard templates (PHP 240,000.00 per legacy source), new integrations beyond the delivered connectors (standard PHP 320,000.00, complex PHP 720,000.00), the go-live of a delivered connector with one partner (PHP 80,000.00 per connector, to confirm by management), activation of the AML/CFT toolkit, the IC compliance registers or the BIR pack (PHP 130,000.00, PHP 100,000.00 and PHP 130,000.00, to confirm by management), set-up of a dealer programme (PHP 50,000.00 per programme, to confirm by management) and of a client brand pack (PHP 30,000.00, to confirm by management), additional line of business after go-live (PHP 100,000.00), new report or document template (typical PHP 60,000.00), on-site days (PHP 20,000.00), 24x7 Severity 1 support (Small PHP 240,000.00 to Enterprise PHP 1,500,000.00 a year), change requests at day rates (business analyst PHP 18,000.00, developer PHP 16,000.00, QA engineer PHP 12,000.00, project manager PHP 22,000.00, blended PHP 16,100.00). The Service Catalogue and Rate Annex holds the full list.

# 7.  Sales process

## 7.1  Stages, collateral and exit criteria

| # | Stage | Collateral to use | Exit criterion | Owner |
| --- | --- | --- | --- | --- |
| 1 | Target and first contact | One-page and two-page brochures; prospect e-mails (cold introduction small or large broker, compliance-led introduction, follow-ups 1 and 2, LinkedIn note, event invitation) | Meeting agreed | Account manager |
| 2 | First meeting and qualification | Client Presentation; pre-meeting agenda and thank-you e-mails; discovery questions of the Demo Script; FAQ and Objection Handling | Qualified against the five criteria | Account manager |
| 3 | Demonstration | Demo Script (60 or 30 minutes, with the optional segments the prospect asks for) on the demo environment with the UAT data set; demo invitation and follow-up e-mails; Mutual NDA if own data is shown | Workshop agreed | Account manager and solution consultant |
| 4 | Discovery workshop and sizing | Product Functionality document; Regulatory Compliance Matrix; Implementation Approach and Plan; ROI Calculator when finance asks; Architecture document for IT | Size, users, lines of business, hosting and model agreed | Solution consultant |
| 5 | Proposal | Rate Card; Quick Quote at list with the Validity and Terms sheet; proposal cover e-mail within 5 working days of the workshop; ROI result | Proposal sent | Account manager |
| 6 | Negotiation | Negotiation Playbook (internal only); negotiation follow-up e-mail; FAQ and Objection Handling | Price and terms agreed within the approval limits | Account manager, sales head |
| 7 | Award | Letter of Award or Proposal Acceptance form | Award received | Account manager |
| 8 | Contract | Contract Pack Index and Cover Letter; MSA, Order Form and schedules for the model; contract dispatch e-mail | Contract set signed | Account manager, legal counsel |
| 9 | Hand-off to delivery | Welcome e-mail within 2 working days of signing; signed deal file; kick-off date | Kick-off held | Account manager, head of delivery |
| 10 | Reference and expansion | Referral request e-mail after go-live and a stable first month-end close | Reference agreed; added users or options | Account manager |

The e-mail sequence and timings are in the Prospect E-mail Templates: follow-up 1 on day 4 to 5, follow-up 2 on day 10 to 12 then a 60-day pause, re-engagement 60 to 90 days after a prospect goes quiet.

## 7.2  Rules for the sales team

- Start at list price. Show the list price in every presentation and the first quotation. Send the quotation within 2 business days of the meeting.

- Trade, do not give. Every concession is exchanged for term, cash timing, a reference, scope or a signing date. Move scope before price.

- Protect the recurring line. The AMC rate (22%) and the yearly escalation (5%) are not discounted.

- Disclose the known limits of the OOTB release when the topic comes up (FAQ, Known limits of the OOTB version).

- Never demonstrate on a production system or with a prospect's real client data.

- The client copy of the prices is the Rate Card. The price book, the floor prices and the Negotiation Playbook are never sent.

## 7.3  Approval gates

| Gate | When | Approver | Evidence |
| --- | --- | --- | --- |
| G1: qualification | Before a demonstration | Account manager; sales head for Large and Enterprise (Proposed) | Qualification criteria met |
| G2: pricing | Before the quotation with any discount leaves iorta TechNXT | By the highest discount on any component (table below) | Quick Quote, reason, levers, written approval in the deal file |
| G3: delivery capacity | Before the proposal states a go-live date (Proposed) | Head of delivery | Size, dates and team confirmed |
| G4: legal review | Before the contract set is sent, when a legal trigger applies | Legal counsel; CEO where the playbook says so | Redline and approval |
| G5: signature | Before signing | Authorised signatory | Completed sales and legal checklists of the Contract Pack Index |

## 7.4  Discount limits

| Component | Account manager | Sales head | CEO | Floor |
| --- | --- | --- | --- | --- |
| Perpetual licence fee | 5% | 10% | 15% | 85% of list |
| Subscription per user per month | 5% | 10% | 15% | 85% of list |
| Implementation or onboarding fee | 5% | 10% | 15% | 85% of list |
| One-time optional services and 24x7 support | 5% | 10% | 15% | 85% of list |
| Hosting per month | 0% | 5% | 10% | 90% of list |
| Change requests and day rates | 0% | 5% | 10% | 90% of list |
| AMC rate (22%) and yearly escalation (5%) | Not discounted | Not discounted | Not discounted | 22% and 5% |

Levers (longer term, upfront payment, reference customer, case study, signing date, onboarding reduction) count toward the limit. No more than three levers on one deal without the sales head.

## 7.5  Legal review triggers

Legal counsel reviews before release when the deal changes: the limitation of liability or the data protection cap; payment term beyond 30 days; suspension terms; auto-renewal; service credits; governing law or venue; adds source code escrow; uses the client's own contract paper; or adds an early termination right. The platform IP position is not negotiable.

# 8.  Delivery model

## 8.1  Phases

| # | Phase | What happens |
| --- | --- | --- |
| 1 | Mobilisation | Kick-off, team and governance, plan confirmed, data requests issued, environments ordered |
| 2 | Discovery and fit-gap | Walk-through of each process on the delivered system; configuration decisions; fit-gap register |
| 3 | Environment set-up | Environment set of the broker size (Dev, UAT and Production; SIT as well for a large broker), e-mail account, backups, monitoring |
| 4 | Configuration | Masters, products and rates, numbering, chart of accounts, posting rules, approvals, security |
| 5 | Data migration | Extraction by the broker, mapping to the templates, mock loads, reconciliation |
| 6 | Integrations | E-mail, bank statement files, payment gateway |
| 7 | Training | Train-the-trainer for key users, then end-user training per role |
| 8 | System integration test | End-to-end runs across roles with the configured data |
| 9 | User acceptance test | Key users run the UAT scripts with the broker's own data |
| 10 | Cutover | Final extract, final loads, reconciliation, go/no-go |
| 11 | Go-live | First day of transactions in iNXT BrokerVerse |
| 12 | Hypercare | Close support until the first month-end close is done |

## 8.2  Timelines by size

| Milestone | Small (8 weeks) | Medium (12 weeks) | Large (20-week plan) |
| --- | --- | --- | --- |
| Kick-off | Week 1 | Week 1 | Week 1 |
| Configuration workbook and fit-gap register signed | Week 2 | Week 3 | Week 5 |
| Mock load 1 reconciled | Week 3 | Week 5 | Week 7 |
| SIT exit report | Week 4 | Week 7 | Week 11 |
| UAT sign-off and go decision | Week 6 | Week 9 | Weeks 13 to 14 |
| Go-live | Week 7 | Week 10 | Week 15 |
| Hypercare exit and handover | Week 8 | Week 12 | Week 20 |

A Large broker with a simple product mix can follow a 16-week variant with go-live at the start of week 13. Enterprise plans are set at mobilisation (20 weeks or more).

## 8.3  Team size by implementation

The average team size below is derived from the base man-days and the duration. Assumption: the actual mix is set by the head of delivery at mobilisation.

| Size | Base man-days | Weeks | Average full-time equivalents | Typical team (Proposed) |
| --- | --- | --- | --- | --- |
| Small | 70 | 8 | About 1.8 | Project manager (part time), one functional consultant, technical and DevOps lead (part time) |
| Medium | 130 | 12 | About 2.2 | Project manager (part time), two functional consultants, migration lead, technical and DevOps lead (part time) |
| Large | 230 | 16 to 20 | About 2.3 to 2.9 | Project manager, two or three functional consultants, migration lead, technical and DevOps lead |
| Enterprise | 360 | 20 or more | About 3.6 or less | Project manager, three functional consultants, migration lead, technical and DevOps lead, head of delivery in the steering committee |

## 8.4  Data migration

- Templates only: every load uses the delivered upload templates. The broker owns, extracts, cleanses and signs off its data; iorta TechNXT advises on mapping, runs the loads with the broker and reports the results.

- Open positions, not history: in-force policies, open receivables, the trial balance and masters at the go-live date. Closed history stays in the old system, kept read-only.

- Mock loads: two for Small followed by the cutover rehearsal, three for Medium, four for Large (the last one is the cutover rehearsal). The rehearsal runs in a temporary Pre-Prod created from a production backup. Exit criteria rise from "all files load" to "all control figures reconcile and UAT on migrated data passes".

- Go/no-go: UAT signed with no open severity 1 or 2 defect; final load reconciled exactly or differences accepted in writing by the Accounting Manager; users trained; cutover checklist done; hypercare team ready; rollback plan confirmed. Rollback is planned up to the end of the first business week; after that, fix forward.

## 8.5  Training

Role-based train-the-trainer: iorta TechNXT trains one key user per team (two for teams of more than 15 users), who then train their teams with iorta TechNXT present at the first sessions. At least two thirds of each session is hands-on. Every user passes a practical assessment before receiving production access; key users need at least 90%. End-user training runs in the two weeks before go-live.

## 8.6  Acceptance

Every phase ends with named deliverables and written acceptance. The Client reviews within 5 Business Days; a deliverable is deemed accepted if no written objection arrives in that time, or if the Client uses it in production. Severity 3 and 4 defects alone do not block acceptance. Three certificates mark the money and service milestones:

| Certificate | Effect |
| --- | --- |
| UAT Sign-off Certificate | Second 40% of the implementation or onboarding fee; condition for the go decision |
| Go-live Acceptance Certificate | Final 20%; perpetual licence fee; subscription Monthly Fee starts; Warranty Period starts |
| Hypercare Exit and Handover to Support Certificate | Production support under the Support Agreement takes over |

## 8.7  Hypercare

The project team stays with the broker after go-live: daily check-ins in the first week, then weekly. Hypercare covers the first month-end close (bank reconciliation, remittance, Month-End Close run, BIR reports). Default length: 2 weeks (Small), 3 weeks (Medium), 4 to 6 weeks (Large). If the first close falls later, hypercare extends at no charge. Exit requires no open P1 or P2, the first close approved, known errors documented, environment and configuration baselines recorded, contacts agreed, L1 trained on tickets, monitoring live and a first restore test passed.

## 8.8  Delivery governance

A steering committee (broker sponsor as chair, broker project manager, Accounting Manager and a business head; iorta TechNXT account manager and project manager) meets every two weeks and at each go/no-go. A weekly status meeting reviews progress, the RAID log and decisions needed. Escalation runs from the project managers to the steering committee, then to the dispute steps of the MSA.

# 9.  Support model

## 9.1  Levels

| Level | Who | Scope |
| --- | --- | --- |
| L1 | Broker super users (one trained key user per team) and the broker's System Administrator | How-to questions; users, roles and password resets; settings and master data; logging tickets with evidence |
| L2 | iorta TechNXT application support | Triage, reproduction, analysis, configuration and data corrections under change control, workarounds, known-error records, release coordination |
| L3 | iorta TechNXT engineering and DevOps | Code defects, database scripts, performance, infrastructure where iorta TechNXT hosts, security incidents, RCA, fixes and releases |

Only named L1 contacts of the broker (up to 5) raise tickets, through one service desk: a portal or mailbox for all tickets and a telephone line for P1.

## 9.2  Service levels

Standard support runs 08:00 to 18:00 PHT, Monday to Friday, except Philippine regular holidays. The 24x7 Severity 1 option adds round-the-clock response to P1 incidents reported by telephone.

| Severity | First response | Updates | Restore or workaround | Permanent fix |
| --- | --- | --- | --- | --- |
| P1 Critical | 30 minutes | Every hour | 4 service hours | RCA in 5 Business Days; next emergency or planned release |
| P2 High | 2 service hours | Every 4 service hours | 2 Business Days | Next planned release |
| P3 Medium | 1 Business Day | Every 3 Business Days | 5 Business Days | Planned release as agreed |
| P4 Low | 2 Business Days | Weekly | Not applicable | Planned, or a change request |

Service credits apply for missed P1 and P2 restore targets and for response and restore SLA below 95% and 90%, capped at 10% of the monthly fee of the affected service. Hosting availability target: 99.5% in service hours.

## 9.3  Release and patch policy

| Item | Policy |
| --- | --- |
| Planned release | Monthly, when there are fixes or changes; release notes at least 10 Business Days before deployment to UAT |
| Emergency release | For a P1 or a security issue, approved by the support manager and the broker's IT head |
| Testing | Installed in Dev, then SIT for a large broker, then UAT; the broker runs the UAT scripts that cover the change; iorta TechNXT runs the regression set; a major release is also rehearsed in a temporary Pre-Prod |
| Deployment | In the maintenance window (default Saturday 20:00 to Sunday 06:00 PHT), announced at least 5 business days ahead; database snapshot before; smoke test after |
| Rollback | Previous image and front-end build; migrations only add, so the previous version runs on the newer schema |
| Supported versions | The current release and the two previous planned releases |
| Patching | Runtime and dependency advisories reviewed monthly; critical fixes as an emergency release; container base image at least quarterly; operating system and database patches monthly critical security patches within 14 days and high within 30 days where iorta TechNXT hosts |

## 9.4  AMC and the subscription

For a perpetual licence, the first 12 months from go-live are the Warranty Period with support at no charge; the AMC starts in Year 2 at 22% of the licence fee a year, invoiced yearly in advance and increasing 5% at each anniversary. A lapsed AMC is reinstated by paying the lapsed fees plus a reinstatement fee. For a subscription, the same support is included in the Monthly Fee. In both, the AMC or subscription covers corrections, updates of the OOTB version, regulatory form updates released for all customers, security patches and standard support.

## 9.5  Service management

- Monthly service report by the 10th Business Day and a monthly service review with the broker's IT head and System Administrator; a yearly review agrees improvements and the release plan.

- Problem records for every P1, for P2s with unknown cause and for causes behind three or more incidents a month.

- A knowledge base shared with L1 contacts, reviewed at each release and at least twice a year.

- Backup verification daily, restore tests quarterly, a tabletop DR exercise yearly and a full recovery every two years where iorta TechNXT hosts.

# 10.  Product lifecycle

## 10.1  Versioning

The release in production is identified by its release tag and the commit shown by GET /api/version. Proposed: name releases by year and sequence, with three levels:

| Level | Content | Cadence (Proposed) | Example |
| --- | --- | --- | --- |
| Major release | New modules, merged change requests, regulatory changes, migrations | Twice a year | 2027.1 |
| Planned (minor) release | Fixes, small merged changes, regulatory form updates | Monthly, when there is content | 2027.1.3 |
| Emergency release | P1 fix or security patch | As needed | 2027.1.3-e1 |

A major release triggers an updated source code escrow deposit for clients with escrow. Supported versions follow the AMC: the current release and the two previous planned releases.

## 10.2  From change request to product feature

- Request. The client raises a change request; iorta TechNXT logs it within 2 Business Days.

- Impact assessment. iorta TechNXT states in Part B of the Change Request Form whether the need can be met by configuration, and whether the change will be merged into the product line (Yes, No, To be decided).

- Product decision. The product council (below) decides the merge for every Medium and Large change request and for any Small one that more than one client has asked for. Criteria: number of clients and prospects asking; regulatory driver; fit with the roadmap; effect on configuration rather than code; support cost of not merging.

- Build once. A merged change is built in the product line as configurable behaviour (a setting, a template or a master), not as a client-specific branch, and released in a planned release.

- Price. The requesting client pays the change request price once. The feature then becomes part of the product for all clients under the AMC or the subscription.

- Not merged. A client-specific change is supported at day rates after its 30-day warranty and is not covered by the AMC.

Proposed: iorta TechNXT may offer a reduced change request price when a change is merged and judged useful to most clients. This is a commercial decision for the CEO, counted against the discount limits.

## 10.3  Roadmap themes

The themes below come from the known limits and the "outside OOTB" list of the current release. They are candidates, not commitments; no dates are promised to clients until the product council approves a release plan.

| Theme | Current release | Candidate direction |
| --- | --- | --- |
| Partner certification | Connectors delivered for SMS, CTPL, LTO, insurers, banks, BIR EIS and screening, in test mode | A list of partners whose interface was accepted, kept per release, so the next client goes live faster |
| BIR eFPS and eBIRForms | Returns, alphalists and DAT files prepared and reconciled; the broker validates and files | Follow the BIR formats each year under the AMC; e-filing only if the BIR offers an interface |
| IC report formats | IC annual statement schedules and production report as working papers (compliance package) | Track the IC form set each year; confirm the account mapping per client chart |
| AMLC reporting | Report files in the BV-AMLC-TXN 1.0 layout, confirmed by the compliance officer | Align the file with the AMLC's current guidelines once confirmed with a first client |
| Mobile | Web application for desktop and laptop browsers; mobile layouts not tested | Responsive layouts for key screens first; a mobile application only if demand is shown |
| In progress | Sales activity log, quote wizard from the Product Configurator, supplier 2307, fixed asset disposal | Complete and release in the next planned release |
| Security and usability | Session in local storage; two-step enrolment without QR code; moderate advisory on a front-end library; no screen for report schedules; some masters without an Upload button; Filipino screens not available | httpOnly cookie session; QR code enrolment; library upgrade; schedule screen; Upload buttons; translation file |
| Capacity | No load test run yet | Load test on a production-sized environment before the first Large go-live |

## 10.4  Development standards

Code changes follow the code fix standards of the Production Support Approach and Standards: branching and review, rules for the change, unit and business-rule tests, and the regression set before each release. Each release is checked against the regression tests (634 business-rule tests in the tested release) and the role-based screen check.

# 11.  Team and roles at iorta TechNXT

## 11.1  Roles by stage

| Role | Sell | Contract | Deliver | Support | Product |
| --- | --- | --- | --- | --- | --- |
| CEO | Approves discounts up to 15%; key accounts | Signs; approves liability and credit changes with legal counsel | Escalation | Escalation | Chairs the product council (Proposed) |
| Sales head | Pipeline; approves up to 10% | Approves payment term up to 45 days, auto-renewal changes, escrow |  |  | Market input |
| Account manager | Prospecting, meetings, demos, proposals; approves up to 5% | Prepares the contract set; deal file | Steering committee member | Commercial owner; renewals; referrals | Client requests |
| Solution consultant | Demos, discovery workshops, sizing | Scope inputs to the SOW | Can join the project as functional consultant (Proposed) |  | Fit-gap patterns |
| Legal counsel |  | Reviews the triggers; owns the templates | Change Request and certificate disputes |  |  |
| Finance | Credit check (Proposed) | Tax treatment, withholding | Milestone invoicing | AMC, subscription and hosting billing; collections |  |
| Head of delivery | Capacity gate G3 | Dates in the Order Form | Delivery quality and resources; approves Medium CRs | Escalation | Delivery feedback |
| Project manager |  |  | Plan, RAID log, status, steering committee papers | Handover |  |
| Functional consultants |  |  | Discovery, configuration, mapping, SIT, train-the-trainer, UAT support | L2 back-up during hypercare |  |
| Migration lead |  |  | Mapping, loads, reconciliation, cutover runbook |  |  |
| Technical and DevOps lead | Hosting answers in presales | Hosting option and sizing | Environments, e-mail, payment gateway, backups, monitoring, cutover | L3 infrastructure, backups, DR drills | Platform operations |
| Support manager |  |  | Hypercare exit | Service desk, SLA, CAB, monthly service report | Problem trends |
| L2 application support |  |  |  | Triage, analysis, configuration and data corrections | Known errors |
| L3 engineering |  |  | Change requests | Code defects, RCA, fixes, releases | Product development |
| Product manager (Proposed) | Roadmap briefings |  |  | Release planning | Roadmap, merge decisions, release notes |
| Data protection officer | NDA and privacy questions | DPA | Data migration privacy | Breach handling; certificates of deletion | Privacy by design |

## 11.2  Capacity

Assumption: with the man-days of the price book, one delivery pod (project manager, two functional consultants, migration lead and a shared technical and DevOps lead) can carry one Medium project, or two Small projects, at a time. The head of delivery uses gate G3 to keep the sales pipeline within the delivery capacity.

# 12.  KPIs by function

Targets marked Proposed are starting values for management to confirm at the first quarterly business review.

## 12.1  Sales

| KPI | Definition | Target |
| --- | --- | --- |
| Qualified pipeline | Value of qualified opportunities at list, 5-year view | 3 times the yearly booking target (Proposed) |
| Win rate | Won / (won + lost) qualified opportunities | 25% (Proposed) |
| Quotation speed | Quotations sent within 2 business days of the meeting | 100% |
| Proposal speed | Proposals sent within 5 working days of the workshop | 100% |
| Average discount | Weighted discount off list, by component | Below 5% (Proposed) |
| Recurring share | Recurring fees (subscription, AMC, hosting) / 5-year contract value | Tracked |
| Sales cycle | Days from first meeting to signature | Tracked by segment |

## 12.2  Delivery

| KPI | Definition | Target |
| --- | --- | --- |
| Go-live on plan | Go-lives on the baselined date or within 2 weeks | 80% (Proposed) |
| Effort variance | Actual man-days / planned man-days, by project | Within 10% (Proposed) |
| Reconciliation at cutover | Control figures agree exactly or differences accepted in writing | 100% |
| UAT first pass | UAT scripts passed in the first cycle | 85% (Proposed) |
| Hypercare exit on plan | Exit by the planned week, or by the first month-end close | 90% (Proposed) |
| Milestone billing | Milestones invoiced within 5 Business Days of the certificate | 100% (Proposed) |
| Client satisfaction at hypercare exit | Survey score | 8 out of 10 (Proposed) |

## 12.3  Support

| KPI | Definition | Target |
| --- | --- | --- |
| Response SLA | Tickets responded to within target / tickets | 95% |
| Restore SLA | Tickets restored within target / tickets | 90% (P1: 100%) |
| Availability (iorta TechNXT hosts) | Available minutes in service hours / minutes in service hours | 99.5% |
| Reopen rate | Tickets reopened / tickets resolved | Below 5% |
| Backlog age | Open P3 tickets older than 30 days | 0 |
| RCA on time | P1 RCA reports within 5 Business Days | 100% |
| Change success | Changes without rollback or incident / changes | 95% |
| Backup tests | Planned restore tests done and passed | 100% |

## 12.4  Product and development

| KPI | Definition | Target |
| --- | --- | --- |
| Release on schedule | Planned releases delivered in the announced window | 90% (Proposed) |
| Regression pass | Business-rule tests passing at release | 100% |
| Escaped defects | P1 and P2 incidents caused by a release, per release | 0 P1 (Proposed) |
| Merge ratio | Change requests merged into the product / change requests delivered | Tracked; rising (Proposed) |
| Security advisories | Critical advisories fixed in an emergency release; high in the next release | Critical within 14 days, high within 30 days |
| Release test status | Failed, blocked and not-run cases of the release test closed | All closed before the next major release (Proposed) |

## 12.5  Finance and management

| KPI | Definition | Target |
| --- | --- | --- |
| Bookings | Contract value signed, at list and at the quoted price | Set yearly by the CEO |
| ARR | Subscription, AMC, hosting and 24x7 support, annualised | Set yearly by the CEO |
| AMC and subscription renewal | Renewals / renewals due | 95% (Proposed) |
| DSO | Average days from invoice to payment | 45 days or less (Proposed) |
| Reference customers | Live clients willing to take reference calls | 2 by the end of the first year (Proposed) |

# 13.  Governance

## 13.1  Internal forums

| Forum | Members | Frequency | Decides |
| --- | --- | --- | --- |
| Pipeline review | Sales head, account managers, solution consultants | Weekly | Qualification, next steps, forecast |
| Deal desk (Proposed) | Sales head, head of delivery, finance; legal counsel when triggered | As needed, within 2 business days of a request | Pricing gate G2, capacity gate G3, legal gate G4 |
| Delivery portfolio review | Head of delivery, project managers | Weekly | Status, risks, resources across projects |
| CAB | Support manager with each client's change owner | Weekly, and as needed for emergencies | Normal and emergency changes in production |
| Product council (Proposed) | CEO (chair), product manager, head of delivery, support manager, engineering lead, sales head | Monthly | Merge decisions, roadmap, release plan |
| Quarterly business review | CEO and function heads | Quarterly | KPIs, targets, investments, price book changes |
| Price book review | CEO, sales head, finance | Yearly | Exchange rate, cloud prices, day rates, IC ranking inputs |

## 13.2  Client-facing forums

| Forum | Frequency | Source |
| --- | --- | --- |
| Project steering committee | Every two weeks and at each go/no-go | Implementation SOW |
| Weekly status meeting | Weekly during the project | Implementation SOW |
| Monthly service review | Monthly after handover | Support Agreement |
| Yearly review | Yearly | Support Agreement |
| Tabletop DR exercise | Yearly, where iorta TechNXT hosts | Hosting Agreement |

## 13.3  Document control

The contract templates, price book, rate card and sales collateral are controlled documents. Prices are changed only by rebuilding the price book from the pricing workbook. Contract templates are changed only with legal counsel. The Contract Pack Index lists the current set.

# 14.  30/60/90-day launch plan

The plan starts on the date management approves this playbook (Day 1). Owners are roles; targets are Proposed.

## 14.1  Days 1 to 30: ready to sell

| # | Action | Owner |
| --- | --- | --- |
| 1 | Approve this playbook and take the owner decisions in the last chapter | CEO |
| 2 | Legal review of the full contract pack; choose an escrow agent; confirm the open bracketed positions | Legal counsel |
| 3 | Confirm cloud and local partner hosting prices with the providers; select the local hosting partner | Technical and DevOps lead |
| 4 | Confirm the withholding treatment of the licence fee and the subscription with the tax adviser | Finance |
| 5 | Set up the demo environment with the UAT data set; rehearse the 60- and 30-minute demonstrations | Solution consultant |
| 6 | Train account managers on the Demo Script, the FAQ, the price book Quick Quote and the Negotiation Playbook | Sales head |
| 7 | Build the target list from the IC list of licensed brokers, by segment, with named buyers | Account managers |
| 8 | Close or explain the failed, blocked and not-run cases of the release test; plan the load test | Engineering lead |
| 9 | Set up the service desk, the knowledge base starter set and the monthly service report template | Support manager |
| 10 | Name the first delivery pod and the project templates (charter, plan, RAID log, configuration workbook) | Head of delivery |

## 14.2  Days 31 to 60: first conversations

| # | Action | Owner |
| --- | --- | --- |
| 11 | Run the e-mail sequence to the target list; LinkedIn notes; one webinar or event | Account managers |
| 12 | Hold first meetings and qualification; target 10 meetings and 4 demonstrations (Proposed) | Account managers |
| 13 | Run the first discovery workshops; produce sized quotations at list | Solution consultant |
| 14 | Start the deal desk; record every approval in the deal file | Sales head |
| 15 | Run the load test on a production-sized environment; publish the result | Engineering lead |
| 16 | Hold the first product council: merge criteria, versioning, roadmap candidates | CEO, product manager |
| 17 | Agree the hosting partner contract and the sub-processor details for DPA Annex 3 | Technical and DevOps lead, DPO |

## 14.3  Days 61 to 90: first commitments

| # | Action | Owner |
| --- | --- | --- |
| 18 | Send first proposals; negotiate within the limits; target 2 proposals and 1 award (Proposed) | Account managers, sales head |
| 19 | Issue the first contract set with the Contract Pack Index checklists | Account manager, legal counsel |
| 20 | Mobilise the first project; first-client terms to secure a reference (reference and case study levers) | Head of delivery, sales head |
| 21 | First quarterly business review: KPIs, pipeline against capacity, price book check | CEO |
| 22 | Publish the first release plan and release notes format | Product manager |

# 15.  Risks

| Risk | Effect | Mitigation |
| --- | --- | --- |
| Small market (about 67 brokers) | Few opportunities a year | Segment carefully; protect references; expand by added users and options |
| Requests for customisation | Longer projects, lower margin, product fragmentation | OOTB rules; change requests at day rates; product council merge decisions |
| Discounting to win early deals | Weak price list for later deals | Discount limits, floor, levers in exchange for references |
| Delivery capacity | Late go-lives, unhappy first clients | Capacity gate G3; one pod per Medium project |
| Data quality at the broker | Late cutover | Data requests in week 1; mock loads; steering committee escalation |
| Cross-border data concerns | Lost deals with data residency needs | Local partner hosting option in the Philippines |
| Known limits of the release | Objections in demos | Disclose with the workaround; roadmap themes; change request route |
| No load test yet | Performance risk for Large clients | Load test before the first Large go-live |
| Partner certification takes longer than the project | Connectors stay in test mode at go-live | Start partner contracts at kick-off (welcome e-mail); go live without the connector and switch it on after |
| Regulatory settings taken as advice | Liability if a threshold, code or tax treatment is wrong | Every delivered value is marked for the compliance officer, DPO or tax adviser to confirm; the documents say so |
| Client brand packs with third-party marks | Trademark exposure | Use only in that client's environments with written permission; never in demos |

# 16.  Decisions for the owner

| # | Decision | Recommendation |
| --- | --- | --- |
| 1 | Confirm the discount limits (5%, 10%, 15%) and the floor | Confirm |
| 2 | Confirm that the AMC is computed on the quoted (net) licence fee | Confirm, as the contracts state |
| 3 | Early termination fee for committed terms: all or 50% of the remaining recurring fees | Decide before the first contract |
| 4 | Hosting fees: no yearly increase (price book) while "recurring optional items" increase 5% (Rate Card wording) | Done: hosting and additional hosted environments have no yearly increase; the Rate Card wording is aligned |
| 5 | Hypercare length: the Commercial Proposal Note says four weeks; the SOW and Implementation Approach set 2, 3 and 4 to 6 weeks by size | Done: the Commercial Proposal Note now follows the SOW |
| 6 | Size thresholds: commercial tiers use 26 to 100 users for Medium; the Implementation Approach uses 26 to 75 users for a Medium project | Done: both documents use 26 to 100 users; data volumes can still move a project to the next delivery size at mobilisation |
| 7 | Versioning scheme and release cadence (Proposed in this playbook) | Approve |
| 8 | Create the product manager role and the product council | Approve |
| 9 | Mobile: the FAQ says "not planned in OOTB, to confirm roadmap" | Keep it as a roadmap theme for responsive layouts; no mobile application commitment |
| 10 | KPI targets marked Proposed | Confirm at the first quarterly business review |
| 11 | Price lines for the activation of the AML/CFT toolkit, the IC compliance registers and the BIR pack, the go-live of each connector, dealer programme set-up and client brand packs (Rate Card, marked to confirm by management) | Confirm the lines and amounts, or fold them into the implementation fee of the size |
| 12 | Whether the AML/CFT toolkit, IC compliance registers and BIR pack stay in every package or become paid modules for new clients | Keep them in every package: they are the main local differentiator and a module price would weaken the per-user comparison |

# 17.  Document Sign-Off

| Serial Number | Description | Owner | Status |
| --- | --- | --- | --- |
| 1 | Owner decisions listed in the last chapter | iorta TechNXT | Open |

| Sign Off Date | Signature | Approved By | Department & Project Role |
| --- | --- | --- | --- |