Toyota Insurance Services Philippines

Delivery Governance, RACI, Risks, Architecture Decisions, Production Readiness, Go-Live and Hypercare

Date - 10 October 2026

Version - 0.9 Draft

Prepared by – iorta TechNXT

TABLE OF CONTENTS

1.	Document Control	4

2.	Acronyms and Glossary	6

1.	Purpose, scope and audience	7

2.	Governance structure and delivery sequence	7

2.1	Governance bodies	7

2.2	Delivery sequence and traceability	9

3.	Workstreams and personas	10

3.1	Workstreams	10

3.2	TISPH personas	10

4.	RACI	11

4.1	RACI per workstream	11

4.2	RACI per persona	12

5.	Risk register and decision log	13

5.1	Risk register	13

5.2	Decision log: open TISPH decisions	18

6.	Architecture decision records	20

6.1	How the ADR log is kept	20

ADR-01 Modular monolith on one PostgreSQL database	20

ADR-02 Node.js API and React single-page application in two container images	20

ADR-03 Route registry as the single source of the API documentation	20

ADR-04 Forward-only, idempotent SQL migrations under a database lock	20

ADR-05 In-process scheduler and database outboxes instead of a message broker	20

ADR-06 Azure Container Apps rather than a self-managed Kubernetes cluster	20

ADR-07 Build once, promote by image digest, with approvals and federated pipeline identity	20

ADR-08 Terraform as the only infrastructure-as-code tool	20

ADR-09 Business rules held as configuration, with owners and maker-checker	20

ADR-10 Controls built into the platform: permissions, maker-checker, SoD rules, authority matrix	20

ADR-11 Field-level encryption of personal identifiers and masking by permission	20

ADR-12 Microsoft Entra ID sign-in with users provisioned in BrokerVerse	20

ADR-13 Environment marker in the database and masking of production copies	20

ADR-14 Go-live through workbooks over the API, transaction reset and go-live lock	20

ADR-15 Audit trail in the operational database, protected by permissions	20

ADR-16 Client branding through a brand pack enforced by the deployment	20

ADR-17 File-based integrations through an outbox framework and SFTP storage	20

7.	Production readiness checklist	28

A. Infrastructure and environments	28

B. Release and change control	28

C. Security and access	29

D. Data protection	30

E. Data, configuration and migration	30

F. Integrations	31

G. Operations, monitoring, backup and recovery	31

H. Support, people and compliance	31

8.	Go-live plan	32

8.1	Approach	32

8.2	Timeline relative to go-live	32

8.3	Decision rights on the cutover weekend	33

8.4	Go/No-Go criteria	33

8.5	Communications	33

8.6	Go-live evidence pack	34

9.	Hypercare plan	34

9.1	Duration and hours	34

9.2	Team	34

9.3	Support flow and severity	35

9.4	Daily and weekly checks	36

9.5	Releases during hypercare	36

9.6	Exit criteria	36

10.	Change management	37

10.1	Scope change (BRD 8)	37

10.2	Release change	37

10.3	Configuration change in production	37

10.4	Emergency access	38

10.5	Organisational change: what changes for TISPH users	38

10.6	Stakeholder map	38

11.	Training and adoption plan	39

11.1	Principles	39

11.2	Materials	39

11.3	Curriculum by persona group (proposal)	39

11.4	Schedule (proposal)	40

11.5	Assessment	40

11.6	Adoption measures (KPIs)	40

12.	Long-term governance (ten years and more)	41

12.1	Recurring activities	41

12.2	Technology lifecycle	41

12.3	Knowledge retention	41

13.	Summary of status	42

14.	Register of Planned items	42

15.	Open questions for TISPH	43

16.	Requirements traceability	45

Appendix A. File references	45

17.	Document Sign-Off	49

# Document Control

| Date | Version | Author & Business Unit Info | Reviewed By & Business Unit Info | Approved By & Business Unit Info | Change History |
| --- | --- | --- | --- | --- | --- |
| 10 October 2026 | 0.9 Draft | iorta TechNXT iorta TechNXT, Project Manager (TISPH programme) | Pending review: Project Manager (BRD section 11 signatory) (TISPH); Project Sponsor (BRD section 11 signatory) (TISPH); Head of Information Technology (BRD section 11 signatory) (TISPH); Head, Risk Management (BRD section 11 signatory) (TISPH); Business Process Owners: Sales, Operations, Cash Control, Finance and General Accounting (BRD section 11 signatories) (TISPH); Internal Audit representative (to be named) (TISPH); Engagement Director (iorta TechNXT); Solution Architect (iorta TechNXT) | Pending approval: TISPH Project Sponsor; TISPH Head of Information Technology; TISPH Project Manager; iorta TechNXT Engagement Director | First issue for review. Governance structure, RACI per workstream and per persona, risk register with the open TISPH decisions, sixteen architecture decision records for choices present in the code at commit 58ad7702, production readiness checklist, go-live plan and Go/No-Go criteria, hypercare plan, change management and the training and adoption plan with adoption measures. |
| 10 October 2026 | 0.9 Draft | iorta TechNXT | As above | As above | Review notes (architecture and audit review against the code at 58ad7702). Corrected: the audit entry is written after the business transaction commits, not inside it (ADR-01, ADR-15, new risk R-34); posting-rule maker-checker is a setting (accounting.configuration_maker_checker) and not fixed (ADR-09, 10.3); the API documentation is generated but not checked for freshness in CI (ADR-03); scheduled jobs are not limited to the 13 of jobs.json (ADR-05); back-end test files are 114, not 117; the data Go/No-Go criteria are G1 to G11; idle time-out default is 30 minutes and lockout applies to password sign-in only; the start-up check refuses a partial Entra ID set-up rather than requiring one; adoption measure A-1 now reads the User Matrix. Added: the single-administrator control switches (R-33, readiness C-12, SEC-Q12); the receipt cancellation right of CCD-BP and the warn-only TISPH SoD rule (3.2, R-15, C-06, GQ-15); access reviews, User Matrix and dormant-account job as built controls (C-11, C-13, 12.1); ADR-17 on file-based integrations; NFR-17.4 posture report (G-08); hypercare exit for supplier accounts (HX-09); supplier accounts in production (C-14); missing cross-references (Data Migration Q17, Q18; SEC-Q6, SEC-Q12). Reviewers now refer to the BRD section 11 signatories. |
| 10 October 2026 | 0.9 Draft | iorta TechNXT | As above | As above | Repository references updated to the reorganised folders (docs/TISPH/pack/, docs/TISPH/frs/, docs/TISPH/testing/); archived e2e records cited under docs/archive/2026-10-10/e2e/. |
| 11 October 2026 | 0.9 Draft | iorta TechNXT | As above | As above | Documentation cleanup: RAID log, training plan and role deck citations replaced by sections 5, 10 and 11 of this document and the TISPH user manual; known limitations and release references point to the TISPH operations and environments documents; training materials table updated (TISPH manual built, Draft). |

Document information

| Item | Value |
| --- | --- |
| Document | BrokerVerse for TISPH: Delivery Governance, RACI, Risks, Architecture Decisions, Production Readiness, Go-Live and Hypercare |
| Client | Toyota Insurance Services Philippines (TISPH) |
| Prepared by | iorta TechNXT |
| Owner | iorta TechNXT, Project Manager (TISPH programme) |
| Version | 0.9 Draft |
| Date | 10 October 2026 |
| Status | Draft for review |
| Classification | Confidential: TISPH and iorta TechNXT |
| Code baseline | TISPH-DEV line, integration branch tisph/integration6, commit 58ad7702 (Azure deployment work of tisph/azure-deploy included). The commit is contained in TISPH-DEV, which has since moved on by three commits (22e3a650, 10 October 2026) |
| Requirements baseline | TISPH Business Requirement Document v2.2 (signed): section 6.3 (non-functional), 5.13 (integrations), 5.14 (access, approval and audit), 8 (change control), 9 (delivery approach) |
| Planning baseline | Platform features build plan of 10 October 2026 (work packages W0 to MAN-B, TISPH decisions P, R, M, E, C, D); Accounts > Remittance build specification of 9 October 2026 (phases R1 to R4, questions Q1 to Q20) |

Reviewers

| Name / role | Organisation | Review focus |
| --- | --- | --- |
| Project Manager (BRD section 11 signatory) | TISPH | Governance bodies, RACI, decision log, go-live plan |
| Project Sponsor (BRD section 11 signatory) | TISPH | Go/No-Go criteria, risk acceptance, hypercare exit |
| Head of Information Technology (BRD section 11 signatory) | TISPH | Architecture decisions, production readiness, support model |
| Head, Risk Management (BRD section 11 signatory) | TISPH | Risk register, control readiness |
| Business Process Owners: Sales, Operations, Cash Control, Finance and General Accounting (BRD section 11 signatories) | TISPH | Persona RACI, UAT and training, adoption measures |
| Internal Audit representative (to be named) | TISPH | Evidence trail, segregation of duties, change control |
| Engagement Director | iorta TechNXT | Commitments, resourcing, escalation |
| Solution Architect | iorta TechNXT | Consistency of the decision records with the code |

- A statement without a label describes the code, infrastructure definitions, scripts or runbooks at the code baseline. Appendix A lists the files behind each section.

- Planned marks something designed but not built. Each planned item names the work package or the TISPH decision it depends on, and is listed in section 14.

- Not built marks a gap with no work package yet. Each one points to an open question in section 15.

- A plan (for example the training timetable or the hypercare roster) is a proposal for TISPH to agree. It is not a claim about the system and carries no label.

- BRD references are given by identifier only (for example NFR-13, INTG-04). The signed BRD remains the authoritative text. People are referred to by role; names are recorded in the RACI once TISPH confirms them (question GQ-03).

# Acronyms and Glossary

| Acronym / Term | Definition / Meaning |
| --- | --- |
| ADR | Architecture decision record: context, decision and consequences of one design choice |
| BPO | Business Process Owner |
| C-1 to C-10 | Steps of the cutover runbook in the Data Migration document |
| CCD | Cash Control Department |
| DA-1 to DA-5 | Tests and activities still to run, listed in the NFR Compliance document |
| Digest | The content hash that identifies one container image exactly |
| FGA | Finance and General Accounting |
| Gate | A point in the delivery sequence where named evidence is reviewed and a decision is recorded |
| Go-live lock | The setting golive.locked; once on, the migration workbook and the transaction reset are refused |
| Hypercare | The period of reinforced support after go-live |
| Key user | A trained member of a team who gives first-line support to colleagues |
| Maker-checker | The rule that the approver of a record is not the user who created or submitted it |
| PMO | Project Management Office |
| RACI | Responsible, Accountable, Consulted, Informed |
| SoD | Segregation of duties |
| SUPERID | A UAT-only TISPH role that includes the System Administrator |
| Work package | A unit of the platform features build plan (for example REG-1, MU-A, PR-1b) |

# Purpose, scope and audience

This document sets out how the delivery of BrokerVerse for TISPH is governed from the signed BRD to steady-state support, and how the platform stays governable for the ten years or more that TISPH expects to run it. It covers:

- the governance bodies, decision rights and the delivery sequence (BRD 8, 9.1, 9.2);

- who is responsible, accountable, consulted and informed, per workstream and per TISPH persona;

- the risk register, including every open TISPH decision that blocks build or go-live;

- architecture decision records (ADRs) for the main choices that the code already embodies;

- the production readiness checklist, the go-live plan with its Go/No-Go criteria, and the hypercare plan;

- change management (scope, release, configuration and organisational change) and the training and adoption plan.

It is written for TISPH IT, who will own and operate the platform; for auditors, who need to see that decisions, changes and go-live were controlled and evidenced; and for a future support team, who will need the decision records and the risk history to change the platform safely.

Detailed procedures are not repeated here. They live in the companion documents of this pack and in the runbooks of the repository:

| Topic | Where |
| --- | --- |
| Solution and deployment architecture | Architecture document of this pack; deploy/AZURE.md |
| Environments, pipeline, release and rollback | Environment Strategy document of this pack; deploy/RELEASE_PIPELINE.md |
| Data migration and cutover runbook | Data Migration document of this pack; docs/onboarding/GO_LIVE_DATA_WORKBENCH.md |
| Non-functional compliance | NFR Compliance document of this pack |
| Security controls | Security document of this pack |
| Data model, lineage and retention | Data document of this pack |
| First-line and production support | docs/onboarding/SUPPORT_AND_ESCALATION.md; docs/developer-guide/ |

# Governance structure and delivery sequence

## Governance bodies

Diagram 1

| Element | Details |
| --- | --- |
| Steering Committee | TISPH Project Sponsor (chair), Head of IT, Business Process Owners, iorta TechNXT Engagement Director |
| Project Management Office | TISPH Project Manager, iorta TechNXT Project Manager |
| Design Authority | TISPH Head of IT and Information Security, iorta TechNXT Solution Architect and Functional Lead |
| Change Control Board | TISPH Project Manager and Process Owners, iorta TechNXT Project Manager and Business Lead |
| Release and Change Advisory | TISPH IT (production approvers), iorta TechNXT DevOps lead |

| From | Connection | To |
| --- | --- | --- |
| Steering Committee | - | Project Management Office |
| Project Management Office | - | Design Authority |
| Project Management Office | - | Change Control Board |
| Project Management Office | - | Release and Change Advisory |
| Project Management Office | - | Workstreams (section 3) |
| Design Authority | architecture decisions (ADRs) | Workstreams (section 3) |
| Change Control Board | approved change requests | Workstreams (section 3) |
| Release and Change Advisory | production approvals | Workstreams (section 3) |

| Body | Decides | Inputs | Cadence (proposed) | Records |
| --- | --- | --- | --- | --- |
| Steering Committee | Scope and phase changes that move a date (BRD 8.1); acceptance of residual risks rated High; Go/No-Go at checkpoint 1 and at C-9; hypercare exit | Status report, risk register, decision log, readiness checklist | Monthly; weekly from four weeks before go-live | Minutes with decisions |
| Project Management Office | Plan, resourcing, decision deadlines, escalation to the Steering Committee | Workstream status, RAID log | Weekly | Status report, RAID log (risk register and decision log of section 5) |
| Design Authority | Architecture decisions and their changes (section 6); non-functional trade-offs; acceptance of security exceptions | ADR proposals, NFR and security assessments | Fortnightly, and on demand | ADR log (section 6) |
| Change Control Board | Change requests against the signed BRD (BRD 8); classification of clarifications and defects that do not move dates | Change request form (template in docs/package/03_Contracts) | Weekly during build | Change request register (BRD 8.2) |
| Release and Change Advisory | Approval of each SIT, UAT and production deployment; emergency changes | Pipeline run, release notes, test evidence | Per release | GitHub environment approvals and run summaries (ADR-07) |

The production approval itself is enforced by the pipeline: SIT, UAT and production deployments wait for the required reviewers configured on the GitHub environments azure-sit, azure-uat and azure-prod (.github/workflows/azure-deploy.yml, deploy/AZURE.md section 9). Who those reviewers are is open (question GQ-05 and Environment Strategy Q2).

## Delivery sequence and traceability

BRD 9.1 sets the delivery sequence from sign-off to go-live and BRD 9.2 requires that every requirement reference carries through the chain: FRS cites the BRD reference, the build item cites the FRS, the test case cites the build item, and the UAT sign-off cites the test case. The gates below apply that chain.

Diagram 2

| No. | Step | Next |
| --- | --- | --- |
| 1 | BRD v2.2 signed (BRD 11) | step 2 (FRS per build item, cites BRD ref) |
| 2 | FRS per build item, cites BRD ref | step 3 (Build on TISPH-DEV, work packages cite FRS) |
| 3 | Build on TISPH-DEV, work packages cite FRS | step 4 (Gate 1, SIT exit) |
| 4 | Decision: Gate 1, SIT exit | step 5 (UAT on Azure UAT, test cases cite build items) |
| 5 | UAT on Azure UAT, test cases cite build items | step 6 (Gate 2, UAT sign-off) |
| 6 | Decision: Gate 2, UAT sign-off | step 7 (Gate 3, Checkpoint 1 (C-10 business days)) |
| 7 | Decision: Gate 3, Checkpoint 1 (C-10 business days) | step 8 (Cutover (Data Migration document)) |
| 8 | Cutover (Data Migration document) | step 9 (Gate 4, Final Go/No-Go (C-9)) |
| 9 | Decision: Gate 4, Final Go/No-Go (C-9) | step 10 (Hypercare) |
| 10 | Hypercare | step 11 (Gate 5, Hypercare exit) |
| 11 | Decision: Gate 5, Hypercare exit | step 12 (Steady-state support) |
| 12 | Steady-state support | End |

| Gate | Entry evidence | Decides |
| --- | --- | --- |
| Gate 1: SIT exit | Full back-end and front-end suites green on the release commit (ci.yml); SIT deployment by digest; interface tests on SIT (SMTP, SFTP); no open severity 1 defect | PMO |
| Gate 2: UAT sign-off | UAT scripts executed per persona; defects triaged; each Business Process Owner signs the area; trace from test case to BRD reference | Business Process Owners, TISPH Project Manager |
| Gate 3: Checkpoint 1 | Production readiness checklist (section 7) complete except cutover items; dress rehearsal reconciled | Steering Committee |
| Gate 4: Final Go/No-Go | Go/No-Go criteria of section 8.4 | Steering Committee |
| Gate 5: Hypercare exit | Exit criteria of section 9.6 | Project Sponsor, Head of IT, Finance Head |

The repository already holds product-level evidence of the kind each gate needs, produced against local environments rather than TISPH's Azure environments: the UAT data scenario (docs/e2e/UAT_SCENARIO_RUN.md, 433 steps passed through the public API), the go-live rehearsal (docs/e2e/GOLIVE_REHEARSAL_RUN.md, 52 checks passed), the role walk (docs/e2e/ROLE_WALK.md) and the defect log (docs/archive/2026-10-10/e2e/DEFECTS.md, archived, 149 defects, each with status Fixed). These runs used the generic broker roles (the earlier persona walks and docs/archive/2026-10-10/e2e/persona_access.md used a role model that has since been replaced); the same scripts must be repeated on TISPH UAT with the TISPH personas before Gate 2.

# Workstreams and personas

## Workstreams

| # | Workstream | Scope | Main artefacts |
| --- | --- | --- | --- |
| WS-01 | Programme management | Plan, status, RAID, decision log, steering | Status report, RAID log, this document |
| WS-02 | Requirements and functional design | FRS per build item; design notes; resolution of open decisions | FRS set, design notes, decision log |
| WS-03 | Front office build | Leads to policies, endorsements, renewals, claims; product configurator | backend/src/modules/* (sales and policy modules), brokerverse/src |
| WS-04 | Finance and Cash Control build | Receipting, collections, remittance, disbursements, accounting, period end, tax | Accounting, receipts, remittance, period-end, BIR modules |
| WS-05 | Platform features | Master upload, Environment Promotion, Copy, Risk Details, personal data, manual (build plan waves 0 to 3) | Build plan work packages |
| WS-06 | Integrations | SMTP (INTG-01), Entra ID (INTG-02), TFS (INTG-03), SAP GL files (INTG-04), insurer channel (INTG-05), banks, BIR EIS | backend/src/modules/integrations/, backend/src/modules/sap-gl/, backend/src/lib/entraId.js, backend/src/lib/mailer.js |
| WS-07 | Infrastructure and DevOps | Azure environments in Terraform, pipeline, monitoring, backup and DR | deploy/azure/, .github/workflows/ |
| WS-08 | Security and privacy | Access model, SoD, personal data protection, scans and penetration test | Security document, backend/src/lib/piiPolicy.js, backend/scripts/mask-data.js |
| WS-09 | Testing | Automated suites, SIT, UAT, performance, DR drill | backend/test, brokerverse/src/**/*.test.js, docs/e2e/ |
| WS-10 | Data migration and cutover | Configuration and migration workbooks, mocks, cutover | backend/src/modules/data-load/, backend/scripts/golive/, Data Migration document |
| WS-11 | Training, change and documentation | User manual and Help, training, communications, adoption | brokerverse/public/help/, docs/TISPH/manual/, docs/onboarding/ |
| WS-12 | Support and service management | Hypercare, support model, handover to TISPH IT | docs/onboarding/SUPPORT_AND_ESCALATION.md, developer guide |

## TISPH personas

The TISPH roles and their permission sets are delivered by migration 0348_tisph_roles.sql for a database in use and by backend/src/db/seed.js (ROLE_PERMS) for a new one; backend/src/db/seeds/82_tisph_roles.sql adds their report lists, notification role lists and one segregation-of-duties rule. The "What the role does" column repeats the role description held in the system.

| Persona (role in the system) | Business unit | What the role does in the system |
| --- | --- | --- |
| TIS Sales Associate (tis-sales-associate) | Sales | Leads, clients, quotations, placements, policies, endorsements and renewals as maker; no approval |
| TIS Sales Officer (tis-sales-officer) | Sales | As the Associate, plus lead allocation, campaigns and approval of another user's quotations, placements and renewals |
| TIS Sales Unit Head (tis-sales-unit-head) | Sales | As the Officer, plus telesales incentives and approval of supplier invoices |
| TIS Operations Associate (tis-ops-associate) | Operations | Placements, policies, endorsements, renewals and claims as maker |
| TIS Operations Officer (tis-ops-officer) | Operations | As the Associate, plus reading journal vouchers and fixed assets |
| TIS Operations Unit Head (tis-ops-unit-head) | Operations | As the Officer, plus approval of quotations, placements, renewals, claim decisions and supplier invoices |
| CCD-PDU (tis-ccd-pdu) | Cash Control | Post-dated cheque encoding, acknowledgement, deposit and cancellation |
| CCD-PDC / CCD-ADA (tis-ccd-pdc) | Cash Control | Post-dated cheques and auto-debit arrangements; reads billing, receipting and reconciliations |
| CCD-BP / QRPh (tis-ccd-bp) | Cash Control | Official and acknowledgement receipts, bills payment and QRPh, posting of collections; no reversals |
| CCD-Recon (tis-ccd-recon) | Cash Control | Daily payment reconciliation, reversals, bank and insurer statement reconciliation and its approval |
| TIS Finance and General Accounting (tis-finance) | Finance and General Accounting | Disbursements, journal vouchers, payables, fixed assets, commission and remittance, period end, bank reconciliation, posting rule approvals |
| TIS IT AppSupport / Admin (tis-it-admin) | Information Technology | Users, roles, access control, settings, reference masters, product configurator, schedules and interfaces; enters no business transactions |
| TIS General Manager (tis-general-manager) | Management | Front office with every front-office approval and supplier invoices; reads accounting, administration and the audit trail |
| SUPERID (tis-superid) | UAT only | Includes the System Administrator for user acceptance testing; to be set Inactive before go-live (role description in 0348_tisph_roles.sql) |

Points an auditor should note about the delivered permission sets:

- Receipting and reversals. CCD-BP, CCD-PDU and CCD-PDC hold write:receipts. That permission also allows cancelling a receipt (POST /receipts/:id/cancel), which reverses its payment journals. "No reversals" for CCD-BP is therefore the role's intent, not a permission boundary. The only TISPH segregation-of-duties rule delivered, SOD-TIS-BP-RECON (CCD-BP with CCD-Recon), is set to warn, not block, because the RBAC v4 user list gives one person both personas (risk R-15, question GQ-15).

- Personal identifiers. The Sales, Operations, Finance and General Manager roles hold view:pii and see full identifiers in the delivered mode; the four Cash Control roles and IT AppSupport / Admin do not.

- Administration. IT AppSupport / Admin holds write:settings, write:roles, write:users and approve:access-control, so it can change the control settings listed in risk R-33.

# RACI

R = Responsible (does the work), A = Accountable (one per row; approves), C = Consulted, I = Informed.

## RACI per workstream

Columns: SP TISPH Project Sponsor and Steering Committee; TPM TISPH Project Manager; BPO TISPH Business Process Owners (Sales, Operations, Cash Control, Finance and General Accounting); TIT TISPH Head of IT and IT AppSupport; TRM TISPH Risk Management and Information Security; DPO TISPH Data Protection Officer; IPM iorta TechNXT Project Manager; IFL iorta TechNXT Business and Functional Leads; ITL iorta TechNXT Solution Architect, technical leads and DevOps lead; IQA iorta TechNXT QA lead.

| Workstream / activity | SP | TPM | BPO | TIT | TRM | DPO | IPM | IFL | ITL | IQA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WS-01 Plan, status and RAID | I | A | I | I | I | I | R | C | C | C |
| WS-01 Steering decisions, risk acceptance | A | R | C | C | C | C | R | I | I | I |
| WS-02 FRS per build item | I | A | C | C | I | I | C | R | C | C |
| WS-02 TISPH decisions (decision log, section 5.2) | I | A | R | R | C | C | C | C | C | I |
| WS-02 Change requests (BRD 8) | A | R | C | C | I | I | R | C | C | I |
| WS-03 Front office build | I | I | C | I | I | I | A | C | R | C |
| WS-04 Finance and Cash Control build | I | I | C | I | I | I | A | C | R | C |
| WS-05 Platform features (build plan) | I | I | C | C | C | C | A | C | R | C |
| WS-06 Interface specifications (TFS, banks, SAP, BIR) | I | A | R | R | C | I | C | C | C | I |
| WS-06 Interface build and test | I | I | C | C | I | I | A | C | R | R |
| WS-07 Azure subscription, identities, Key Vault administrators | I | I | I | A/R | C | I | I | I | C | I |
| WS-07 Terraform, pipeline, monitoring | I | I | I | C | C | I | A | I | R | I |
| WS-07 Production deployment approval | I | C | C | A/R | C | I | C | I | R | C |
| WS-08 Access model and SoD rules per persona | I | C | R | C | A | I | C | R | C | I |
| WS-08 VA, MBSS scans and penetration test | I | I | I | C | A/R | I | C | I | R | I |
| WS-08 Personal data decisions (P1, P2), masking approvals | I | C | C | C | C | A/R | C | C | C | I |
| WS-08 Changes to control settings in production (R-33) and their weekly review | I | I | C | R | A | I | I | I | C | I |
| WS-08 Access reviews (Access Control > Access Reviews) | I | I | R | R | A | I | I | I | I | I |
| WS-09 Automated tests and SIT | I | I | I | I | I | I | A | C | R | R |
| WS-09 UAT execution and sign-off | C | A | R | C | C | I | C | C | C | R |
| WS-09 Performance test and DR drill | I | C | I | R | C | I | A | I | R | R |
| WS-10 Legacy extracts, cleansing, control figures | I | C | A/R | C | I | C | C | C | C | I |
| WS-10 Workbooks, loads, reconciliation workbooks | I | C | C | C | I | I | A | R | R | C |
| WS-10 Reconciliation sign-off | I | C | A/R | I | I | I | C | C | I | I |
| WS-11 TISPH user manual and Help | I | C | C | C | I | I | A | R | R | C |
| WS-11 Training delivery and key users | I | A | R | C | I | I | C | R | I | I |
| WS-11 Communications to staff, insurers, banks | A | R | R | C | I | I | C | C | I | I |
| WS-12 Hypercare | C | A | C | R | I | I | R | R | R | C |
| WS-12 Steady-state support and handover | I | C | C | A/R | C | I | R | C | R | I |

## RACI per persona

Columns: FRS review of the functional specification of the area; UAT-E execution of UAT scripts; UAT-S sign-off of the area; KEY provides the key user of the team (trained first, trains colleagues, first-line support in hypercare); MIG validation of migrated samples (cutover step C-8); CFG owner of configuration of the area (rates, limits, templates, masters); HC hypercare role.

| Persona | FRS | UAT-E | UAT-S | KEY | MIG | CFG | HC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TIS Sales Associate | I | R | I | C | I | I | Raises issues through the key user |
| TIS Sales Officer | C | R | C | R | C | C | Key user, first line for Sales |
| TIS Sales Unit Head | C | R | C | A | C | C | Approves Sales workarounds |
| Business Process Owner, Sales | A | C | A | I | A | A | Escalation point for Sales |
| TIS Operations Associate | I | R | I | C | R | I | Raises issues through the key user |
| TIS Operations Officer | C | R | C | R | R | C | Key user, first line for Operations |
| TIS Operations Unit Head | C | R | C | A | A | C | Approves Operations workarounds |
| Business Process Owner, Operations | A | C | A | I | A | A | Escalation point for Operations |
| CCD-PDU | I | R | I | C | I | I | Raises issues through the key user |
| CCD-PDC / CCD-ADA | I | R | I | C | R | I | Raises issues through the key user |
| CCD-BP / QRPh | C | R | C | R | R | I | Key user, first line for receipting |
| CCD-Recon | C | R | C | R | R | C | Key user, daily reconciliation checks |
| Head, Cash Control | A | C | A | A | A | A | Escalation point for Cash Control |
| TIS Finance and General Accounting | C | R | C | R | R | R | Key user, daily trial balance and SAP file checks |
| Unit Head, Finance and General Accounting | A | C | A | A | A | A | Signs financial reconciliation; first month-end |
| TIS IT AppSupport / Admin | C | R | C | R | C | R | Second line: users, settings, schedules, interfaces |
| Head of Information Technology | C | I | A (IT checks) | I | I | A (system settings) | Accountable for support model |
| TIS General Manager | I | R (approvals) | C | I | I | I | Informed daily during hypercare |
| SUPERID (UAT only) | I | R (UAT set-up only) | I | I | I | I | Not used; role set Inactive before go-live |

Persona-to-person allocation, and one key user per team, are to be confirmed by TISPH (question GQ-03).

# Risk register and decision log

## Risk register

Likelihood (L) and impact (I) are rated High (3), Medium (2) or Low (1); the score is L x I. Ratings are the delivery team's assessment at the baseline date and are reviewed weekly by the PMO. Risks scoring 6 or more are reported to the Steering Committee.

| ID | Risk | L | I | Score | Owner | Mitigation | Linked to |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | TISPH decisions that block platform work packages (personal data P1, P2; risk details R1 to R6; covers R7, R14; masters M1 to M15; environments E1 to E15; copy C1 to C13; manual D1 to D14) are not taken by their needed-by dates, so wave 2 of the build plan cannot start | H | H | 9 | TISPH Project Manager | Decision log (5.2) with owner and date per decision; default proposals already written in the design notes; weekly decision review; Steering Committee escalation after one missed date | 5.2; GQ-04 |
| R-02 | Remittance questions Q1 to Q20 (approvers and limits, Metrobank layouts, insurer contacts and SOA formats, settlement basis, GL accounts) stay open, so remittance phases R1 to R4 slip and go-live runs on the current remittance screens | H | H | 9 | Unit Head, Finance and General Accounting | Answer Q1, Q13 before R1; Q2, Q10, Q11, Q12, Q14, Q15, Q19, Q20 before R2; until then batching disabled and cheque used as the specification provides | GP-13, GP-14 |
| R-03 | Interface specifications are late: TFS file layout (INTG-03), bank layouts and SFTP pick-up, SAP transfer method (INTG-04) | H | H | 9 | TISPH Head of IT | Agree owners and dates per interface; manual upload screens remain available as fallback; interface tests on SIT before Gate 1 | GP-21 to GP-23; Architecture Q1 to Q4 |
| R-04 | BIR EIS enrolment and certification timetable not known; EIS cannot go live with the BIR signing method | M | H | 6 | Unit Head, Finance and General Accounting | Enrolment plan with TISPH tax adviser; the EIS outbox supports manual upload fallback (SUPPORT_AND_ESCALATION.md section 6) | GP-24; Architecture Q5 |
| R-05 | Open development streams (build plan gates G1 to G8) merge late or conflict, causing regressions in shared files | M | H | 6 | iorta TechNXT Solution Architect | Fixed merge order (build plan section 4); integration branches with full back-end, front-end, menu and help suites green before TISPH-DEV; CI gate on SIT, UAT and production | ADR-07 |
| R-06 | Volume of planned work (build plan about 285 developer days with contingency; remittance specification 140 person-days) does not fit the SOW timeline, which the BRD states is not extended by clarification (BRD 1.2) | M | H | 6 | iorta TechNXT Engagement Director | Classify each planned item as needed for go-live or after (GQ-02); squads per build plan section 5; scope changes only through BRD 8 | GQ-02 |
| R-07 | Performance targets of NFR-07 family and NFR-12 not evidenced at production sizing | M | H | 6 | iorta TechNXT Solution Architect | Performance and stress test on UAT with production sizing and a volume-loaded masked database before Gate 3 | GP-15; NFR Q2 |
| R-08 | Disaster recovery not rehearsed, so RPO 1 hour and RTO 4 hours (NFR-06.2, NFR-06.3) are unproven at go-live | M | H | 6 | TISPH Head of IT | DR drill on UAT and geo-restore rehearsal before Gate 3 (deploy/AZURE.md section 12) | GP-16 |
| R-09 | Ten-year database backup retention (NFR-11) is not met by the 35-day point-in-time window | H | M | 6 | TISPH Head of IT | Decide method (vault long-term retention or monthly export to immutable storage); add before first anniversary of go-live at the latest | Not built; NFR Q7 |
| R-10 | Security testing (VA, MBSS, penetration test) finds issues late in the plan | M | H | 6 | TISPH Head, Risk Management | Run scans on UAT through Front Door as soon as UAT is deployed; fix window reserved before Gate 3 | GP-17 |
| R-11 | Azure environments not yet provisioned and privileged role holders not named (Key Vault administrators, operator addresses, alert mailbox, release approvers) | M | H | 6 | TISPH Head of IT | Name holders (Architecture Q10, Security SEC-Q7); first deployment of DEV and SIT with iorta TechNXT DevOps following deploy/AZURE.md sections 1 to 9 | Readiness A-01 |
| R-12 | Migration scope unconfirmed (masters only, or open business as well) and legacy data quality unknown | M | H | 6 | Business Process Owner, Operations | Confirm scope (Data Migration Q1); Mock 1 and Mock 2 with the migration kit; reconciliation sign-off per data owner | Data Migration Q1, Q2 |
| R-13 | No permanent PRE-PROD on Azure, so the dress rehearsal and major-release rehearsals run on UAT | M | M | 4 | TISPH Head of IT | Decide E1; until then run the go-live rehearsal on a UAT restore | GP-01 |
| R-14 | Configuration drifts between UAT and production while the Environment Promotion module is not built | M | M | 4 | TIS IT AppSupport / Admin | Configuration workbook and compare:environments (exit code 0 means mirrored) before every production change; W0-4 stops environment-bound settings travelling with the workbook | GP-02, GP-05 |
| R-15 | Segregation of duties weakened: fewer than two eligible approvers in small teams; SUPERID left active; the one delivered TISPH SoD rule (CCD-BP with CCD-Recon) only warns; CCD-BP can cancel receipts through write:receipts although its role description says "no reversals" | M | H | 6 | TISPH Head, Risk Management | Readiness checks C-05 to C-08 and C-11 (section 7); at least two approvers per approval type; decide whether the rule blocks and whether receipt cancellation needs its own permission (GQ-15); Audit Trail review of receipt cancellations in hypercare | ADR-10; GQ-15 |
| R-16 | Sign-in controls of NFR-03 (3-minute idle time-out, 15-minute automatic unlock, single session) disrupt finance work or are only partly met. As built: idle time-out is a setting (default 30 minutes; deploy/AZURE.md section 13 recommends 3); lockout after five failures applies to password sign-in and is cleared by an administrator; Microsoft sign-in lockout is Entra ID's | M | M | 4 | TISPH Head of IT | Confirm settings (NFR Q9); automatic unlock and single session once decided | Not built; NFR Q9 |
| R-17 | Auditors require a technically immutable audit trail; the audit trail is protected by permissions, not by append-only storage | L | H | 3 | TISPH Head, Risk Management | Decide requirement (NFR Q19); minimal remedy is revoking update and delete on audit_log from the application role | Not built; ADR-15 |
| R-18 | Data scope by office and department (BRD 5.14) is required in Phase 1; the build scopes by own book | M | M | 4 | Business Process Owners | Confirm roles needing branch or department scope (Data Q10); extension of lib/scope.js | Not built; Data Q10 |
| R-19 | Access tokens kept in browser local storage do not satisfy TISPH security policy | L | M | 2 | TISPH Head, Risk Management | Strict content security policy in place; secure-cookie sessions as a later change if required (SEC-Q2) | Not built; SEC-Q2 |
| R-20 | Users resist enforced controls (maker-checker, masked identifiers, Microsoft sign-in, CCD-only receipting) and keep shadow spreadsheets | M | H | 6 | TISPH Project Sponsor | Change plan (section 10.5), key users per team, adoption measures (section 11.6), legacy set to read-only after cutover | Section 10, 11 |
| R-21 | Training uses the base user manual whose role chapters name the generic broker roles until the TISPH edition is built | H | M | 6 | iorta TechNXT Project Manager | Persona training scripts mapped to the TISPH roles (section 11.3); MAN-A before training starts, MAN-B before go-live | GP-12 |
| R-22 | Knowledge held by few people; TISPH IT cannot support or change the platform over ten years | M | H | 6 | TISPH Head of IT | Developer guide, module guide, ADR log, generated API documentation; shadowing during hypercare; handover certificate; source code escrow (template in the contract pack) | Section 12 |
| R-23 | Technology end of life during the platform's life: Node.js 22 (end of maintenance April 2027), PostgreSQL 16 (end of support November 2028), the React build tool react-scripts 5 (no longer developed by its maintainers), Express 4 | H | M | 6 | TISPH Head of IT | Lifecycle plan (section 12.2); upgrades as normal releases through the pipeline; full test suites as regression net | Section 12.2 |
| R-24 | Loss of the personal identifier key or data encryption key makes identifiers unreadable after a restore or regional failover | L | H | 3 | TISPH Head of IT | Offline backup of the three production keys with the DR documents (deploy/AZURE.md section 12); key rotation procedure (npm run pii:rotate); old key kept with older backups | ADR-11 |
| R-25 | Entra ID client secret expires (24 months) and Microsoft sign-in stops | M | M | 4 | TIS IT AppSupport / Admin | Expiry in the operations calendar; break-glass password route for System Administrator (security.password_sign_in_roles) | ADR-12 |
| R-26 | Pipeline platform (GitHub Actions as built, or Azure DevOps) and repository ownership not settled. The repository also carries the product's own EC2 and Railway workflows (ci.yml calling deploy.yml, and rollback.yml), which deploy to GitHub environments named dev, sit, uat, preprod and production when those are configured | M | M | 4 | TISPH Head of IT | Decide E4; images, Terraform and scripts are pipeline-neutral; repository ownership agreed in the support contract; for TISPH configure only the azure-* environments | GP-06; Environment Q4; GQ-14 |
| R-27 | API rate-limit counters are per replica, so the allowance doubles with two replicas | L | L | 1 | iorta TechNXT Solution Architect | Front Door limit on /api/auth/ applies across replicas (SEC-Q3) | Architecture section 13 |
| R-28 | Scheduled jobs run inside user-facing API replicas and compete for capacity at month-end | L | M | 2 | iorta TechNXT Solution Architect | Advisory locks prevent double runs; SCHEDULER_ENABLED=false allows a dedicated job instance (Architecture Q11) | ADR-05 |
| R-29 | The applicability of foreign regimes and certifications named in NFR-17.x is disputed at acceptance | M | M | 4 | TISPH Head, Risk Management | Agree applicable regimes and vendor certifications (NFR Q12) before Gate 2 | NFR Q12 |
| R-30 | Support model, hours and targets (NFR-13 family) not agreed before go-live | M | H | 6 | TISPH Project Manager | Support agreement (DA-4) as a Gate 3 entry criterion; targets in SUPPORT_AND_ESCALATION.md are a starting proposal | GP-18 |
| R-31 | Azure Container Apps not accepted as meeting NFR-19 ("orchestration via Kubernetes") | L | M | 2 | TISPH Head of IT | ADR-06 rationale; images portable to AKS; Helm chart only if TISPH decides to standardise on AKS | GP-20 |
| R-32 | Personal data used in mock migrations or UAT without approval | L | H | 3 | TISPH Data Protection Officer | DPO approval per refresh; masking tool refuses a database marked production and verifies the copy (backend/scripts/mask-data.js) | ADR-13; Data Migration Q9 |
| R-33 | Control switches are ordinary settings that one administrator (System Administrator or TIS IT AppSupport / Admin, both holding write:settings) can change on Master > Configuration without a second approval: finance.maker_checker_enabled, accounting.configuration_maker_checker, access.sod_enforced, access.authority_without_limit, privacy.masking_enabled, golive.locked. Each change is in the Audit Trail with before and after values | M | H | 6 | TISPH Head, Risk Management | Baseline of control settings signed at go-live (C-12); weekly Audit Trail review of entities settings and system-settings; second-administrator approval for these settings is Not built (SEC-Q12) | Not built; SEC-Q12 |
| R-34 | The audit entry is written after the business transaction commits, as a separate insert; an interruption between the two (for example a lost database connection) leaves a committed change without its audit entry | L | M | 2 | iorta TechNXT Solution Architect | Decide with NFR Q19; moving the audit insert into the business transaction is a code change across the modules | Not built; ADR-15; NFR Q19 |

Diagram 3: Risk position at baseline (likelihood vs impact)

Positions are on a scale of 0 to 1 (Low likelihood to High likelihood; Low impact to High impact).

| Item | Likelihood (0-1) | Impact (0-1) | Quadrant |
| --- | --- | --- | --- |
| R-01 decisions | 0.90 | 0.90 | Steering Committee |
| R-03 interfaces | 0.86 | 0.88 | Steering Committee |
| R-02 remittance | 0.88 | 0.85 | Steering Committee |
| R-06 capacity | 0.55 | 0.85 | Steering Committee |
| R-09 backups | 0.85 | 0.55 | Steering Committee |
| R-08 DR | 0.52 | 0.82 | Steering Committee |
| R-23 lifecycle | 0.82 | 0.52 | Steering Committee |
| R-07 performance | 0.50 | 0.80 | Steering Committee |
| R-21 manual | 0.80 | 0.50 | Steering Committee |
| R-33 control switches | 0.50 | 0.78 | Steering Committee |
| R-17 audit | 0.20 | 0.80 | Watch impact |
| R-27 rate limit | 0.20 | 0.20 | Monitor |

## Decision log: open TISPH decisions

These decisions are taken by TISPH. Each blocks a work package or a go-live activity. The references are those of the build plan (section 8) and of the remittance specification (section 11).

| Ref | Decision | Blocks | Needed by | Decision owner (proposed) | Status |
| --- | --- | --- | --- | --- | --- |
| P1 | Personal data: full values always for permitted users (as built), or masked until asked, time-limited and recorded | PD-1b | Start of build wave 2 | Data Protection Officer | Open |
| P2 | Who may see full personal data; exports during a reveal; retention of access records | PD-1b | Start of build wave 2 | Data Protection Officer | Open |
| R1 to R4 | Risk details field lists (Group PA, Parcel, Credit Life Voluntary, CTPL), required stage, value lists, approver | RD-A | Start of build wave 2 | Business Process Owner, Operations | Open |
| R5, R6 | Free extra details; duplicates and masking of the loan account number | RD-A, RD-B | Build wave 2 | Business Process Owner, Operations | Open |
| R7, R14 | Covers and benefits of PA, Travel and Credit Life; deactivation of two unused motor templates | CB-1b | Build wave 2 | Business Process Owner, Sales | Open |
| M1, M2 | Masters needing a second person's approval; who uploads and approves per group | MU-A | Start of build wave 2 | Head of IT with Process Owners | Open |
| M5 | Conversion of the completed configuration sheets into the Setup Workbook by iorta TechNXT; TISPH sign-off from the report | MU-A | Build wave 2 | TISPH Project Manager | Open |
| M3, M6 to M10, M12 to M15 | Deactivation of missing records, volumes, file retention, default download, user upload in production, permissions, reference lists, language, referrer key, vendor code | MU-A, MU-B | Build wave 2 | Head of IT | Open |
| E1 | Environment ladder: separate SIT; permanent PRE-PROD; UAT straight to production | PR-1a, GP-01 | Start of build wave 2 | Head of IT | Open |
| E2 | Promotion menu for IT AppSupport; production approvers; business approvers for products and accounting | PR-1b | Build wave 2 | Head of IT | Open |
| E3, E4 | Change reference tool and format; Azure DevOps or GitHub Actions; may the pipeline apply configuration outside production | PR-1b, PR-2 | Build waves 2 and 3 | Head of IT | Open |
| E5 to E9 | Users, exchange rates, holiday calendar, referrer and payee bank accounts promoted or kept per environment; Finance re-approval of promoted accounting changes; template effective dates | ADP-1, PR-1b | Build wave 2 | Head of IT with Finance | Open |
| E10 to E15 | Emergency changes and realignment; retention; freeze windows; step-up method; signing key custody; verification cases and owner | PR-1a, PR-1b | Build wave 2 | Head of IT | Open |
| C1 to C13 | Copy of transactions: which transactions, exclusions, TFS loan fields, documents, referrers, statuses, default sections, user limits, template copy approval | CL-A, CL-B | Build wave 2 | Process Owners, Sales and Operations | Open |
| D1 to D14 | User manual: system name, document control, logo, role chapter names, SUPERID, owners of finance masters, sign-in for the manual, labels, access matrix recipients, operating rules, Help Desk contacts, formats, language | MAN-A (D1 to D4), MAN-B | Build waves 1 and 3 | TISPH Project Manager | Open |
| Remittance Q1, Q13 | Remittance makers, approvers and cash release; off-cycle reasons and who may run or import | Remittance R1 | Remittance phase 1 UAT | Unit Head, Finance and General Accounting | Open |
| Remittance Q2, Q10 to Q12, Q14, Q15, Q19, Q20 | Metrobank batch in or outside BrokerVerse; GL accounts; uncleared cheques; proof of payment; opening remittances; approver of bank batch; returned remittances; due date basis | Remittance R2 | Remittance phase 2 | Unit Head, Finance and General Accounting; Head, Cash Control | Open |
| Remittance Q3 to Q6 | Metrobank file and status layouts; insurer confirmations; insurer contacts and accounts; SOA layouts | Remittance R3 | Remittance phase 3 | Head, Cash Control | Open |
| Remittance Q7 to Q9, Q16 | Settlement basis; net payable formula and EWT rate; billing statement numbering; approver of rule changes | Remittance R4 | Remittance phase 4 | Unit Head, Finance and General Accounting | Open |
| Remittance Q17 | Should approvals without an authority limit be refused globally (access.authority_without_limit) | All approvals | Before go-live | Head, Risk Management | Open |
| Remittance Q18 | Phase and owner of the non-payment cancellation notice, service invoice issuance, Credit Life premium billing, remittance events in the SAP GL file | Planning | Planning | TISPH Project Manager | Open |
| SEC-Q12 | Should changes to security and control settings need a second administrator's approval, as authority limits already do | R-33 remedy (no work package yet) | Before go-live | Head, Risk Management | Open |
| GQ-15 | Should receipt cancellation be a permission separate from receipt issue, and should rule SOD-TIS-BP-RECON block | R-15 remedy (no work package yet) | Before UAT sign-off | Head, Cash Control with Head, Risk Management | Open |

# Architecture decision records

## How the ADR log is kept

Each record below describes a choice that the code at the baseline already embodies. Its status is Accepted (as built): the decision is implemented and in use, and TISPH's Design Authority is asked to confirm it (question GQ-10). A change of an accepted decision is made by a new record that supersedes it, never by editing the old one, so that the history stays readable for the support team. New records are numbered in sequence and stored with this document until a decision register exists in the repository.

| ADR | Title | Status |
| --- | --- | --- |
| ADR-01 | Modular monolith on one PostgreSQL database | Accepted (as built) |
| ADR-02 | Node.js API and React single-page application in two container images | Accepted (as built) |
| ADR-03 | Route registry as the single source of the API documentation | Accepted (as built) |
| ADR-04 | Forward-only, idempotent SQL migrations under a database lock | Accepted (as built) |
| ADR-05 | In-process scheduler and database outboxes instead of a message broker | Accepted (as built) |
| ADR-06 | Azure Container Apps rather than a self-managed Kubernetes cluster | Accepted (as built); TISPH confirmation pending (NFR-19) |
| ADR-07 | Build once, promote by image digest, with approvals and federated pipeline identity | Accepted (as built) |
| ADR-08 | Terraform as the only infrastructure-as-code tool | Accepted (as built); TISPH confirmation pending (NFR-19.1) |
| ADR-09 | Business rules held as configuration, with owners and maker-checker | Accepted (as built) |
| ADR-10 | Controls built into the platform: permissions, maker-checker, SoD rules, authority matrix | Accepted (as built) |
| ADR-11 | Field-level encryption of personal identifiers and masking by permission | Accepted (as built) |
| ADR-12 | Microsoft Entra ID sign-in with users provisioned in BrokerVerse | Accepted (as built) |
| ADR-13 | Environment marker in the database and masking of production copies | Accepted (as built) |
| ADR-14 | Go-live through workbooks over the API, transaction reset and go-live lock | Accepted (as built) |
| ADR-15 | Audit trail in the operational database, protected by permissions | Accepted (as built); tamper evidence open (NFR Q19) |
| ADR-16 | Client branding through a brand pack enforced by the deployment | Accepted (as built) |
| ADR-17 | File-based integrations through an outbox framework and SFTP storage | Accepted (as built); file transfer to SAP Planned (GP-21) |

## ADR-01 Modular monolith on one PostgreSQL database

- Context. TISPH is one broker with one ledger. A business event (for example a receipt) must change the business record, post the journal and queue any outgoing message together, or not at all. The platform must be operable by a small IT team for many years.

- Decision. One Node.js API process holds every business module. Each folder under backend/src/modules/ that has a router.js is mounted under /api at start-up (backend/src/app.js); there are 69 modules at the baseline. All modules share one PostgreSQL database and one transaction scope.

- Consequences. One transaction covers business change, journal and outgoing message (the outbox row is written in the module's transaction), which simplifies reconciliation and recovery. The audit entry is written just after that transaction commits (ADR-15, risk R-34). One backup and one restore cover everything. Modules cannot be scaled or released separately, and module boundaries are kept by convention and review (backend/docs/MODULE_GUIDE.md). A second legal entity with its own ledger needs its own deployment.

## ADR-02 Node.js API and React single-page application in two container images

- Context. The platform needs a staff web application, a few public pages and a documented API, packaged for Docker (NFR-19).

- Decision. The API is Node.js (engine 22 or later) with Express 4 and the pg driver; the front end is React 18 built with react-scripts 5 through craco, served by nginx. Two images are built: backend/Dockerfile (node:22-alpine, production dependencies only, runs as user node) and brokerverse/Dockerfile (React build with no environment values, then nginx:1.27-alpine). Environment-specific values reach the browser at run time through env-config.js.

- Consequences. One language across front and back end; one image of each kind serves every environment. The front-end build tool and the Node.js line must be upgraded during the platform's life (risk R-23, section 12.2).

## ADR-03 Route registry as the single source of the API documentation

- Context. BRD section 9.2 requires traceability, and support staff must find which route and table serve a screen. Hand-written API documentation drifts from the code.

- Decision. Every endpoint is declared through moduleRouter(...).define({ method, path, summary, screen, ... }) in backend/src/lib/registry.js, which records it in ROUTES. npm run export:api (backend/src/tools/export-api.js) generates the OpenAPI file, the Postman collection and the API touchpoint workbook in backend/docs/api/.

- Consequences. The documentation is generated from the routes, so it is correct as soon as it is regenerated; each route names its screen, which supports defect tracing (docs/developer-guide/backend.md). Every new route must use define(). Regenerating the export is part of the build plan's definition of done; CI does not check that the committed files in backend/docs/api/ are current, so a release can carry stale API files.

## ADR-04 Forward-only, idempotent SQL migrations under a database lock

- Context. Releases must be reversible at the application level without losing data, and several API instances may start together.

- Decision. Schema changes are numbered SQL files in backend/src/db/migrations/ (174 at the baseline), applied in name order by backend/src/db/migrate.js under a PostgreSQL advisory lock and recorded in schema_migrations. There are no down-migrations; removals follow expand-then-contract over two releases (deploy/RELEASE_PIPELINE.md section 8). The reference seed is re-applied on every start and is idempotent. In Azure, a Container Apps job runs the migrations with the new image before the apps switch.

- Consequences. The previous release still runs on the newer schema, so an application rollback is safe and needs no database restore. Removing a column takes two releases. A migration file is never edited once it has left DEV; a correction is a new file.

## ADR-05 In-process scheduler and database outboxes instead of a message broker

- Context. The platform runs scheduled jobs (13 in backend/src/db/seeds/jobs.json, more added by later migrations, for example the SAP GL export of 0347_sap_gl_export.sql) and sends e-mail, SMS and integration messages. Volumes are those of one broker.

- Decision. Jobs run inside the API process (backend/src/jobs/scheduler.js); each run takes a PostgreSQL advisory lock keyed on the job code, so a job never runs twice at the same time across replicas. Outgoing messages are rows in outbox tables, picked with FOR UPDATE SKIP LOCKED (backend/src/modules/integrations/framework/outbox.js) and retried independently.

- Consequences. No extra infrastructure to operate, back up or secure; messages are restored with the data. The throughput of asynchronous work is bounded by job intervals and the one database. Jobs share capacity with user requests: Terraform sets SCHEDULER_ENABLED=true on the API app, and no dedicated job instance is defined; one can be added by setting SCHEDULER_ENABLED=false on the user-facing replicas (risk R-28, Architecture Q11).

## ADR-06 Azure Container Apps rather than a self-managed Kubernetes cluster

- Context. NFR-06.1 prefers Azure; NFR-19 asks for Docker and orchestration via Kubernetes. The workload is two stateless containers, an in-process scheduler and a one-shot migration job.

- Decision. Azure Container Apps, defined in deploy/azure/modules/environment/containerapps.tf, with managed ingress, revisions, scale rules, Key Vault references and zone redundancy in production. The reasoning is recorded in deploy/AZURE.md ("Why Container Apps and not AKS").

- Consequences. No cluster to patch, upgrade or staff. The images, probes (/api/health, /api/health/live), graceful shutdown and configuration are Kubernetes-ready, so a move to AKS keeps them unchanged. Kubernetes manifests or a Helm chart are not maintained (Planned only if TISPH decides to standardise on AKS, GP-20). TISPH acceptance against NFR-19 is open (risk R-31).

## ADR-07 Build once, promote by image digest, with approvals and federated pipeline identity

- Context. What was tested must be exactly what runs in production, and each production change must be approved and evidenced (NFR-8.2).

- Decision. A push to TISPH-DEV builds the API and web images once and pushes them to the shared Azure Container Registry; DEV, SIT, UAT and production run the same digests (.github/workflows/azure-deploy.yml). SIT, UAT and production wait for required reviewers on their GitHub environments and refuse a commit whose CI run (ci.yml: lint, back-end tests on PostgreSQL 16, front-end tests and build, dependency audit) did not pass. Each environment job signs in to Azure with OpenID Connect trusted only for its own GitHub environment; no Azure secret is stored in GitHub. A failed smoke test (deploy/smoke-test.sh) restores the previous images automatically; a run in rollback mode redeploys an earlier commit's images without migrations (.github/workflows/azure-deploy-environment.yml).

- Consequences. Environment differences must be variables, secrets or settings only. DEV receives a build as soon as the images are pushed, before the CI result is known; the CI gate applies from SIT onwards. Required reviewers and the TISPH-DEV branch restriction are GitHub settings, not code, and must be set by the repository owner (readiness B-01). The approval and run history in GitHub is the deployment evidence for auditors; its retention and the change reference to record on each production deployment depend on decisions E3 and E4 (GP-06). CI artefacts are kept 90 days (ci.yml).

## ADR-08 Terraform as the only infrastructure-as-code tool

- Context. NFR-19.1 names Terraform and Ansible for automated provisioning. The Azure design has no virtual machines to configure.

- Decision. All Azure resources are Terraform: deploy/azure/bootstrap (state storage), shared (container registry), environment with modules/environment (network, Container Apps, PostgreSQL 16 Flexible Server, Azure Files, Key Vault, Front Door with WAF, SFTP storage, Log Analytics, Application Insights, alerts, federated identity) and one tfvars file per environment (dev, sit, uat, prod). Ansible is not used.

- Consequences. Every environment is rebuilt from code, which is also the regional disaster recovery method (deploy/AZURE.md section 12). Whether Terraform alone is acceptable against NFR-19.1, and whether plans run in the pipeline, are open (Environment Strategy Q6, Q7).

## ADR-09 Business rules held as configuration, with owners and maker-checker

- Context. TISPH must change rates, limits, templates, numbering and texts without a release (NFR-08.1), and changes affecting money must be controlled.

- Decision. Business parameters are settings in app_settings read through backend/src/lib/settings.js, masters, posting rules, product templates, authority limits, document numbering series and file layouts, maintained on screens. Settings that belong to a dedicated screen can only be changed there (backend/src/lib/settingOwners.js). Posting rule and account determination changes go through the configuration approvals of migration 0174_configuration_controls.sql while accounting.configuration_maker_checker is on (the default); the approver must then differ from the maker whatever finance.maker_checker_enabled says (backend/src/modules/posting-rules/service.js).

- Consequences. Change without release, with audit evidence. Configuration needs its own promotion between environments: today the configuration workbook and environment comparison; the Environment Promotion module is Planned (GP-05). npm run check:settings reports settings read in code but created by no migration or seed, and the back-end suite runs it. The control settings themselves can be switched by one administrator (risk R-33).

## ADR-10 Controls built into the platform: permissions, maker-checker, SoD rules, authority matrix

- Context. BRD 4.2 states that the person who raises a transaction can never approve it; BRD 5.14 requires role-based rights per screen, segregation of duties across modules and an audit trail.

- Decision. Permissions are checked on every route; assertChecker (backend/src/lib/makerChecker.js) refuses an approval by the maker; segregation-of-duties rules are data (sod_rules, migration 0193_access_control.sql) checked when roles are given to a user, on the user screen and in the configuration workbook; a rule either blocks or warns, and the check as a whole follows access.sod_enforced (modules/access-control/service.js, assertSod); authority limits are proposed and approved by a second administrator (modules/access-control/service.js). The TISPH roles and their permissions are delivered by migration 0348_tisph_roles.sql.

- Consequences. Controls are enforced in the API, so they hold for every screen and integration, and their behaviour is covered by the automated test suite. Small teams need at least two eligible users per approval type. The switches are settings: finance.maker_checker_enabled (posting rules excepted), access.sod_enforced and access.authority_without_limit (default allow) must be set as agreed and watched (readiness C-06, C-12; risk R-33). For TISPH only one SoD rule is delivered and it warns (section 3.2). Access reviews, the User Matrix with SoD conflicts and last sign-in, delegations and automatic deactivation of dormant accounts (access.dormant_days, default 90, job dormant-users) support periodic review. Scope by office and department is Not built (Data Q10).

## ADR-11 Field-level encryption of personal identifiers and masking by permission

- Context. NFR-01 and NFR-17 require protection of non-public personal information; the Data Privacy Act applies.

- Decision. Personal identifiers are encrypted at rest in the application with AES-256 using PII_ENCRYPTION_KEY (backend/src/lib/pii.js, migration 0277_personal_identifier_encryption.sql), with blind indexes for searching. Users without the permission view:pii see masked values (backend/src/lib/piiPolicy.js). The key is rotated with npm run pii:rotate (backend/scripts/rotate-pii-key.js). The production start-up check refuses missing, weak or equal keys (backend/src/config.js).

- Consequences. A database copy without the key does not expose identifiers. Losing the key makes identifiers unreadable, so keys are kept in Key Vault with an offline backup (risk R-24). A mode in which permitted users see masked values until they switch on "Show full identifiers" exists (privacy.pii_reveal_mode = on-request, each unmasked request audited); TISPH is delivered in mode always. Masking of write answers and of the current-data workbooks, and a time-limited reveal, are Planned (GP-07, GP-08).

## ADR-12 Microsoft Entra ID sign-in with users provisioned in BrokerVerse

- Context. INTG-02 requires single sign-on with Microsoft; NFR-04 requires MFA; roles must stay under BrokerVerse's own controls.

- Decision. Staff sign in with OpenID Connect (authorisation code with PKCE); the API validates the ID token and matches the account to an existing BrokerVerse user (backend/src/lib/entraId.js). Users are not created by the sign-in; security.sso_register_users stays off in production. MFA is enforced by TISPH's Conditional Access policy. Password sign-in can be switched off for everyone except the roles in security.password_sign_in_roles, which keep a break-glass route (deploy/AZURE.md section 14).

- Consequences. Joiners and leavers are controlled in two places: the Entra ID group assignment and Master > User Management. The client secret expires (24 months) and must be renewed (risk R-25).

## ADR-13 Environment marker in the database and masking of production copies

- Context. Non-production environments may be refreshed from production copies; personal data must not leave production unmasked, and an environment must know what it is.

- Decision. The setting system.environment (migration 0249_system_environment.sql, backend/src/lib/environment.js) records which environment a database serves. The masking tool npm run mask:data (backend/scripts/mask-data.js) refuses a database marked production, masks every catalogued personal data column with deterministic pseudonyms, disables e-mail sending, sets the marker and verifies the result (docs/onboarding/DATA_MASKING.md).

- Consequences. A masked copy keeps joins and searches working. Today the configuration workbook can carry the marker between environments; work package W0-4 stops that (Planned, GP-02). mask:data can record where production lives (system.production_identity) so that a restored copy is told apart from production; a check that blocks work when the deployment's environment name and the database marker differ is Planned with PR-1a.

## ADR-14 Go-live through workbooks over the API, transaction reset and go-live lock

- Context. Configuration and the open book must be loaded reproducibly, validated before loading, reconciled, and protected once production is live.

- Decision. The Go-Live Data Workbench (backend/src/modules/data-load/) offers a configuration workbook and a migration workbook, validated row by row before any load, loaded in one transaction and compared between environments (npm run compare:environments). After a smoke test, npm run reset:transactions removes business records and keeps masters, configuration and users; it refuses to run once golive.locked is on (backend/src/lib/goLiveLock.js), and the lock also refuses the migration workbook. The whole sequence is rehearsed by npm run rehearsal:golive (backend/scripts/golive-rehearsal.js).

- Consequences. The go-live is repeatable and evidenced (rehearsal: 52 checks passed on local environments). The lock is a setting that an administrator can switch off; doing so is audited and must be controlled (readiness item E-09).

## ADR-15 Audit trail in the operational database, protected by permissions

- Context. BRD 5.14 requires every create, update and workflow transition with actor, time, before and after values and remark.

- Decision. Audit entries are written by backend/src/lib/audit.js into audit_log with the channel (screen, API or job) and request context. Handlers call it after their business transaction has committed, so the entry is a separate insert (it joins a transaction only when the caller runs inside one, as the go-live workbench does). The history of a record is shown to holders of read:audit and to users who may read or write that record's module (backend/src/modules/audit/router.js). A hash-chained or append-only audit table was considered and left out because it conflicts with the personal data maintenance of migration 0277 (remittance specification decision D9).

- Consequences. The audit trail is restored together with the data it describes. A failure between commit and audit insert can leave a change without its entry (risk R-34). It is not technically immutable against a database administrator; whether auditors require that is open (NFR Q19, risk R-17).

## ADR-16 Client branding through a brand pack enforced by the deployment

- Context. The same product serves several brokers; the TISPH deployment must always show TISPH's identity and never another client's.

- Decision. Brand packs are shipped with the product (docs/package/04_Onboarding_and_Go_Live/Brand_Packs/); a deployment names its pack in BRAND_PACK (backend/src/config.js), and the API applies it at every start (backend/src/modules/branding/bundled.js). The TISPH environments use toyota-insurance-services.

- Consequences. A restart restores the brand if it was changed on screen. A client brand pack is used only in that client's environments under its contract (SUPPORT_AND_ESCALATION.md section 6).

## ADR-17 File-based integrations through an outbox framework and SFTP storage

- Context. BRD 5.13 states that the Phase 1 interfaces are file-based or e-mail-based; insurer REST integration is held for a later phase. Partners (SAP, banks, TFS) must exchange files without reaching the application network.

- Decision. Outgoing and incoming messages go through the integration framework (backend/src/modules/integrations/framework/): a module queues a message in its own transaction with an idempotency key; the outbox sends it through the connector's adapter with exponential back-off until a maximum number of attempts, then marks it failed for resend from the monitor; inbound files and messages are stored in an inbox and can be reprocessed. Each connector is enabled and switched to live separately. On Azure, an SFTP storage account per environment (deploy/azure/modules/environment/sftp.tf) has the containers sap-outbound, bank-inbound and bank-outbound, key-only partner users and an address allow-list; the API reaches it through a private endpoint with its managed identity. The SAP GL files are written daily to the documents share.

- Consequences. No partner calls the API, which keeps the attack surface small; messages and files are backed up with the data. The copy of the SAP GL files from the documents share to sap-outbound is not built (Planned, GP-21; deploy/AZURE.md section 11); bank files are moved by hand until GP-22.

# Production readiness checklist

Status at the baseline: Built (the capability exists in the code or infrastructure definitions; the item is to be verified in the TISPH environment), To do (an activity with existing tools), Planned (depends on a work package or decision), Decision (waiting for TISPH), Not built (gap without a work package). Each item is signed by its owner at checkpoint 1 or, for cutover items, at C-9.

## A. Infrastructure and environments

| # | Item | Evidence / how verified | Status | Owner |
| --- | --- | --- | --- | --- |
| A-01 | DEV, SIT, UAT and PROD provisioned from Terraform in TISPH's subscription | Terraform apply output; deploy/AZURE.md sections 1 to 4 | Built (definitions); provisioning To do | TISPH Head of IT, iorta TechNXT DevOps lead |
| A-02 | PRE-PROD for the dress rehearsal | Decision E1 | Planned (GP-01) | TISPH Head of IT |
| A-03 | Production sizing: two or more API and web replicas, zone-redundant PostgreSQL with standby, GZRS documents, WAF in Prevention | prod.tfvars; Architecture document 12.3 | Built | iorta TechNXT DevOps lead |
| A-04 | Custom domain and TLS on Front Door; certificate expiry alert | deploy/AZURE.md section 8, section 15 | Built (definitions); domain To do | TISPH Head of IT |
| A-05 | Key Vault holds generated secrets; administrators named; offline backup of the three production keys | deploy/AZURE.md sections 6, 12 | Built; holders Decision (Architecture Q10) | TISPH Head of IT |
| A-06 | Production start-up check passes (secrets set, not placeholders, at least 32 characters and different from each other; CORS origins listed, not *; public address set; Entra ID variables either all set or none) | API starts in production mode; backend/src/config.js | Built | iorta TechNXT DevOps lead |
| A-07 | Sample data off (SEED_SAMPLE_DATA=false) in every Azure environment | tfvars; GET /api/version, data counts | Built | iorta TechNXT DevOps lead |

## B. Release and change control

| # | Item | Evidence / how verified | Status | Owner |
| --- | --- | --- | --- | --- |
| B-01 | Required reviewers on azure-sit, azure-uat, azure-prod; production: TISPH IT and the business owner; deployment branches limited to TISPH-DEV | GitHub environment settings; deploy/AZURE.md section 9 | Pipeline built; environment protection To do (GitHub settings, not code); reviewers Decision (GQ-05) | TISPH Head of IT |
| B-02 | Release commit has a green CI run; production deploys the digests tested in UAT | Run summary of azure-deploy.yml | Built | iorta TechNXT DevOps lead |
| B-03 | Smoke test and automatic rollback proven once in UAT | Run with a deliberate failed smoke test | To do | iorta TechNXT DevOps lead |
| B-04 | Manual rollback to an earlier commit proven in UAT (mode: rollback) | Run record | To do | iorta TechNXT DevOps lead |
| B-05 | Change reference recorded for each production deployment | Decision E3 | Planned (GP-06) | TISPH Head of IT |
| B-06 | Security scanning in CI (static analysis, image scanning, secret scanning) | ci.yml has dependency audit only | Not built (Environment Q5, SEC-Q13) | TISPH Head, Risk Management |
| B-07 | Release notes and version identity agreed for production releases | Template docs/package/06_Support/BrokerVerse_Release_Notes_Template.docx | To do (Environment Q8) | iorta TechNXT Project Manager |

## C. Security and access

| # | Item | Evidence / how verified | Status | Owner |
| --- | --- | --- | --- | --- |
| C-01 | Entra ID app registration per environment; assignment required; Conditional Access MFA | deploy/AZURE.md section 14 | Built (code); tenant set-up To do | TISPH Head of IT |
| C-02 | Password sign-in off except break-glass roles; break-glass account with long password and two-factor | Master > Configuration; sign-in history | To do | TIS IT AppSupport / Admin |
| C-03 | Sign-in protection settings agreed and set (limits.max_login_attempts 5; limits.session_idle_minutes, delivered as 30 and recommended as 3 for NFR-03; rate limits) | Master > Configuration export | To do; automatic unlock and single session Not built (NFR Q9) | TISPH Head of IT |
| C-04 | Production users loaded with TISPH roles; every user signed in once; demo accounts disabled | User list; sign-in history (GET /users/:id/login-history) | To do | TIS IT AppSupport / Admin |
| C-05 | SUPERID role set Inactive and no user holds it | Master > User Management > Role | To do | TIS IT AppSupport / Admin |
| C-06 | finance.maker_checker_enabled, accounting.configuration_maker_checker and access.sod_enforced on; SoD rules reviewed against the TISPH personas, including whether SOD-TIS-BP-RECON blocks and who may cancel receipts (GQ-15) | Configuration export; Access Control > Segregation of Duties | To do | TISPH Head, Risk Management |
| C-07 | At least two eligible approvers per approval type; authority limits approved by a second administrator | Authority Matrix; user list | To do | Business Process Owners |
| C-08 | system-admin held only by named administrators | Role report | To do | TISPH Head of IT |
| C-09 | VA and MBSS scans on UAT through Front Door; penetration test; findings closed or accepted | Scan reports | Planned (GP-17) | TISPH Head, Risk Management |
| C-10 | WAF exclusions tuned in SIT; production in Prevention | Front Door WAF log review | To do | iorta TechNXT DevOps lead |
| C-11 | Access review run on production users before go-live; User Matrix shows no blocking SoD conflict | Access Control > Access Reviews (closed review, downloadable); User Matrix export | Built (function); run To do | TISPH Head, Risk Management |
| C-12 | Baseline of the control settings of risk R-33 signed; weekly Audit Trail review of setting changes set up | Signed configuration export; review log | To do; second approval of these settings Not built (SEC-Q12) | TISPH Head, Risk Management |
| C-13 | Dormant-account period agreed (access.dormant_days, delivered 90) and job dormant-users switched on | Master > Schedules | To do | TIS IT AppSupport / Admin |
| C-14 | Accounts of iorta TechNXT staff in production named, time-limited and listed for deactivation at hypercare exit | User list; Data Migration Q18 | Decision | TISPH Head of IT |

## D. Data protection

| # | Item | Evidence / how verified | Status | Owner |
| --- | --- | --- | --- | --- |
| D-01 | Personal data decisions P1 and P2 taken | Decision log | Decision | Data Protection Officer |
| D-02 | Masking of write answers and current-data workbooks | Work package PD-1a | Planned (GP-07) | iorta TechNXT Solution Architect |
| D-03 | DPO approval for any production copy in non-production; copies masked and verified (exit code 0) | npm run mask:data report | Built (tool); approvals To do | Data Protection Officer |
| D-04 | Encryption key custody and rotation procedure accepted | deploy/REFERENCE.md; rotate-pii-key.js | Built | TISPH Head of IT |

## E. Data, configuration and migration

| # | Item | Evidence / how verified | Status | Owner |
| --- | --- | --- | --- | --- |
| E-01 | Configuration loaded in production from the accepted UAT configuration | Configuration workbook batch records | To do | TIS IT AppSupport / Admin |
| E-02 | UAT and production mirrored apart from environment-specific values | compare:environments exit code 0; comparison workbook | Built (tool); run To do | TIS IT AppSupport / Admin |
| E-03 | Environment-bound settings not carried by the workbook | Work package W0-4 | Planned (GP-02) | iorta TechNXT Solution Architect |
| E-04 | Company, letterhead, brand pack toyota-insurance-services, document numbering above legacy numbers, official receipt series per BIR registration | Numbering export; test PDF | To do | Unit Head, Finance and General Accounting |
| E-05 | Fiscal year and periods; periods before cutover closed; bank accounts' reconcile-from date | Period screens | To do | Unit Head, Finance and General Accounting |
| E-06 | Mock 1, Mock 2 and dress rehearsal reconciled and signed | Data Migration document section 11 | To do | Business Process Owners |
| E-07 | Smoke test in production followed by transaction reset (dry run, then execute) | reset:transactions report | Built (tool); run To do | iorta TechNXT DevOps lead |
| E-08 | Migration loaded and reconciled; Go/No-Go migration criteria met | Reconciliation workbook | To do | Unit Head, Finance and General Accounting |
| E-09 | golive.locked switched on after the Go decision; who may switch it off agreed | Audit entry of the setting change | Built; control To do | TISPH Head of IT |
| E-10 | Remittance go-live clean-up and opening remittances | Remittance R2 | Planned (GP-14) | Unit Head, Finance and General Accounting |

## F. Integrations

| # | Item | Evidence / how verified | Status | Owner |
| --- | --- | --- | --- | --- |
| F-01 | E-mail through TISPH's authenticated SMTP (INTG-01); password reset e-mail received | deploy/AZURE.md section 7 | Built; test To do | TISPH Head of IT |
| F-02 | SAP GL daily files produced and delivered (INTG-04) | sap-gl module; transfer decision | Built (files); transfer Planned (GP-21) | Unit Head, Finance and General Accounting |
| F-03 | Bank files and statements per bank in use at go-live | Bank layouts; SFTP | Built (manual); automation Planned (GP-22) | Head, Cash Control |
| F-04 | TFS intake (INTG-03) | TFS specification | Planned (GP-23) | TISPH Head of IT |
| F-05 | BIR EIS operating mode at go-live | Enrolment status | Planned (GP-24) | Unit Head, Finance and General Accounting |
| F-06 | Integration connectors Enabled and Live where intended; credentials in Key Vault only | Master > System Configuration > Integrations | To do | TIS IT AppSupport / Admin |
| F-07 | Scheduled jobs reviewed and switched on as agreed; owners notified on failure | Master > Schedules run history | To do | TIS IT AppSupport / Admin |

## G. Operations, monitoring, backup and recovery

| # | Item | Evidence / how verified | Status | Owner |
| --- | --- | --- | --- | --- |
| G-01 | Availability test every 5 minutes from five locations; alert mailbox monitored | Application Insights; monitoring.tf | Built; mailbox Decision (Architecture Q10) | TISPH Head of IT |
| G-02 | Logs in Log Analytics with request id; support staff can query them | deploy/AZURE.md section 15; developer guide section 6 | Built | TIS IT AppSupport / Admin |
| G-03 | API error-rate and latency alerts; operations workbook | NFR document section 9 | Not built (NFR Q13) | iorta TechNXT DevOps lead |
| G-04 | Point-in-time restore tested; documents restore tested | DR drill record | Planned (GP-16) | TISPH Head of IT |
| G-05 | Geo-restore rehearsal for production | DR drill record | Planned (GP-16) | TISPH Head of IT |
| G-06 | Ten-year backup retention method in place | NFR-11 | Not built (NFR Q7) | TISPH Head of IT |
| G-07 | Performance and stress test passed at production sizing | Test report | Planned (GP-15) | iorta TechNXT Solution Architect |
| G-08 | Means of producing the yearly cloud security posture report (NFR-17.4) agreed; Microsoft Defender for Cloud is not part of the Terraform | NFR Q13 | Not built (NFR Q13) | TISPH Head, Risk Management |

## H. Support, people and compliance

| # | Item | Evidence / how verified | Status | Owner |
| --- | --- | --- | --- | --- |
| H-01 | Support agreement: hours, channels, severity targets, Azure support plan | Signed agreement | Planned (GP-18) | TISPH Project Manager |
| H-02 | Hypercare roster, contacts and daily checklist in place | Section 9 | To do | iorta TechNXT Project Manager |
| H-03 | Every user trained and assessed for their persona; key user per team ready | Training records | To do | TISPH Project Manager |
| H-04 | TISPH edition of the manual and Help | MAN-A, MAN-B | Planned (GP-12) | iorta TechNXT Project Manager |
| H-05 | Communications sent to staff, insurers, banks, TFS | Communication log | To do | TISPH Project Sponsor |
| H-06 | UAT signed per area with traceability to BRD references (BRD 9.2) | UAT sign-off | To do | Business Process Owners |
| H-07 | Legacy system frozen and read-only plan agreed; retention custodian named | Data Migration Q11 | Decision | TISPH Head of IT |
| H-08 | Evidence archive location for go-live records agreed | Section 8.6 | Decision (GQ-13) | TISPH Project Manager |

# Go-live plan

## Approach

Go-live is a single cutover of the TISPH book into production over a weekend, followed by hypercare. The step-by-step cutover runbook (C-1 legacy freeze to C-10 production open), the data roles and the rollback points RB-1 to RB-4 are in the Data Migration document (sections 12 to 17) and are not repeated here. This section gives the plan around the cutover and the governance of the decision. The target go-live date is the one stipulated in the signed SOW (BRD 1.2); it is not restated here (question GQ-02).

## Timeline relative to go-live

| When | Activity | Owner | Gate |
| --- | --- | --- | --- |
| G-12 to G-8 weeks | UAT cycles on Azure UAT with TISPH personas; performance test; DR drill; VA and MBSS scans; training of key users | TISPH Project Manager, iorta TechNXT Project Manager | Gate 2 at the end |
| G-8 to G-6 weeks | Mock 2 with reconciliation; support agreement signed; production provisioned and smoke-tested; Entra ID production registration | Process Owners, TISPH Head of IT |  |
| G-6 to G-3 weeks | End-user training per persona; dress rehearsal with timings (on PRE-PROD if decided, otherwise a UAT restore) | TISPH Project Manager |  |
| G-2 weeks (C-10 business days) | Checkpoint 1: readiness checklist complete except cutover items | Steering Committee | Gate 3 |
| G-5 business days | Users loaded and first Microsoft sign-in tested; communications to staff, insurers, banks, TFS | TISPH Head of IT, Project Sponsor |  |
| G-3 business days | Numbering checked against legacy numbers and BIR registration | Finance Head, System Administrator |  |
| Cutover weekend | C-1 freeze to C-10 open, per the Data Migration document section 13.2 | Cutover team | Gate 4 at C-9 |
| Go-live day and first four weeks | Hypercare (section 9) | Hypercare lead | Gate 5 at exit |

Diagram 4

| No. | Step | Next |
| --- | --- | --- |
| 1 | UAT cycles, performance, DR drill, security scans | step 2 (Gate 2, UAT sign-off) |
| 2 | Decision: Gate 2, UAT sign-off | step 3 |
| 3 | Mock 2, dress rehearsal, end-user training, production smoke test | step 4 (Gate 3, Checkpoint 1) |
| 4 | Decision: Gate 3, Checkpoint 1 | step 5 (Final week: users, numbering, communications) |
| 5 | Final week: users, numbering, communications | step 6 (Cutover weekend, C-1 to C-8) |
| 6 | Cutover weekend, C-1 to C-8 | step 7 (Gate 4, Go/No-Go (C-9)) |
| 7 | Decision: Gate 4, Go/No-Go (C-9) | Go: step 8 (C-10 lock on, interfaces and jobs on) No-Go: step 9 (Rollback RB-1 / RB-2, legacy stays live) |
| 8 | C-10 lock on, interfaces and jobs on | step 10 (Hypercare) |
| 9 | Rollback RB-1 / RB-2, legacy stays live | End |
| 10 | Hypercare | End |

## Decision rights on the cutover weekend

| Decision | Who decides | Who must be consulted |
| --- | --- | --- |
| Start the legacy freeze (C-1) | TISPH Project Manager | Process Owners |
| Accept a reconciliation difference | Unit Head, Finance and General Accounting (in writing) | Migration lead |
| Waive a Go/No-Go criterion that may be waived | Project Sponsor (in writing) | Head of IT, Head of Risk Management |
| Go or No-Go | Steering Committee, chaired by the Project Sponsor | All workstream leads |
| Rollback after go-live (RB-3) | Steering Committee | Head of IT, Finance Head |
| Application release rollback (RB-4) | TISPH Head of IT on the advice of the iorta TechNXT DevOps lead | Project Manager |

## Go/No-Go criteria

The data criteria G1 to G11 of the Data Migration document (section 16) apply unchanged. The criteria below add the technical, security, operational and people conditions. Criteria marked No waiver cannot be waived; the others only by the Project Sponsor in writing.

| # | Criterion | Evidence | Waiver |
| --- | --- | --- | --- |
| GN-01 | UAT signed by every Business Process Owner; no open severity 1 or 2 defect; traceability from UAT test cases to BRD references | UAT sign-off; defect log | No waiver |
| GN-02 | Data criteria G1 to G11 of the Data Migration document met | Signed reconciliation, comparison workbook | G2 to G5 no waiver |
| GN-03 | Production deployed by digest from a green CI run; smoke test passed; rollback rehearsed in UAT (B-03, B-04) | Pipeline run summaries | No waiver |
| GN-04 | Readiness sections A, B, C and E complete, except items marked Planned or Not built that the Steering Committee has accepted to follow go-live (GQ-11) | Readiness checklist | Per item |
| GN-05 | Security scans run and every High finding closed or formally accepted by the Head of Risk Management | Scan report; acceptance record | No waiver for unaccepted High findings |
| GN-06 | DR drill done with achieved RPO and RTO recorded | DR drill record | Sponsor waiver with a dated plan |
| GN-07 | Performance test passed at the agreed load, or the shortfall accepted with a dated plan | Test report | Sponsor waiver |
| GN-08 | Support agreement in force; hypercare roster and contacts published; alert mailbox monitored | Agreement; roster | No waiver |
| GN-09 | Users trained and able to sign in; key user per team ready; SUPERID inactive; control settings at their signed baseline (C-06, C-12) | Training records; sign-in history; configuration export | No waiver for SUPERID or the control settings |
| GN-10 | Communications sent to staff, insurers, banks and TFS | Communication log | Sponsor waiver |
| GN-11 | Rollback team available; legacy system can be reopened until the end of the rollback window | Cutover log | No waiver |

A No-Go records the reason, the actions, their owners and the new date.

## Communications

| Audience | Message | Channel | When | Owner |
| --- | --- | --- | --- | --- |
| Steering Committee | Readiness, risks, decisions needed | Steering meeting | Weekly from G-4 weeks | TISPH Project Manager |
| All TISPH users | What changes, training dates, go-live date, where to get help (Help panel F1, key user) | E-mail from the Project Sponsor; team meetings | G-4 weeks, G-1 week, go-live day | TISPH Project Sponsor |
| Team leaders | Release of staff for training and UAT; key user role | Briefing | G-8 weeks | TISPH Project Manager |
| Insurers | Go-live date; changes in remittance advice, statements and debit notes; contacts | Letter or e-mail from Finance | G-2 weeks | Unit Head, Finance and General Accounting |
| Banks, TFS, SAP team | Go-live date for files; contacts during hypercare | E-mail from IT | G-2 weeks | TISPH Head of IT |
| Hypercare team | Roster, daily check-in time, escalation path | Hypercare kick-off | G-3 business days | iorta TechNXT Project Manager |

## Go-live evidence pack

The following records are kept as the audit evidence of go-live, in the archive TISPH designates (question GQ-13): Gate 2 UAT sign-offs and defect log; readiness checklist with signatures; pipeline run summaries and approval records of the production deployment; comparison workbook UAT against production; migration batch records, errors workbooks and reconciliation workbooks with signatures; transaction reset report; Go/No-Go minute; audit entries of the golive.locked change and of the first sign-ins; hypercare log and exit certificate (template docs/package/03_Contracts/iNXT_BrokerVerse_Hypercare_Exit_and_Handover_Certificate.docx).

# Hypercare plan

## Duration and hours

| Item | Plan |
| --- | --- |
| Duration | Four weeks from go-live, and in any case until the first month-end close in BrokerVerse is completed (Data Migration Q12) |
| Hours | NFR-13 support window, Monday to Saturday 08:30 to 17:30 Philippine time; on call for severity 1 outside the window |
| Infrastructure | Azure monitoring and alerting around the clock (NFR-13.2); alert mailbox watched by TISPH IT and iorta TechNXT DevOps |
| Location | Key users on the floor in their teams; iorta TechNXT functional consultants on site or on call (to be agreed) |

## Team

| Role | Party | Responsibilities |
| --- | --- | --- |
| Hypercare lead | iorta TechNXT Project Manager | Daily check-in, triage, release decisions with TISPH IT, daily status |
| Functional consultants (Sales and Operations; Cash Control and Finance) | iorta TechNXT | How-to answers, configuration corrections, defect reproduction |
| DevOps lead | iorta TechNXT | Monitoring, logs, deployments, rollback |
| Developers on call | iorta TechNXT | Fixes through the normal pipeline |
| Key users (one per team) | TISPH | First line: how-to, missing role or setting, floor support |
| TIS IT AppSupport / Admin | TISPH | Second line: users, roles, passwords, two-step resets, settings, schedules, interfaces; shadows the iorta TechNXT team |
| Process Owners | TISPH | Accept workarounds; prioritise defects of their area |

## Support flow and severity

Diagram 5

| No. | Step | Next |
| --- | --- | --- |
| 1 | User | step 2 (Key user (first line)) |
| 2 | Key user (first line) | how-to answered: step 3 (Closed, added to tips) role, password, setting: step 4 (TIS IT AppSupport / Admin (second line)) |
| 3 | Closed, added to tips | End |
| 4 | TIS IT AppSupport / Admin (second line) | resolved: step 3 (Closed, added to tips) defect, data, interface, outage: step 5 (iorta TechNXT hypercare (third line)) |
| 5 | iorta TechNXT hypercare (third line) | step 6 (Severity) |
| 6 | Decision: Severity | 1 or 2: step 7 3 or 4: step 8 (Backlog; next planned release) |
| 7 | Workaround now; fix through the pipeline (production approval) | step 3 (Closed, added to tips) |
| 8 | Backlog; next planned release | End |

Reports follow docs/onboarding/SUPPORT_AND_ESCALATION.md section 2 (screen, record number, time, request ID, screenshot with personal data covered, role and environment from Help > About). The severity definitions and the proposed response targets of that document apply during hypercare until the support agreement sets the final figures:

| Severity | Meaning | First response (proposal) | Workaround or fix (proposal) |
| --- | --- | --- | --- |
| 1 Critical | System down, a core process stopped for everyone, or data wrong or exposed | 1 business hour | 1 business day |
| 2 High | A core process stopped for one team, no workaround | 4 business hours | 3 business days |
| 3 Medium | A function fails with a workaround | 1 business day | Next planned release |
| 4 Low | Question, cosmetic issue or change request | 2 business days | Planned with TISPH |

During hypercare, change requests are logged but not built unless the Change Control Board classifies them as a correction of an agreed requirement (BRD 8.1).

## Daily and weekly checks

| Frequency | Check | Where in the system | Owner |
| --- | --- | --- | --- |
| Daily, 09:00 | Availability and alerts of the last 24 hours | Application Insights; alert mailbox | DevOps lead |
| Daily | API health and pending migrations | GET /api/health | DevOps lead |
| Daily | Scheduled jobs ran and succeeded | Master > Schedules run history | TIS IT AppSupport / Admin |
| Daily | E-mail and integration outboxes: no message stuck or failed | Master > System Configuration > Integrations | TIS IT AppSupport / Admin |
| Daily | SAP GL file produced for the previous day | SAP GL file runs (GET /api/sap-gl/runs) | Finance key user |
| Daily | Trial balance balances; receivables control account against open items | Accounting reports | Finance key user |
| Daily | Receipts on migrated open items; new numbers above legacy numbers | Receipts register; numbering | CCD-BP key user |
| Daily | Sign-in problems and locked users | Sign-in history; user list | TIS IT AppSupport / Admin |
| Daily | Server errors by request id | Log Analytics ContainerAppConsoleLogs_CL | DevOps lead |
| Weekly | Renewal queue picks up migrated policies; ageing of migrated items | Renewals; receivable ageing | Operations key user |
| Weekly | Audit Trail review of corrections to migrated records, of receipt cancellations and of configuration changes (entities settings and system-settings, risk R-33); golive.locked still on | Master > Audit Trail | Head, Risk Management |
| Weekly | Adoption measures (section 11.6) | As listed there | TISPH Project Manager |

## Releases during hypercare

Fixes follow the normal pipeline: merge to TISPH-DEV, DEV, then SIT or UAT for regression of the affected area, then production with approval (ADR-07). An emergency change uses the same pipeline with a shortened test in UAT and is reviewed at the next Release and Change Advisory meeting; whether a separate hotfix path is required is decision E10. Migrations stay forward-only, so a rolled-back release keeps running on the database (ADR-04).

## Exit criteria

| # | Criterion |
| --- | --- |
| HX-01 | First month-end closed in BrokerVerse and the SAP GL files of the month accepted by Finance |
| HX-02 | No open severity 1 or 2 defect; severity 3 defects have a planned release |
| HX-03 | Migration reconciliation differences cleared or accepted |
| HX-04 | Adoption measures at or above their exit targets (section 11.6), or a recovery plan agreed |
| HX-05 | TIS IT AppSupport trained on the runbooks and has handled second-line tickets without help for one week |
| HX-06 | Support agreement in force for steady state; contacts and escalation published |
| HX-07 | Legacy system read-only and its retention custodian confirmed |
| HX-08 | Hypercare exit and handover certificate signed by the Project Sponsor, Head of IT and Finance Head |
| HX-09 | iorta TechNXT cutover and support accounts in production set inactive, confirmed by an access review (Data Migration section 18) |

# Change management

## Scope change (BRD 8)

After sign-off, any change to the BRD runs through a change request, whichever party raises it (BRD 8). A change may move a delivery date only when it changes scope and both parties agree the effect in writing on the change request (BRD 8.1); clarification, wording correction and defect fixes do not move dates. The change request register (BRD 8.2) holds seventeen change requests covering the approved Phase 1 customisations. The Change Control Board (section 2.1) records each new request with its BRD references so that the traceability chain of BRD 9.2 extends to it.

## Release change

| Change type | Route | Approval | Evidence |
| --- | --- | --- | --- |
| Standard release | Pull request, CI, merge to TISPH-DEV, DEV, SIT, UAT, production by digest | Required reviewers per environment; production by TISPH IT and the business owner | Pipeline run and approval records |
| Emergency fix | Same pipeline, shortened UAT regression | Production approvers; review at the next advisory meeting | As above, with the incident reference |
| Rollback | azure-deploy.yml in rollback mode, or automatic on smoke-test failure | As a deployment | Run summary |
| Infrastructure change | Terraform plan reviewed, then apply by an operator | TISPH Head of IT | Plan output and state history |

## Configuration change in production

Configuration is data (ADR-09), so most business changes do not need a release. Controls that apply:

- changes to posting rules and account determination go through configuration approvals with a second person while accounting.configuration_maker_checker is on (it must stay on: readiness C-06);

- authority limits are proposed by one administrator and approved by another;

- settings owned by a dedicated screen can only be changed there;

- every change is in the Audit Trail with before and after values; changes to the control settings themselves need no second person and are therefore reviewed weekly (risk R-33);

- larger changes are prepared in UAT, exported with the configuration workbook, loaded in production and verified with the environment comparison. Signed promotion packages with approval and verification are Planned (GP-05).

## Emergency access

The break-glass route is a password sign-in reserved for the roles in security.password_sign_in_roles (default System Administrator), with a long password and two-factor authentication (ADR-12). Its use is visible in the sign-in history and the Audit Trail and is reviewed by the Head of Risk Management after each use.

## Organisational change: what changes for TISPH users

| Change | Personas affected | What it means in daily work |
| --- | --- | --- |
| Maker and checker are always different people | All approving personas | A quotation, placement, renewal, claim decision, voucher, remittance or close cannot be approved by the user who raised it (BRD 4.2) |
| Receipts are issued by Cash Control | Sales, Operations, CCD-BP | Front office records how the client paid; CCD-BP issues and posts the official receipt; CCD-Recon reverses |
| Policy live only on insurer confirmation | Sales, Operations | No screen lets a TISPH user complete cover; issuance follows the insurer's confirmation (BRD 4.2) |
| Microsoft sign-in and MFA | Everyone | Staff sign in with their Microsoft 365 account; local passwords only for break-glass administrators |
| Idle time-out and lockout | Everyone | Sessions end after the configured idle time (3 minutes if TISPH confirms NFR-03); with password sign-in, five failures lock the account until an administrator unlocks it; Microsoft sign-in follows TISPH's Entra ID policy |
| Masked personal identifiers | Cash Control personas and IT AppSupport / Admin (no view:pii) | TIN, ID numbers and similar identifiers show partially masked |
| My Work | Everyone | One worklist per user and team with overdue and due-today items |
| Closed periods | Finance | Closed periods take no postings |
| Everything is audited | Everyone | Every create, update and workflow step is recorded with the user and time |

## Stakeholder map

| Stakeholder | Interest | Engagement |
| --- | --- | --- |
| Project Sponsor | Benefits, risk, date | Chairs the Steering Committee; signs go-live and hypercare exit |
| Business Process Owners | Processes and controls of their area | FRS review, UAT sign-off, key users, decisions |
| TISPH IT | Operability for ten years | Design Authority, production approvals, support model |
| Risk Management and Internal Audit | Controls and evidence | Readiness sections C and D, evidence pack, ADR-10 and ADR-15 |
| Data Protection Officer | Personal data | Decisions P1 and P2; masking approvals |
| End users | Ease of daily work | Training, key users, Help panel, feedback in hypercare |
| Insurers, banks, TFS, SAP team | Files and documents | Interface specifications, test files, go-live notices |

# Training and adoption plan

## Principles

Training is by persona, on the TISPH UAT environment (or a training copy marked training, ADR-13), with TISPH data patterns and the TISPH brand pack. Key users are trained first and co-deliver end-user sessions. Every session ends with a practical assessment.

## Materials

| Material | State at the baseline |
| --- | --- |
| In-application Help panel (avatar menu > Help, F1 or "?") opening the manual section of the current screen | Built (brokerverse/src/components/HelpPanel/) |
| TISPH user manual, HTML, Word and PDF, PH Version 1.3 of 10 October 2026 (Draft until TISPH sign-off) | Built (brokerverse/public/help/) |
| UAT scripts per role | Built, TISPH roles (docs/onboarding/UAT_SCRIPTS.md) |
| Getting started guide; go-live data set-up; support and escalation | Built (docs/onboarding/) |
| Role chapters of the TISPH user manual (one per TISPH role: menus, access, approvals, segregation of duties) | Built (docs/TISPH/manual/chapters/role-*.md); the generic role decks were retired on 11 October 2026 |
| TISPH edition of the manual and Help: TISPH title and brand, one chapter per TISPH role with generated menus, approvals and SoD | Built (docs/TISPH/manual/); Draft until TISPH decisions D1 to D14 and sign-off (GP-12) |
| Persona training scripts for the 13 TISPH roles | To be written from the UAT scripts during UAT (plan, section 11.3) |

## Curriculum by persona group (proposal)

| Persona group | Modules | Duration (proposal) |
| --- | --- | --- |
| All personas | Sign-in with Microsoft, navigation, My Work, Help panel, reporting a problem, personal data rules | 1.5 hours |
| Sales Associate, Officer, Unit Head | Leads and campaigns, clients, motor and non-motor quotations, placement requests, policies, endorsements, renewals; approvals for Officer and Unit Head; incentives for Unit Head | 2 days |
| Operations Associate, Officer, Unit Head | Placements and issuance, endorsements, cancellations, renewals, claims; approvals for Unit Head | 2.5 days |
| CCD-PDU, CCD-PDC / ADA | Post-dated cheques and auto-debit arrangements; reports | 1 day |
| CCD-BP / QRPh | Receipting, bills payment and QRPh, posting of collections | 1.5 days |
| CCD-Recon | Reconciliation, reversals, bank and insurer statements | 2 days |
| Finance and General Accounting | Disbursements, journal vouchers, payables, fixed assets, commission, remittance, period end, tax and BIR, SAP GL file | 5 days |
| IT AppSupport / Admin | Users and roles, access control, settings, masters, product configurator, schedules, integrations, audit trail, health and logs, go-live workbench | 3.5 days |
| General Manager | Dashboards, approvals, audit trail, reports | Half a day |
| Key users (one per team) | Their persona curriculum plus first-line support, exercise book, train-the-trainer | Plus 1 day |

## Schedule (proposal)

| When | Activity |
| --- | --- |
| G-12 to G-10 weeks | Key users trained during UAT preparation |
| G-8 weeks | Training environment ready; persona scripts final |
| G-6 to G-3 weeks | End-user sessions by persona, at most 12 participants each |
| G-2 weeks | Assessment of every user; catch-up sessions |
| Go-live + 1 month | Refresher before the first month-end; topics from hypercare tickets |
| Steady state | New joiners trained by key users with the same curriculum and assessment |

## Assessment

Each participant completes the scenarios of their persona on the training environment without help. Pass mark and records system are to be agreed (question GQ-08). A user who does not pass repeats the session before receiving production access.

## Adoption measures (KPIs)

| KPI | Definition | Source in the system | Target (proposal) | Measured |
| --- | --- | --- | --- | --- |
| A-1 Activation | Licensed users who have signed in at least once | Access Control > User Matrix (last sign-in per user; downloadable) | 100% by day 3 | Daily, week 1 |
| A-2 Daily use | Users signed in on a business day divided by users expected to work that day | Daily download of the User Matrix (last sign-in) | 90% from week 2 | Daily, hypercare |
| A-3 System of record | New policies, receipts and vouchers created outside BrokerVerse after cutover | Legacy system read-only; registers | Zero | Weekly |
| A-4 Workload control | Overdue items per team in My Work | GET /my-work/summary and /my-work/team | Falling week on week; no team above its agreed ceiling by week 4 | Weekly |
| A-5 Approval turnaround | Items waiting for approval older than two business days | My Work items by category and due date | Below 5% by week 4 | Weekly |
| A-6 Self-service | Share of tickets resolved at first or second line | Support log (outside the system) | 70% by week 4 | Weekly |
| A-7 Training | Users trained and assessed for their persona before production access | Training records (outside the system) | 100% | Before go-live |
| A-8 Operational health | Failed scheduled job runs | Master > Schedules run history | Zero unresolved at day end | Daily |
| A-9 Finance cycle | First month-end closed on time; daily SAP GL file produced every business day | Period-end; SAP GL file runs | On time; 100% | Monthly; daily |
| A-10 Data quality | Corrections to migrated records | Audit Trail filtered on migrated records | Falling to near zero by week 4 | Weekly |

No single adoption report is built; the measures are read from the screens and exports listed. A usage report is Not built (question GQ-09).

# Long-term governance (ten years and more)

## Recurring activities

| Activity | Frequency | Owner | Reference |
| --- | --- | --- | --- |
| Steering-level service review: availability, incidents, capacity, risks | Quarterly | TISPH Head of IT | NFR-14, NFR-20 |
| DR drill on UAT; geo-restore rehearsal for production | Twice a year | TISPH Head of IT | deploy/AZURE.md section 12 |
| Vulnerability assessment and penetration test | Yearly | TISPH Head, Risk Management | NFR-16 |
| Access review of users and roles (Access Control > Access Reviews), SoD rules and authority limits | Twice a year | Process Owners with Head, Risk Management | BRD 5.14 |
| Review of control settings against the signed baseline (risk R-33) | Quarterly | Head, Risk Management | BRD 5.14 |
| Cloud security posture report | Yearly | TISPH Head, Risk Management | NFR-17.4; method open (NFR Q13) |
| Rotation of the personal identifier key | Per TISPH key policy | TISPH Head of IT | npm run pii:rotate |
| Renewal of the Entra ID client secret | Before 24-month expiry | TIS IT AppSupport / Admin | deploy/AZURE.md section 14 |
| Review of the ADR log and risk register | Yearly and with each major release | Design Authority | Section 6 |
| Dependency audit and patch releases | Every release (CI) and monthly review | iorta TechNXT technical lead | ci.yml |
| Capacity forecast | Yearly | TISPH Head of IT | NFR-20 |

## Technology lifecycle

| Component | Version at baseline | Where set | Lifecycle note |
| --- | --- | --- | --- |
| Node.js | 22 | backend/Dockerfile, backend/package.json engines, ci.yml | Plan the move to the next long-term-support line before Node.js 22 leaves maintenance (April 2027) |
| PostgreSQL | 16 | deploy/azure/modules/environment/database.tf, ci.yml service | Major upgrade before community support ends (November 2028); test on a restore first |
| React build tool | react-scripts 5.0.1 with craco | brokerverse/package.json | No longer developed by its maintainers; plan a move to a maintained build tool |
| React | 18 | brokerverse/package.json | Upgrade with the build tool |
| Express | 4 | backend/package.json | Upgrade path to the next major line to be planned |
| multer (file uploads) | 1.4.5-lts.1 | backend/package.json | The 1.x line is superseded by 2.x; plan the upgrade with the upload tests |
| nginx | 1.27 (alpine) | brokerverse/Dockerfile | Image refreshed with each release |

Each upgrade is a normal release through the pipeline, protected by the full test suites (114 test files in backend/test, 64 front-end test files) and recorded as an ADR when it changes a decision above.

## Knowledge retention

The support team's entry points are the developer guide (docs/developer-guide/), the module guide (backend/docs/MODULE_GUIDE.md), the generated API documentation and touchpoint workbook (backend/docs/api/), the runbooks in deploy/, the onboarding guides in docs/onboarding/ and this pack. The contract pack contains templates for a source code escrow agreement and an exit and transition plan (docs/package/03_Contracts/); whether TISPH uses them is a commercial decision (question GQ-14).

# Summary of status

| Area | As built | Main open points |
| --- | --- | --- |
| Governance bodies | Proposed in this document | Membership and cadence (GQ-01) |
| Release control | Pipeline with approvals, CI gate, digest promotion, automatic rollback | Reviewers, change reference, pipeline tool (GQ-05, E3, E4) |
| Architecture decisions | Seventeen recorded, all as built | TISPH confirmation (GQ-10), especially ADR-06 and ADR-08 |
| Controls | Maker-checker, SoD check on role assignment, authority matrix, access reviews, audit trail | Control switches changeable by one administrator (R-33); audit insert outside the business transaction (R-34); receipt cancellation right of CCD-BP (GQ-15) |
| Readiness | Tools for comparison, reset, lock, masking, rehearsal, smoke test exist | Provisioning, drills, scans, performance, support agreement |
| Go-live | Rehearsed end to end on local environments | Date, decisions, rehearsal on TISPH environments |
| Training | Help panel and base manual built | TISPH edition (GP-12); persona scripts |

# Register of Planned items

Every item below is designed but not built at the baseline.

| # | Planned item | Section | Depends on |
| --- | --- | --- | --- |
| GP-01 | PRE-PROD environment on Azure (tfvars, GitHub environment, pipeline stage) | 7 A-02, 8.2 | TISPH decision E1 |
| GP-02 | Environment marker and environment-bound settings never exported or loaded by the configuration workbook | 6 ADR-13, 7 E-03 | Work package W0-4 |
| GP-03 | Shared master data registry and case-insensitive business keys with a pre-flight duplicates report | 6 ADR-09 | Work package REG-1 (migration 0411) |
| GP-04 | Upload with template on every master and the Setup Workbook | 10.3 | Work packages MU-A, MU-B; decisions M1 to M15 |
| GP-05 | Environment Promotion: signed packages, approval, apply, before-image rollback, verification | 6 ADR-09, 10.3 | Work packages PR-1a, PR-1b (after REG-1, ADP-1); decisions E1, E2, E5 to E15 |
| GP-06 | Promotion command-line tool, pipeline stage with workload identity, change reference on production deployments | 6 ADR-07, 7 B-05 | Work package PR-2; decisions E3, E4 |
| GP-07 | Personal data security fixes (masked write answers and current-data workbooks; identifier menu item only where it acts) | 6 ADR-11, 7 D-02 | Work packages W0-3, PD-1a |
| GP-08 | Time-limited, recorded reveal of full personal identifiers | 6 ADR-11 | Work package PD-1b; decisions P1, P2 |
| GP-09 | Risk Details replacing Risk Mapping | 5.2 | Work packages W0-1, RD-A, RD-B, RD-C; decisions R1 to R6 |
| GP-10 | Coverage Builder clean-up | 5.2 | Work packages CB-1a, CB-1b; decisions R7, R14 |
| GP-11 | Copy of transactions and configuration records | 5.2 | Work packages CL-1, CL-A, CL-B; decisions C1 to C13 |
| GP-12 | TISPH edition of the user manual and Help with one chapter per TISPH role | 7 H-04, 11.2 | Work packages MAN-A, MAN-B; decisions D1 to D14 |
| GP-13 | Remittance redesign: menu, approvals, insurer payments, one payment path, reconciliation, exceptions, insurer billing | 5.1 R-02 | Remittance phases R1 to R4; remittance questions Q1 to Q20 |
| GP-14 | Remittance go-live clean-up and opening remittances from a policy list | 7 E-10 | Remittance phase R2; remittance question Q14 |
| GP-15 | Performance and stress test at production sizing | 7 G-07 | Test activity DA-1; NFR question Q2 |
| GP-16 | DR drill on UAT and geo-restore rehearsal for production | 7 G-04, G-05 | Test activity DA-2; Azure UAT and PROD provisioned |
| GP-17 | VA and MBSS scans before go-live; yearly penetration test | 7 C-09 | Test activity DA-3 |
| GP-18 | Support agreement with hours, channels, targets and service reports | 7 H-01 | Activity DA-4; NFR question Q17 |
| GP-19 | WCAG 2.1 AA audit and fixes | 12 | Activity DA-5; NFR question Q15 |
| GP-20 | Kubernetes manifests or Helm chart | 6 ADR-06 | TISPH decision to standardise on AKS (Architecture Q6) |
| GP-21 | Transfer of the SAP GL files to SAP over SFTP | 7 F-02 | TISPH choice of transfer method (Architecture Q1) |
| GP-22 | Automatic bank file pick-up and drop over SFTP | 7 F-03 | Bank file specifications and transfer decision (Architecture Q2) |
| GP-23 | Dedicated TFS feed (leads, Credit Life loan batch, account and expiry lists) | 7 F-04 | TFS file specification (INTG-03; Architecture Q4) |
| GP-24 | BIR EIS live operation with the BIR signing method | 7 F-05 | TISPH EIS enrolment and certification (Architecture Q5) |

Number of Planned items: 24.

Not built and without a work package (each linked to an open question): ten-year backup retention (NFR Q7); automatic unlock and single-session enforcement (NFR Q9); API error-rate and latency alerts (NFR Q13); security scanning in CI (Environment Q5, SEC-Q13); technically immutable audit trail (NFR Q19); data scope by office and department (Data Q10); secure-cookie sessions (SEC-Q2); usage and adoption report (GQ-09); second-administrator approval of control settings (SEC-Q12); audit entry inside the business transaction (NFR Q19); cloud security posture report (NFR Q13).

# Open questions for TISPH

Questions already raised in the companion documents and needed for governance: Architecture Q1 to Q6 and Q10; Environment Strategy Q1 to Q5, Q8, Q9 and Q12; NFR Q2, Q7, Q9, Q12, Q13, Q17 and Q19; Security SEC-Q2, SEC-Q7 and SEC-Q13, plus SEC-Q6 (approvals without an authority limit) and SEC-Q12 (second approval of security settings); Data Migration Q1, Q6, Q9 to Q12, Q17 (compensating controls for the go-live lock) and Q18 (supplier administrator account in production); the decision log of section 5.2. New questions:

| Serial Number | Description | Owner | Status |
| --- | --- | --- | --- |
| GQ-01 | Who sits on the Steering Committee, the Design Authority, the Change Control Board and the Release and Change Advisory, how often do they meet, and who may sign waivers on behalf of the Project Sponsor? Needed for: Section 2.1 | TISPH | Open |
| GQ-02 | Which go-live date and SOW milestones apply, and which planned items (section 14) are required at go-live and which may follow it? Needed for: Plan, R-06, GN-04 | TISPH | Open |
| GQ-03 | Which named people hold each RACI role and each persona, and who is the key user of each team? Needed for: Section 4 | TISPH | Open |
| GQ-04 | Who owns each decision series (P, R, M, E, C, D; remittance Q1 to Q20) and by what date will each be taken? Needed for: Section 5.2, R-01, R-02 | TISPH | Open |
| GQ-05 | Who are the required reviewers of the SIT, UAT and production deployments, and does TISPH have an existing change advisory board and change tool that releases must follow? Needed for: ADR-07, readiness B-01 | TISPH | Open |
| GQ-06 | Is a four-week hypercare, extended to the first month-end close, acceptable; on site or remote; and who signs the hypercare exit? Needed for: Section 9 | TISPH | Open |
| GQ-07 | What is the steady-state support model: TISPH first and second line, iorta TechNXT third line, hours under NFR-13, and who holds the Azure support plan? Needed for: Section 9, GP-18 | TISPH | Open |
| GQ-08 | Where will training take place, on which environment (UAT or a separate training copy), what is the assessment pass mark, and where are training records kept? Needed for: Section 11 | TISPH | Open |
| GQ-09 | Are the proposed adoption targets acceptable, who reports them, and should a usage report be built into the platform? Needed for: Section 11.6 | TISPH | Open |
| GQ-10 | Will TISPH's Design Authority confirm the seventeen ADRs, in particular Azure Container Apps for NFR-19 (ADR-06) and Terraform without Ansible for NFR-19.1 (ADR-08)? Needed for: Section 6 | TISPH | Open |
| GQ-11 | What residual risk is TISPH willing to accept at go-live, for example going live with the configuration workbook and environment comparison before the Environment Promotion module (GP-05) is built? Needed for: Gate 3, Gate 4 | TISPH | Open |
| GQ-12 | When will the legacy system be decommissioned, and who keeps its records for the retention periods of NFR-11.1 and NFR-11.2? Needed for: H-07, HX-07 | TISPH | Open |
| GQ-13 | Where is the go-live evidence pack (section 8.6) archived and for how long, and how long must the pipeline run and approval history be kept? Needed for: Section 8.6, ADR-07 | TISPH | Open |
| GQ-14 | Who owns the source repository and its settings for the life of the platform, and will TISPH use source code escrow? Needed for: Section 12.3, R-22, R-26 | TISPH | Open |
| GQ-15 | Should receipt cancellation (which reverses payment journals) be a permission separate from receipt issue, held by CCD-Recon only, and should rule SOD-TIS-BP-RECON block rather than warn? Needed for: 3.2, R-15, C-06 | TISPH | Open |

# Requirements traceability

| BRD reference | Short phrase | Section |
| --- | --- | --- |
| 1.2 | Timeline as stipulated in the signed SOW | 5.1 (R-06), 8.1 |
| 4.2 | Raiser can never approve | 6 (ADR-10), 10.5 |
| 5.13 | Integrations "file-based or e-mail-based" | 5.1 (R-03, R-04), 6 (ADR-17), 7 F, 14 (GP-21 to GP-24) |
| 5.14 | Access, approval and audit | 3.2, 5.1 (R-15, R-33, R-34), 6 (ADR-10, ADR-15), 7 C, 12.1 |
| 8, 8.1, 8.2 | Change control; effect on schedule; change request register | 2.1, 10.1 |
| 9.1 | Delivery sequence from sign-off | 2.2, 8 |
| 9.2 | Traceability from BRD to UAT sign-off | 2.2, 8.4 (GN-01) |
| 11 | Requirements sign-off roles | 2.1, 4 |
| NFR-8.2 | Change management and configuration control | 6 (ADR-07, ADR-09), 10 |
| NFR-06.1, NFR-19, NFR-19.1 | Azure; Docker and Kubernetes; Terraform | 6 (ADR-06, ADR-07, ADR-08) |
| NFR-06.2, NFR-06.3 | RPO and RTO | 5.1 (R-08), 7 G, 12.1 |
| NFR-07 family, NFR-12 | Performance, concurrency | 5.1 (R-07), 7 G-07 |
| NFR-11, NFR-11.1, NFR-11.2 | Retention | 5.1 (R-09), 7 G-06, H-07 |
| NFR-13, NFR-13.1, NFR-13.2 | Support window, channels, 24x7 infrastructure | 9.1, 7 H-01 |
| NFR-14 family, NFR-20 | Monitoring; capacity forecast | 9.4, 12.1 |
| NFR-16, NFR-16.4 | Security testing; secure SDLC | 7 B-06, C-09, 12.1 |
| NFR-17.4 | Annual cloud security posture report | 7 G-08, 12.1 |
| NFR-01, NFR-17 | Data protection | 6 (ADR-11, ADR-13), 7 D |
| NFR-02, NFR-03, NFR-04 | Access control, lockout, MFA | 6 (ADR-12), 7 C, 10.5 |
| INTG-01 to INTG-05 | Interfaces | 6 (ADR-17), 7 F, 14 |

# Appendix A. File references

All paths are in the repository at the code baseline unless stated otherwise.

Section 2 (governance and delivery sequence)

- .github/workflows/azure-deploy.yml, .github/workflows/azure-deploy-environment.yml, .github/workflows/ci.yml

- deploy/AZURE.md (section 9 releases), deploy/RELEASE_PIPELINE.md

- docs/e2e/UAT_SCENARIO_RUN.md, docs/e2e/GOLIVE_REHEARSAL_RUN.md, docs/e2e/ROLE_WALK.md, docs/archive/2026-10-10/e2e/DEFECTS.md

- Section 5 of this document (risk register, decision log); change request form in docs/package/03_Contracts/

Section 3 (workstreams and personas)

- backend/src/db/migrations/0348_tisph_roles.sql (TISPH roles and permissions), backend/src/db/seed.js (ROLE_PERMS), backend/src/db/seeds/82_tisph_roles.sql (report lists, SOD-TIS-BP-RECON)

- backend/src/modules/receipts/router.js (POST /:id/cancel under write:receipts)

- backend/src/modules/ (69 modules), brokerverse/src/, deploy/azure/

Section 5 (risks and decisions)

- backend/src/lib/makerChecker.js (finance.maker_checker_enabled), backend/src/lib/goLiveLock.js

- backend/src/modules/system-settings/router.js (PUT /configuration under write:settings, audited), backend/src/modules/settings/router.js, backend/src/lib/settingOwners.js

- backend/src/modules/posting-rules/service.js (accounting.configuration_maker_checker), backend/src/db/migrations/0193_access_control.sql (access.sod_enforced, access.authority_without_limit)

- backend/src/lib/audit.js, backend/src/db/pool.js (ambient transactions) for R-34

- backend/src/modules/auth/router.js (lockout), backend/src/db/seeds/settings.json (limits.session_idle_minutes 30)

- backend/src/jobs/scheduler.js (advisory locks; SCHEDULER_ENABLED)

- deploy/AZURE.md sections 12 to 15; docs/TISPH/pack/TISPH_Operations_and_Support.docx section 17 (known limitations)

- Planning sources outside the repository: platform features build plan of 10 October 2026 (sections 2, 5, 8, 9, 10); Accounts > Remittance build specification of 9 October 2026 (sections 0, 8, 10, 11)

Section 6 (architecture decisions)

- ADR-01: backend/src/app.js, backend/src/server.js, backend/docs/MODULE_GUIDE.md

- ADR-02: backend/Dockerfile, backend/package.json, brokerverse/Dockerfile, brokerverse/package.json

- ADR-03: backend/src/lib/registry.js, backend/src/tools/export-api.js, backend/docs/api/, backend/test/tools.test.js

- ADR-04: backend/src/db/migrate.js, backend/src/db/migrations/, backend/src/db/seed.js, deploy/RELEASE_PIPELINE.md section 8

- ADR-05: backend/src/jobs/scheduler.js, backend/src/db/seeds/jobs.json, backend/src/db/migrations/0347_sap_gl_export.sql, backend/src/modules/integrations/framework/outbox.js, deploy/azure/modules/environment/containerapps.tf (SCHEDULER_ENABLED)

- ADR-06: deploy/azure/modules/environment/containerapps.tf, deploy/AZURE.md ("What runs where")

- ADR-07: .github/workflows/azure-deploy.yml, .github/workflows/azure-deploy-environment.yml, .github/workflows/ci.yml, deploy/smoke-test.sh, deploy/azure/wait-for-revision.sh

- ADR-08: deploy/azure/bootstrap/, deploy/azure/shared/, deploy/azure/environment/, deploy/azure/modules/environment/*.tf, deploy/azure/environment/environments/*.tfvars

- ADR-09: backend/src/lib/settings.js, backend/src/lib/settingOwners.js, backend/src/db/migrations/0174_configuration_controls.sql, backend/src/modules/posting-rules/service.js, backend/scripts/check-settings.js, backend/test/configuration.test.js

- ADR-10: backend/src/lib/makerChecker.js, backend/src/db/migrations/0193_access_control.sql, backend/src/modules/access-control/service.js (assertSod, deactivateDormant), backend/src/modules/access-control/router.js (User Matrix, Access Reviews, Delegations), backend/src/modules/users/router.js, backend/src/db/seeds/jobs.json (dormant-users), backend/src/db/migrations/0348_tisph_roles.sql, backend/src/db/seeds/82_tisph_roles.sql

- ADR-11: backend/src/lib/pii.js, backend/src/lib/piiPolicy.js (privacy.pii_reveal_mode), backend/src/db/migrations/0277_personal_identifier_encryption.sql, backend/scripts/rotate-pii-key.js, backend/src/config.js

- ADR-12: backend/src/lib/entraId.js, deploy/AZURE.md section 14

- ADR-13: backend/src/lib/environment.js, backend/src/db/migrations/0249_system_environment.sql, backend/scripts/mask-data.js, docs/onboarding/DATA_MASKING.md

- ADR-14: backend/src/modules/data-load/, backend/scripts/reset-transactions.js, backend/scripts/compare-environments.js, backend/scripts/golive-rehearsal.js, backend/scripts/golive/, backend/src/lib/goLiveLock.js

- ADR-15: backend/src/lib/audit.js, backend/src/db/pool.js, backend/src/modules/audit/router.js; handler pattern for example in backend/src/modules/receipts/router.js

- ADR-16: backend/src/config.js (BRAND_PACK), backend/src/modules/branding/bundled.js, docs/package/04_Onboarding_and_Go_Live/Brand_Packs/

- ADR-17: backend/src/modules/integrations/framework/ (outbox.js, connectors.js, registry.js), backend/src/modules/sap-gl/, deploy/azure/modules/environment/sftp.tf, deploy/AZURE.md section 11

Section 7 (readiness)

- deploy/AZURE.md sections 1 to 15; deploy/RAILWAY.md (TISPH DEV), docs/onboarding/GO_LIVE_DATA_SETUP.md; deploy/smoke-test.sh

- deploy/azure/modules/environment/monitoring.tf, database.tf; deploy/azure/environment/environments/prod.tfvars

- backend/src/modules/users/router.js (/users/:id/login-history), backend/src/modules/access-control/router.js (/access-control/user-matrix, /access-control/reviews)

- backend/src/config.js (productionConfigProblems), backend/src/lib/environment.js

- docs/package/06_Support/BrokerVerse_Release_Notes_Template.docx

Section 8 (go-live)

- Data Migration document of this pack, sections 12 to 19

- docs/onboarding/GO_LIVE_DATA_SETUP.md, docs/onboarding/GO_LIVE_DATA_WORKBENCH.md, docs/onboarding/SMOKE_TEST_AND_RESET.md

- docs/package/03_Contracts/iNXT_BrokerVerse_Hypercare_Exit_and_Handover_Certificate.docx

Section 9 (hypercare)

- docs/onboarding/SUPPORT_AND_ESCALATION.md (sections 1 to 6), docs/developer-guide/backend.md

- deploy/AZURE.md sections 10, 15 and "Checks when something is wrong"

Section 10 (change management)

- backend/src/lib/settingOwners.js, backend/src/db/migrations/0174_configuration_controls.sql

- docs/TISPH/pack/TISPH_Environments_and_Release.docx sections 6 to 11; deploy/RELEASE_PIPELINE.md section 8 (migrations policy)

Section 11 (training and adoption)

- brokerverse/src/components/HelpPanel/index.jsx, brokerverse/public/help/ (sections.json, user-manual.html, TISPH_User_Manual.docx and .pdf)

- docs/onboarding/UAT_SCRIPTS.md, docs/onboarding/GETTING_STARTED.md, docs/TISPH/manual/ (chapters, manual.json)

- backend/src/modules/my-work/router.js (/my-work/summary, /my-work/team, /my-work/items); backend/src/modules/sap-gl/router.js (/sap-gl/runs)

Section 12 (long-term governance)

- backend/package.json, brokerverse/package.json, backend/Dockerfile, brokerverse/Dockerfile

- deploy/azure/modules/environment/database.tf (PostgreSQL 16)

- backend/test/ (114 test files), front-end test files under brokerverse/src/ (64)

- docs/developer-guide/, backend/docs/MODULE_GUIDE.md, backend/docs/api/, docs/package/03_Contracts/

# Document Sign-Off

| Sign Off Date | Signature | Approved By | Department & Project Role |
| --- | --- | --- | --- |
|  |  |  | TISPH Project Sponsor |
|  |  |  | TISPH Head of Information Technology |
|  |  |  | TISPH Project Manager |
|  |  |  | iorta TechNXT Engagement Director |