## Instructions
BrokerVerse OOTB: Discovery and Configuration Workbook
Purpose | Records every configuration decision of the broker during mobilisation and the discovery workshops. It is the configuration workbook named in the Implementation Approach and Plan and is signed off at the end of discovery.
How to use | One sheet per area. Each row is a question or a configuration item, the BrokerVerse screen where it is set, and the value delivered out of the box. The broker writes its decision in Client answer (yellow). Leave Client answer empty to keep the OOTB default and set Status to Confirmed.
Columns | ID; Topic; Question or configuration item; BrokerVerse screen (menu path as on screen); OOTB default (seeded value); Client answer; Owner (broker role that answers); Needed by (project phase); Due date (set at kick-off); Status; Notes and setting key (technical key on Master > Configuration, upload template or reference document).
Status values | Open: not yet answered. Answered: broker answer recorded. Confirmed: reviewed in the workshop by the owner and iorta TechNXT. Configured: entered in the test environment and checked. Not applicable: area not used. Gap (CR): cannot be met by configuration; recorded in the fit-gap register as a change request.
Needed by | Mobilisation (week 1), Discovery (workshops), Configuration, Mock load 1, UAT. Due dates follow the plan of the implementation size.
Defaults | OOTB defaults are the values seeded in the delivered system on 03 October 2026. Money in PHP. Tax rates, ATC and GL accounts are confirmed by the broker's accountant and tax adviser before configuration.
Rules | Do not change the layout of the sheets. Add rows at the end of a sheet with the next ID if a new item comes up. Personal data (staff lists, client extracts) is not pasted into this workbook; it goes into the upload templates.
Companion | Discovery Workbook Guide (how to run the workshops); Implementation Approach and Plan; Data Migration and Cutover Plan; upload templates in docs/templates.

## Summary
Sheet | Items | Open | Answered | Confirmed | Configured | Not applicable | Gap (CR) | Percent configured
Company and Branches
Users and Roles
Insurers
Products and LOB
Commission Rates
Chart of Accounts
Banks and Gateways
Numbering Series
Approvals and Limits
E-mail and Templates
Taxes and LGU
Data Migration Sources
Integrations
Reports
Total

## Company and Branches
ID | Topic | Question or configuration item | BrokerVerse screen | OOTB default | Client answer | Owner (broker) | Needed by | Due date | Status | Notes and setting key
CO-01 | Legal identity | Registered company name exactly as on the SEC and BIR registration | Master > Generals > Organization > Company | Seeded company ITX "iorta TechNXT Corp.": replace |  | Sponsor | Mobilisation |  | Open | Primary company is the letterhead on documents and BIR forms
CO-02 | Legal identity | TIN and RDO code | Master > Generals > Organization > Company | Blank |  | Accounting Manager | Mobilisation |  | Open | Fields TIN, RDO Code
CO-03 | Legal identity | Registered address, ZIP code, city, province | Master > Generals > Organization > Company | Blank |  | Accounting Manager | Mobilisation |  | Open | Fields Address Line 1 to 3, Pin Code, City, State
CO-04 | Legal identity | Insurance Commission certificate of authority (licence) number and validity | Master > Generals > Organization > Company | Blank |  | Sponsor | Mobilisation |  | Open | Field License Number
CO-05 | Legal identity | Company e-mail, telephone, website | Master > Generals > Organization > Company | Blank |  | System Administrator | Configuration |  | Open
CO-06 | Legal identity | More than one legal entity on the system? Which one is the letterhead company | Master > Generals > Organization > Company | One company |  | Sponsor | Discovery |  | Open | Field "Letterhead company - used on documents and reports"
CO-07 | Branding | Logo for printed documents (PNG, at least 300 px wide) | Master > Generals > Organization > Company | iorta TechNXT logo (fallback) |  | System Administrator | Configuration |  | Open | documents.default_logo_path is the fallback only
CO-08 | Branding | Application name on the sign-in page, side bar and browser tab | Master > System Settings | BrokerVerse |  | Sponsor | Configuration |  | Open | general.system_name
CO-09 | Branding | Screen logo and colours | Master > System Settings | Primary #0072d8, secondary #004ea8 |  | System Administrator | Configuration |  | Open | branding.logo_url, branding.primary_color, branding.secondary_color
CO-10 | Branding | Accent colour of printed documents and report PDFs | Master > Configuration (Company & Branding) | #1f4e79 |  | System Administrator | Configuration |  | Open | documents.accent_color
CO-11 | Branches | List of branches: code, name, address, e-mail, telephone | Master > Generals > Organization > Branch | HO Head Office, Makati City |  | Operations head | Mock load 1 |  | Open | Branch_Upload_Template.xlsx
CO-12 | Branches | Departments per branch | Master > Generals > Organization > Branch (Department_Upload_Template.xlsx) | Seeded departments |  | Operations head | Mock load 1 |  | Open | Department upload through the API route written on the template
CO-13 | People | Employee hierarchy (ranks) and designations | Master > Generals > Employee Management > Hierarchy; Designation | Seeded hierarchy and designations |  | HR | Mock load 1 |  | Open | Hierarchy_ and Designation_Upload_Template.xlsx
CO-14 | People | Employees and sales persons with branch, department, reporting line | Master > Generals > Employee Management > Employee | None |  | HR | Mock load 1 |  | Open | Employee codes EMP-0001 (series employee)
CO-15 | Calendar | Fiscal year start month | Master > Configuration (Accounting & Tax) | 1 (January) |  | Accounting Manager | Discovery |  | Open | accounting.fiscal_year_start_month
CO-16 | Calendar | Time zone and date format | Master > System Settings | Asia/Manila; DD/MM/YYYY |  | System Administrator | Configuration |  | Open | general.timezone, general.date_format
CO-17 | Calendar | Go-live date and first open accounting period | Accounts > Period End > Period Management | None |  | Sponsor | Mobilisation |  | Open | Drives cutover and opening balance date
CO-18 | Calendar | Month-end close calendar, BIR filing dates and peak renewal months to avoid for releases | Not a system setting | Not applicable |  | Accounting Manager | Discovery |  | Open | Used for the maintenance window and the BCP
CO-19 | Dashboards | Management targets: revenue, active policies, new business, claims ratio, retention, satisfaction | Master > Configuration (Reports & Dashboards) | Revenue PHP 5,000,000.00; 250 policies; new business PHP 2,000,000.00; claims ratio 70; retention 90; satisfaction 95 |  | Sponsor | Configuration |  | Open | dashboard.targets
CO-20 | Dashboards | Sum insured above which a policy is flagged as high value | Master > Configuration (Reports & Dashboards) | PHP 5,000,000.00 |  | Sponsor | Configuration |  | Open | dashboard.high_sum_insured
CO-21 | Hosting | Hosting option: AWS Singapore, Azure Singapore, Philippine partner, or own data centre | Not a system setting | AWS Singapore (implementation assumption) |  | IT head | Mobilisation |  | Open | Architecture document; data residency decision recorded by the DPO
CO-22 | Hosting | Planned maintenance window | Not a system setting | Saturday 20:00 to Sunday 06:00 PHT |  | IT head | Discovery |  | Open | Production Support Approach and Standards

## Users and Roles
ID | Topic | Question or configuration item | BrokerVerse screen | OOTB default | Client answer | Owner (broker) | Needed by | Due date | Status | Notes and setting key
US-01 | Users | List of named users: full name, user name, e-mail, branch, department, role | Master > Generals > User Management > User | Administrator BrokerVerse only |  | System Administrator | Mock load 1 |  | Open | Users_Provisioning_Template.xlsx; user list due two weeks before training
US-02 | Roles | Map each job title to one of the seven delivered roles | Master > Generals > User Management > Role | System Administrator, Sales & Marketing, Processing Team, Operations, Claims, Accounting, Accounting Manager |  | Sponsor | Discovery |  | Open | One role per user is the norm
US-03 | Roles | Changes to the permissions of a delivered role | Master > Generals > User Management > Role Permissions | Delivered grants |  | Sponsor | Discovery |  | Open | Review with the User Access Matrix
US-04 | Administrators | Names of the System Administrator and a deputy | Master > Generals > User Management > User | None |  | IT head | Mobilisation |  | Open | At least two recommended
US-05 | Approvers | Names of a second Accounting Manager and second checkers for each maker-checker flow | Master > Generals > User Management > User | None |  | Accounting Manager | Discovery |  | Open | Maker and checker must be different users
US-06 | Security | Roles that must use two-step verification (authenticator app) | Master > Configuration (Security & Access) | None |  | IT head | Configuration |  | Open | security.require_2fa_roles; recommended system-admin, accounting, accounting-manager
US-07 | Security | Password policy: length, character classes, history, maximum age | Master > Configuration (Security & Access) | 8 characters; upper, lower, digit, symbol; last 5 refused; 90 days |  | IT head | Configuration |  | Open | security.password_*
US-08 | Security | Failed sign-ins before the account is locked | Master > Configuration (Security & Access) | 5 |  | IT head | Configuration |  | Open | limits.max_login_attempts
US-09 | Security | Sign-in attempts per IP and user name | Master > Configuration (Security & Access) | 10 per 300 seconds |  | IT head | Configuration |  | Open | security.login_rate_limit
US-10 | Security | Idle sign-out | Master > Configuration (Security & Access) | 30 minutes |  | IT head | Configuration |  | Open | limits.session_idle_minutes
US-11 | Security | Days without sign-in before an account is deactivated | Master > Configuration (Security & Access) | 90 days |  | IT head | Configuration |  | Open | access.dormant_days
US-12 | Scope | Roles that see only their own book (records and clients they own) | Master > Configuration (Security & Access) | None |  | Sponsor | Discovery |  | Open | security.scoped_roles
US-13 | Segregation of duties | Accept or change the SoD rules | Master > Generals > User Management > Segregation of Duties | Block: placement and payment; placement and payment approval; claims and payment. Warn: sales and collection; sales and claims |  | Sponsor | Discovery |  | Open | access.sod_enforced = true
US-14 | Access reviews | Frequency and reviewer of access recertification | Master > Generals > User Management > Access Reviews | Not scheduled |  | IT head | Discovery |  | Open | Twice a year recommended
US-15 | Delegations | Delegations of approval authority needed at go-live (leave, travel) | Master > Generals > User Management > Delegations | None |  | Accounting Manager | UAT |  | Open
US-16 | Commission | Roles that earn commission on the policies they produce | Master > Configuration (Commission & Incentives) | Sales & Marketing |  | Sales head | Discovery |  | Open | commission.eligible_roles
US-17 | Notifications | Roles told when a client approves a quotation | Master > Configuration (Sales, Quotations & Placement) | Processing Team |  | Sales head | Discovery |  | Open | quotations.approval_notify_roles
US-18 | Notifications | Roles that approve renewals | Master > Configuration (Policies, Endorsements & Renewals) | Processing Team |  | Operations head | Discovery |  | Open | renewals.approver_roles

## Insurers
ID | Topic | Question or configuration item | BrokerVerse screen | OOTB default | Client answer | Owner (broker) | Needed by | Due date | Status | Notes and setting key
IN-01 | Insurer master | Insurers the broker places with: legal name, short name, code, TIN, address | Master > Generals > Insurance Management > Insurance Company | Six Philippine non-life insurers seeded (MAPFRE, Malayan, Pioneer, FPG, Standard, Mercantile) with example contact e-mails |  | Processing Team lead | Mock load 1 |  | Open | Insurance_Company_Upload_Template.xlsx; replace example e-mails
IN-02 | Insurer master | Default commission rate per insurer | Master > Generals > Insurance Management > Insurance Company | 14% to 17.5% on the seeded insurers |  | Accounting Manager | Mock load 1 |  | Open | Rate matrix rows override it
IN-03 | Credit terms | Premium payment warranty days per insurer | Master > Generals > Insurance Management > Insurance Company | Blank |  | Accounting Manager | Mock load 1 |  | Open | Field Premium Payment Warranty (days)
IN-04 | Credit terms | Remittance terms: days after collection per insurer | Master > Generals > Insurance Management > Insurance Company | Blank; fallback 30 days |  | Accounting Manager | Mock load 1 |  | Open | Field Remittance Terms; remittance.default_due_days
IN-05 | Billing | Default billing mode per insurer: broker billed or direct bill | Master > Generals > Insurance Management > Insurance Company | Broker billed |  | Accounting Manager | Discovery |  | Open | Field Default Billing Mode; direct_bill.default_billing_mode
IN-06 | Contacts | Underwriting, claims and accounting contacts per insurer (for slips, loss advice, remittance statements, debit notes) | Master > Generals > Insurance Management > Insurance Company | Example addresses only |  | Processing Team lead | Configuration |  | Open
IN-07 | Claims | Default recipient of the preliminary loss advice | Master > Configuration (Claims) | claims@brokerverse.local (placeholder) |  | Claims head | Configuration |  | Open | claims.pla_default_recipient; replace before go-live
IN-08 | Statements | Format of each insurer statement of account (columns, file type) and a sample file | Master > Finance > Insurer Statement Formats | None |  | Accounting | Configuration |  | Open | Used by Accounts > Insurer Reconciliation
IN-09 | Co-insurance | Lines usually co-insured; lead insurer practice; who confirms shares | Operations > Sales & Marketing > Placement Slips | Shares must total 100%; rounding to the lead |  | Processing Team lead | Discovery |  | Open
IN-10 | Placement | Days an insurer offer stays valid | Master > Configuration (Sales, Quotations & Placement) | 30 days |  | Processing Team lead | Discovery |  | Open | placement.offer_validity_days
IN-11 | Signatories | Authorised signatories printed on documents | Master > Generals > Insurance Management > Signatories | None in production |  | Sponsor | Configuration |  | Open | Signatories_Upload_Template.xlsx
IN-12 | Reinsurance | Does the broker arrange reinsurance? Reinsurers and treaties | Master > Finance > Reinsurance Treaty | Minimum security rating A-; treaty approval required; retention target 65% |  | Processing Team lead | Discovery |  | Open | reinsurance.*; skip if not used
IN-13 | Direct bill | EWT the insurer withholds on direct-bill commission | Master > Finance > Taxation | WC139 10% |  | Accounting Manager | Configuration |  | Open | direct_bill.insurer_ewt_code
IN-14 | Direct bill | Commission debit note: title, remarks, due days, e-mail text | Master > Configuration (Billing, Collections & Credit) | Commission Debit Note; 30 days |  | Accounting Manager | Configuration |  | Open | direct_bill.debit_note_*
IN-15 | Reconciliation | Tolerance for remittance reconciliation differences | Master > Configuration (Remittance & Reconciliation) | PHP 0.50 |  | Accounting Manager | Configuration |  | Open | remittance.reconciliation_tolerance

## Products and LOB
ID | Topic | Question or configuration item | BrokerVerse screen | OOTB default | Client answer | Owner (broker) | Needed by | Due date | Status | Notes and setting key
PR-01 | Lines | Lines of business written; the three with the most premium | Master > Generals > Insurance Management > Line of Business | Philippine non-life lines delivered |  | Sales head | Discovery |  | Open | Number of lines drives the implementation fee
PR-02 | Products | Products per line, mapped to the delivered products | Master > Generals > Insurance Management > Product | Motor, CTPL, Fire, Marine Cargo, PA, CGL, Group EB, Surety Bond; travel, householder, micro-insurance, group PA, CAR, EAR, machinery breakdown, marine hull, money and securities |  | Processing Team lead | Discovery |  | Open | Product_Upload_Template.xlsx for additions
PR-03 | Products | Policy types per product | Master > Generals > Insurance Management > Product | For example Comprehensive, TPL, Own Damage / Theft; Residential, Commercial; Import, Domestic |  | Processing Team lead | Configuration |  | Open | Policy_Type_Upload_Template.xlsx
PR-04 | Products | Package or non-package classification per product | Master > Generals > Insurance Management > Product | Set per delivered product |  | Processing Team lead | Discovery |  | Open | Drives the placement journey
PR-05 | Products | Tax regime per product: VAT or premium tax | Master > Generals > Insurance Management > Product | As delivered per product |  | Accounting Manager | Discovery |  | Open | Confirm with each insurer
PR-06 | Covers | Covers and limits offered; excess bodily injury and property damage limits on motor | Master > Generals > Insurance Management > Cover | BI and PD limits PHP 100,000.00 to 500,000.00 |  | Processing Team lead | Configuration |  | Open | quote.bodily_injury_limits, quote.property_damage_limits
PR-07 | Journey | Placement journey per line: Request for Quotation, Quotation Slip, Placement Slip, Record Issued Policy | Master > Configuration (Sales, Quotations & Placement) | Motor: Quotation Slip required. Fire, IAR, Marine, Casualty, Engineering: Placement Slip required. Others optional |  | Processing Team lead | Discovery |  | Open | placement.journey
PR-08 | Motor | Confirm the motor tariff, CTPL 1-year and 3-year amounts per vehicle class | Product Configurator > Product Templates (MOT-003-2025) | 2025 tariff, confirmed 29 September 2026 |  | Processing Team lead | Configuration |  | Open | motor.pricing_template_code
PR-09 | Motor | Auto Passenger PA rates and limits | Product Configurator > Product Templates | Per seat from the motor template |  | Processing Team lead | Configuration |  | Open
PR-10 | Motor | Vehicle makes, models and variants to add | Master > Generals > Insurance Management > Vehicle | Toyota, Mitsubishi, Honda, Ford, Nissan, Hyundai, Suzuki, Isuzu with models |  | Processing Team lead | Mock load 1 |  | Open | Vehicle_* templates
PR-11 | KYC | Identifiers required before issue, per line | Master > Configuration (Policies, Endorsements & Renewals) | Motor: ID type, number, image, chassis, motor and plate number |  | Compliance officer | Discovery |  | Open | policy.kyc_required_fields
PR-12 | KYC | Accepted government ID documents | Master > Configuration (Policies, Endorsements & Renewals) | PhilSys ID, UMID, Passport, Driver's License, PRC ID, SSS ID, GSIS and others |  | Compliance officer | Discovery |  | Open | policy.kyc_id_types
PR-13 | Quick Quote | Package bundles and insurer rate tables for Quick Quote and Compare Insurers | Master > Finance > Package Bundles; Insurer Rate Tables | Delivered bundles |  | Sales head | Configuration |  | Open | packages.*
PR-14 | Rules | Acceptance rules and product approval workflows | Product Configurator > Acceptance Rules; Approval Workflows | Delivered rules |  | Processing Team lead | Configuration |  | Open
PR-15 | Documents | Policy schedule, quotation and endorsement layouts; wording to print | Product Configurator > Document Manager | Delivered layouts |  | Processing Team lead | Configuration |  | Open | Layout changes outside OOTB are change requests
PR-16 | Quotation | Quotation validity; maker-checker on quotations; approval link validity | Master > Configuration (Sales, Quotations & Placement) | 30 days; on; 168 hours |  | Sales head | Discovery |  | Open | limits.quote_validity_days, workflow.quote_maker_checker, quotations.approval_link_ttl_hours
PR-17 | Policy | Default policy term | Master > Configuration (Policies, Endorsements & Renewals) | 12 months |  | Processing Team lead | Discovery |  | Open | policies.default_term_months
PR-18 | Renewals | Renewal timetable: pipeline, notices, grace, reinstatement | Master > Configuration (Policies, Endorsements & Renewals) | Pipeline 90 days; notices 60, 30, 15 days; grace 30 days; reinstatement 90 days |  | Operations head | Discovery |  | Open | renewals.pipeline_days, limits.renewal_notice_days, renewals.grace_period_days, renewals.reinstatement_days
PR-19 | Renewals | Renewal pricing: claims loading, loyalty discount, maker-checker | Master > Configuration (Policies, Endorsements & Renewals) | Loading 10% (cap 30%); loyalty 2% (cap 10%); maker-checker on |  | Operations head | Discovery |  | Open | renewals.claims_loading_*, renewals.loyalty_discount_*
PR-20 | Claims | Claims controls: refuse claims on unpaid premium, check loss date, settlement maker-checker, SLA days, ageing | Master > Configuration (Claims) | On; on; on; 20 days; 7, 15, 30 days |  | Claims head | Discovery |  | Open | claims.block_unpaid_premium, claims.sla_days, claims.aging_thresholds
PR-21 | Packages | Pro-rata pricing of section endorsements on package policies | Master > Configuration (Sales, Quotations & Placement) | On |  | Processing Team lead | Discovery |  | Open | packages.endorsement_prorata
PR-22 | Prospects | Age limits for a prospect or client date of birth | Master > Configuration (Sales, Quotations & Placement) | 18 to 100 years |  | Sales head | Configuration |  | Open | leads.min_age_years, leads.max_age_years

## Commission Rates
ID | Topic | Question or configuration item | BrokerVerse screen | OOTB default | Client answer | Owner (broker) | Needed by | Due date | Status | Notes and setting key
CM-01 | Insurer commission | Commission rate by insurer, product or line, new or renewal, with effective dates | Master > Finance > Commission Rate Matrix | Fallback 15% |  | Accounting Manager | Configuration |  | Open | commission.default_rate; no upload template, entered on screen
CM-02 | Referrers | Referrers and sub-agents: name, payee type, TIN, bank account | Commission > Agents/Referrer Accounts | None in production |  | Accounting | Mock load 1 |  | Open | A referrer needs a bank account before payout (commission.require_bank_account)
CM-03 | Sharing | Sub-agent (comsub) share by level | Master > Configuration (Commission & Incentives) | Level 1 8%; level 2 5% |  | Sales head | Discovery |  | Open | commission.comsub_rate_by_level
CM-04 | Withholding | Withholding tax code per payee type | Master > Configuration (Commission & Incentives) | Agent WI515 5%; Sub-agent WI515 5%; External WC515 10% |  | Accounting Manager | Discovery |  | Open | commission.wht_code_by_type; confirm with the tax adviser
CM-05 | Payout rule | Commission payable only when the premium is fully paid | Master > Configuration (Commission & Incentives) | On; eligible automatically on full payment |  | Accounting Manager | Discovery |  | Open | commission.require_full_payment, commission.auto_eligible_on_full_payment
CM-06 | Commission master | Commission master records (codes) used by sales | Master > Generals > Commission | COM- series |  | Sales head | Configuration |  | Open
CM-07 | VAT | Is the broker VAT-registered; is commission quoted VAT-inclusive | Master > Configuration (Billing, Collections & Credit) | VAT-registered: yes; VAT-inclusive: no |  | Accounting Manager | Discovery |  | Open | direct_bill.broker_vat_registered, direct_bill.commission_vat_inclusive
CM-08 | Incentives | Incentive programmes for sales staff: basis, period, targets, payout | Master > Finance > Incentive Programs | None in production |  | Sales head | Configuration |  | Open | Skip if not used
CM-09 | Open balances | Commission due to referrers earned before go-live | Accounts > Disbursement | Part of the commission payable opening balance |  | Accounting | Mock load 1 |  | Open | Paid with payment vouchers

## Chart of Accounts
ID | Topic | Question or configuration item | BrokerVerse screen | OOTB default | Client answer | Owner (broker) | Needed by | Due date | Status | Notes and setting key
GL-01 | Chart | Adopt the delivered Philippine broker chart of accounts, or map the broker's chart to it | Master > Finance > Account Category; Main Account; Sub Account | Delivered chart of about 110 accounts |  | Accounting Manager | Discovery |  | Open | Chart_of_Accounts_Upload_Template.xlsx
GL-02 | Chart | Premium trust account and other bank GL accounts needed | Master > Finance > Main Account; Sub Account | Cash in Bank: Operating, E-wallet Clearing, Premium Trust, Payroll |  | Accounting Manager | Discovery |  | Open
GL-03 | Account determination | GL account for cash on hand | Master > Finance > Account Determination | 1101001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-04 | Account determination | GL account for cash in bank (default) | Master > Finance > Account Determination | 1102001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-05 | Account determination | GL account for petty cash fund | Master > Finance > Account Determination | 1103001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-06 | Account determination | GL account for premium receivable | Master > Finance > Account Determination | 1202001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-07 | Account determination | GL account for commission receivable | Master > Finance > Account Determination | 1203001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-08 | Account determination | GL account for agent receivable | Master > Finance > Account Determination | 1204001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-09 | Account determination | GL account for insurer refund receivable | Master > Finance > Account Determination | 1203002 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-10 | Account determination | GL account for employee advances | Master > Finance > Account Determination | 1205001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-11 | Account determination | GL account for input vat | Master > Finance > Account Determination | 1301001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-12 | Account determination | GL account for creditable withholding tax | Master > Finance > Account Determination | 1302001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-13 | Account determination | GL account for output vat | Master > Finance > Account Determination | 2204003 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-14 | Account determination | GL account for due to insurers | Master > Finance > Account Determination | 2201001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-15 | Account determination | GL account for commission payable | Master > Finance > Account Determination | 2203001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-16 | Account determination | GL account for withholding tax payable | Master > Finance > Account Determination | 2204001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-17 | Account determination | GL account for client refund payable | Master > Finance > Account Determination | 2205001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-18 | Account determination | GL account for supplier payable | Master > Finance > Account Determination | 2206001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-19 | Account determination | GL account for commission income | Master > Finance > Account Determination | 3201001 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-20 | Account determination | GL account for commission expense | Master > Finance > Account Determination | 4401010 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-21 | Account determination | GL account for write-off | Master > Finance > Account Determination | 4401009 |  | Accounting Manager | Configuration |  | Open | accounting.account.*
GL-22 | Account determination | Payable account per payee type | Master > Finance > Account Determination | Insurer 2201001; Client 2205001; Agent/Referrer 2203001; Supplier 2206001 |  | Accounting Manager | Configuration |  | Open | accounting.payable_account_by_payee
GL-23 | Account determination | Cash account per payment mode | Master > Finance > Account Determination | Cash 1101001; cheque, bank transfer, card 1102001; GCash and online 1102002 |  | Accounting Manager | Configuration |  | Open | accounting.cash_account_by_payment_mode
GL-24 | Posting rules | Review the posting rule of each business event; agree changes | Master > Finance > Posting Rules; Accounting Flow | Delivered rules |  | Accounting Manager | Configuration |  | Open | Changes approved by a second user in Configuration Approvals
GL-25 | Controls | Maker-checker on finance documents; journal approval; period close approval | Master > Configuration (Accounting & Tax) | All on |  | Accounting Manager | Discovery |  | Open | finance.maker_checker_enabled, journal.require_approval, accounting.period_close_requires_approval
GL-26 | Transaction codes | Transaction codes with GL accounts and user limits | Master > Finance > Transaction Code | Delivered codes |  | Accounting Manager | Configuration |  | Open | Transaction_Code_Upload_Template.xlsx
GL-27 | Write-off | Write-off reasons, GL account and maximum amount | Master > Finance > Account Determination | Delivered reasons |  | Accounting Manager | Configuration |  | Open | Write_off_Reason_Upload_Template.xlsx
GL-28 | Close | Month-end close checklist items | Master > Finance > Close Checklist | Delivered checklist incl. sub-ledger tie-out and bank reconciliation |  | Accounting Manager | Configuration |  | Open
GL-29 | Close | Recurring journals (rent, depreciation, accruals) | Accounts > Period End > Recurring Journals | None |  | Accounting | UAT |  | Open
GL-30 | Opening balances | Trial balance at the day before go-live and its date | Accounts > Period End > Period Management (Import opening balances) | None |  | Accounting Manager | Mock load 1 |  | Open | Opening_Balances_Upload_Template.xlsx
GL-31 | Currency | Currencies used and source of exchange rates | Master > Finance > Currency; Exchange Rate | PHP base; USD, EUR, SGD, JPY |  | Accounting Manager | Configuration |  | Open | Exchange_Rate_Upload_Template.xlsx
GL-32 | Receivables | Ageing buckets; receivable due days | Master > Configuration (Billing, Collections & Credit) | 30, 60, 90, 120 days; due in 30 days |  | Accounting Manager | Discovery |  | Open | limits.receivable_ageing_buckets, receivables.due_days
GL-33 | Collections | Credit days, overdue levels, reminder timing | Master > Configuration (Billing, Collections & Credit) | 30 days; 30 and 60 days; 7 days before, every 7 days |  | Accounting Manager | Discovery |  | Open | collections.*
GL-34 | Petty cash | Petty cash funds: custodian, amount, replenishment limit | Master > Finance > Petty Cash | None |  | Accounting Manager | Configuration |  | Open | PCF- codes
GL-35 | External ledger | Will a corporate ledger be kept in another package? Export needs | Reports > Financial Reports > Trial Balance; Journal | Ledger kept in BrokerVerse |  | Accounting Manager | Discovery |  | Open | Excel or CSV export; a direct interface is a change request

## Banks and Gateways
ID | Topic | Question or configuration item | BrokerVerse screen | OOTB default | Client answer | Owner (broker) | Needed by | Due date | Status | Notes and setting key
BK-01 | Bank accounts | Broker's bank accounts: bank, branch, account number, purpose (operating, premium trust, payroll), GL cash account | Master > Finance > Bank | Banks seeded: BDO, BPI, Metrobank, Land Bank, Security Bank, China Bank; no accounts |  | Accounting Manager | Mock load 1 |  | Open | Bank_Account_Upload_Template.xlsx
BK-02 | Statements | Statement export format per account and one sample statement | Master > Finance > Bank Statement Formats | BDO-SAMPLE, BPI-SAMPLE, MBT-SAMPLE, GENERIC |  | Accounting | Configuration |  | Open
BK-03 | Statements | Reconcile-from date per account | Master > Finance > Bank | Go-live date |  | Accounting Manager | Mock load 1 |  | Open | Older items stay on the old reconciliation
BK-04 | Statements | Bank transaction types: charges, interest, final tax, others | Master > Finance > Bank Transaction Types | Delivered types |  | Accounting | Configuration |  | Open
BK-05 | Payments in | How clients may pay | Master > Configuration (Billing, Collections & Credit) | Bank transfer, cheque, online, cash |  | Accounting Manager | Discovery |  | Open | policy.payment_capture_modes
BK-06 | Payments in | Default payment mode on receipts; on disbursements | Master > Configuration (Billing, Collections & Credit) | Bank transfer; cheque |  | Accounting | Configuration |  | Open | receipts.default_payment_mode, disbursements.default_payment_mode
BK-07 | Gateway | Online payment gateway to use: PayMongo, Dragonpay or none; merchant account owner | Master > Finance > Payment Gateways | PayMongo and Dragonpay off (sandbox mode); Sandbox gateway on (switch off in production) |  | Accounting Manager | Discovery |  | Open | Keys only in the secret store: PAYMONGO_*, DRAGONPAY_*
BK-08 | Gateway | Methods offered and fee handling (absorbed or charged) | Master > Finance > Payment Gateways | Absorb; PayMongo 2.5%; Dragonpay PHP 20.00 |  | Accounting Manager | Configuration |  | Open | Confirm with the merchant agreement
BK-09 | Gateway | Payment link validity; automatic official receipt on confirmed payment | Master > Configuration (Billing, Collections & Credit) | 72 hours; on |  | Accounting Manager | Configuration |  | Open | payments.link_validity_hours, payments.auto_receipt
BK-10 | Payments out | Transfer methods to insurers (InstaPay, PESONet, RTGS, cheque) and who executes them in the bank portal | Accounts > Remittance > Electronic Transfer | Recorded and approved in BrokerVerse; executed in the bank portal |  | Accounting Manager | Discovery |  | Open | Bank payment files are a change request
BK-11 | Payments out | Cheque series in use per account | Accounts > Disbursement | None |  | Accounting | Mock load 1 |  | Open
BK-12 | Remittance | Bank account used for remittance reconciliation | Master > Configuration (Remittance & Reconciliation) | Blank |  | Accounting | Configuration |  | Open | remittance.reconciliation_bank_account

## Numbering Series
ID | Topic | Question or configuration item | BrokerVerse screen | OOTB default | Client answer | Owner (broker) | Needed by | Due date | Status | Notes and setting key
NU-01 | Rules | Continue the old system's numbers at go-live? Next number per series | Master > Document Numbering | Counters start at 1; can be set to continue |  | Accounting Manager | Configuration |  | Open | Counters only move forward
NU-02 | Series | Lead: prefix, pattern and reset rule | Master > Document Numbering | LD, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code lead
NU-03 | Series | Quotation: prefix, pattern and reset rule | Master > Document Numbering | QT, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code quote
NU-04 | Series | Client Code: prefix, pattern and reset rule | Master > Document Numbering | CL, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code client
NU-05 | Series | Policy (when the insurer number is not given): prefix, pattern and reset rule | Master > Document Numbering | POL, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code policy
NU-06 | Series | Endorsement: prefix, pattern and reset rule | Master > Document Numbering | END, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code endorsement
NU-07 | Series | Renewal: prefix, pattern and reset rule | Master > Document Numbering | RN, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code renewal
NU-08 | Series | Renewal Quotation: prefix, pattern and reset rule | Master > Document Numbering | RQ, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code renewal_quote
NU-09 | Series | Renewal Batch: prefix, pattern and reset rule | Master > Document Numbering | RB, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code renewal_batch
NU-10 | Series | Win-back Campaign: prefix, pattern and reset rule | Master > Document Numbering | WB, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code campaign
NU-11 | Series | Claim: prefix, pattern and reset rule | Master > Document Numbering | CLM, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code claim
NU-12 | Series | Broker Slip: prefix, pattern and reset rule | Master > Document Numbering | BS, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code broker_slip
NU-13 | Series | Placement Slip: prefix, pattern and reset rule | Master > Document Numbering | PS, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code placement
NU-14 | Series | Insurer Offer: prefix, pattern and reset rule | Master > Document Numbering | OFR, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code insurer_offer
NU-15 | Series | Package Quotation: prefix, pattern and reset rule | Master > Document Numbering | PQ, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code package_quote
NU-16 | Series | Package Policy: prefix, pattern and reset rule | Master > Document Numbering | PKG, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code package_policy
NU-17 | BIR document | Official Receipt: prefix, pattern and reset rule; registered series (ATP or system-generated equivalent) | Master > Document Numbering | OR, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | Accounting Manager | Configuration |  | Open | Series code receipt; confirm with the tax adviser
NU-18 | Series | Receipt Transaction: prefix, pattern and reset rule | Master > Document Numbering | RT, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code receipt_txn
NU-19 | BIR document | Acknowledgement Receipt: prefix, pattern and reset rule; registered series (ATP or system-generated equivalent) | Master > Document Numbering | AR, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | Accounting Manager | Configuration |  | Open | Series code acknowledgement_receipt; confirm with the tax adviser
NU-20 | BIR document | Invoice / Bill: prefix, pattern and reset rule; registered series (ATP or system-generated equivalent) | Master > Document Numbering | INV, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | Accounting Manager | Configuration |  | Open | Series code invoice; confirm with the tax adviser
NU-21 | Series | Payment Link: prefix, pattern and reset rule | Master > Document Numbering | PL, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code payment_link
NU-22 | Series | Payment Voucher: prefix, pattern and reset rule | Master > Document Numbering | PV, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code voucher
NU-23 | Series | Disbursement Transaction: prefix, pattern and reset rule | Master > Document Numbering | DT, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code disbursement_txn
NU-24 | Series | Payable (Invoice List): prefix, pattern and reset rule | Master > Document Numbering | IL, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code invoice_list
NU-25 | Series | Petty Cash Transaction: prefix, pattern and reset rule | Master > Document Numbering | PC, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code petty_cash
NU-26 | Series | Petty Cash Request: prefix, pattern and reset rule | Master > Document Numbering | PCR, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code petty_cash_request
NU-27 | Series | Petty Cash Receipt: prefix, pattern and reset rule | Master > Document Numbering | PCRC, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code petty_cash_receipt
NU-28 | BIR document | Commission Debit Note: prefix, pattern and reset rule; registered series (ATP or system-generated equivalent) | Master > Document Numbering | DN, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | Accounting Manager | Configuration |  | Open | Series code commission_debit_note; confirm with the tax adviser
NU-29 | Series | Debit Note Collection: prefix, pattern and reset rule | Master > Document Numbering | DNC, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code dn_collection
NU-30 | Series | Journal Voucher: prefix, pattern and reset rule | Master > Document Numbering | JV, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code journal
NU-31 | Series | Month-end Close: prefix, pattern and reset rule | Master > Document Numbering | MEC, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code period_close
NU-32 | Series | Year-end Close: prefix, pattern and reset rule | Master > Document Numbering | YEC, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code year_end_close
NU-33 | Series | Recurring Journal: prefix, pattern and reset rule | Master > Document Numbering | RJV, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code recurring_journal
NU-34 | BIR document | BIR Form 2307: prefix, pattern and reset rule; registered series (ATP or system-generated equivalent) | Master > Document Numbering | CWT, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | Accounting Manager | Configuration |  | Open | Series code bir_2307; confirm with the tax adviser
NU-35 | Series | Bank Statement: prefix, pattern and reset rule | Master > Document Numbering | BST, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code bank_statement
NU-36 | Series | Bank Reconciliation: prefix, pattern and reset rule | Master > Document Numbering | BRC, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code bank_reconciliation
NU-37 | Series | Insurer Statement Reconciliation: prefix, pattern and reset rule | Master > Document Numbering | ISR, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code insurer_statement
NU-38 | Series | Remittance: prefix, pattern and reset rule | Master > Document Numbering | REM, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code remittance
NU-39 | Series | Direct / Agency Bill: prefix, pattern and reset rule | Master > Document Numbering | BIL, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code remittance_bill
NU-40 | Series | Remittance Batch: prefix, pattern and reset rule | Master > Document Numbering | BLK, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code remittance_batch
NU-41 | Series | Settlement: prefix, pattern and reset rule | Master > Document Numbering | SET, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code settlement
NU-42 | Series | Remittance Adjustment: prefix, pattern and reset rule | Master > Document Numbering | ADJ, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code adjustment
NU-43 | Series | Electronic Transfer: prefix, pattern and reset rule | Master > Document Numbering | TRF, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code transfer
NU-44 | Series | Remittance Statement: prefix, pattern and reset rule | Master > Document Numbering | STMT, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code statement
NU-45 | Series | Remittance Exception: prefix, pattern and reset rule | Master > Document Numbering | EXC, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code remittance_exception
NU-46 | Series | Remittance Notification: prefix, pattern and reset rule | Master > Document Numbering | NTF, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code remittance_notice
NU-47 | Series | Remittance Schedule: prefix, pattern and reset rule | Master > Document Numbering | SCH, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code remittance_schedule
NU-48 | Series | Remittance Report: prefix, pattern and reset rule | Master > Document Numbering | RPT, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code remittance_report
NU-49 | Series | Bank Transaction: prefix, pattern and reset rule | Master > Document Numbering | BNK, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code bank_txn
NU-50 | Series | Reinsurer: prefix, pattern and reset rule | Master > Document Numbering | RE, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code reinsurer
NU-51 | Series | Treaty: prefix, pattern and reset rule | Master > Document Numbering | TRT, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code treaty
NU-52 | Series | Cession: prefix, pattern and reset rule | Master > Document Numbering | CES, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code cession
NU-53 | Series | RI Recovery Claim: prefix, pattern and reset rule | Master > Document Numbering | RCL, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code ri_recovery
NU-54 | Series | Bordereau: prefix, pattern and reset rule | Master > Document Numbering | BDX, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code bordereau
NU-55 | Series | RI Reconciliation: prefix, pattern and reset rule | Master > Document Numbering | REC, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code ri_reconciliation
NU-56 | Series | Incentive Program: prefix, pattern and reset rule | Master > Document Numbering | INC, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code incentive_program
NU-57 | Series | Incentive Calculation: prefix, pattern and reset rule | Master > Document Numbering | CALC, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code incentive_calc
NU-58 | Series | Product Template: prefix, pattern and reset rule | Master > Document Numbering | TPL, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code product_template
NU-59 | Series | Data Subject Request: prefix, pattern and reset rule | Master > Document Numbering | DSR, {PREFIX}-{YYYY}-{SEQ}, width 5, yearly reset |  | System Administrator | Configuration |  | Open | Series code data_subject_request
NU-60 | Master codes | Commission Code: prefix and pattern | Master > Document Numbering | COM, {PREFIX}-{SEQ}, width 5, never reset |  | System Administrator | Configuration |  | Open | Series code commission_master
NU-61 | Master codes | Employee Code: prefix and pattern | Master > Document Numbering | EMP, {PREFIX}-{SEQ}, width 4, never reset |  | System Administrator | Configuration |  | Open | Series code employee
NU-62 | Master codes | Petty Cash Code: prefix and pattern | Master > Document Numbering | PCF, {PREFIX}-{SEQ}, width 3, never reset |  | System Administrator | Configuration |  | Open | Series code petty_cash_fund

## Approvals and Limits
ID | Topic | Question or configuration item | BrokerVerse screen | OOTB default | Client answer | Owner (broker) | Needed by | Due date | Status | Notes and setting key
AP-01 | Authority matrix | Approval limit: Quotation discount (percent), per role or named user | Master > Generals > User Management > Authority Matrix | Sales 10; Operations 10; Processing 15; Accounting Manager 25 |  | Sponsor | Configuration |  | Open | Transaction type quotation_discount; replace with the board-approved signing authority
AP-02 | Authority matrix | Approval limit: Policy issue (sum insured, PHP), per role or named user | Master > Generals > User Management > Authority Matrix | Sales 1,000,000.00; Operations 1,000,000.00; Processing 5,000,000.00; Accounting Manager no limit |  | Sponsor | Configuration |  | Open | Transaction type policy_issue; replace with the board-approved signing authority
AP-03 | Authority matrix | Approval limit: Return premium (PHP), per role or named user | Master > Generals > User Management > Authority Matrix | Operations 100,000.00; Processing 250,000.00; Accounting 250,000.00; Accounting Manager no limit |  | Sponsor | Configuration |  | Open | Transaction type return_premium; replace with the board-approved signing authority
AP-04 | Authority matrix | Approval limit: Claim settlement (PHP), per role or named user | Master > Generals > User Management > Authority Matrix | Claims 1,000,000.00; Accounting Manager no limit |  | Sponsor | Configuration |  | Open | Transaction type claim_settlement; replace with the board-approved signing authority
AP-05 | Authority matrix | Approval limit: Payment voucher (PHP), per role or named user | Master > Generals > User Management > Authority Matrix | Accounting 2,000,000.00; Accounting Manager no limit |  | Sponsor | Configuration |  | Open | Transaction type payment_voucher; replace with the board-approved signing authority
AP-06 | Authority matrix | Approval limit: Journal voucher (PHP), per role or named user | Master > Generals > User Management > Authority Matrix | Accounting 1,000,000.00; Accounting Manager no limit |  | Sponsor | Configuration |  | Open | Transaction type journal_voucher; replace with the board-approved signing authority
AP-07 | Authority matrix | Approval limit: Write-off (PHP), per role or named user | Master > Generals > User Management > Authority Matrix | Accounting 1,000.00; Accounting Manager 50,000.00 |  | Sponsor | Configuration |  | Open | Transaction type write_off; replace with the board-approved signing authority
AP-08 | Authority matrix | Approval limit: Commission payout (PHP), per role or named user | Master > Generals > User Management > Authority Matrix | Accounting 500,000.00; Accounting Manager no limit |  | Sponsor | Configuration |  | Open | Transaction type commission_payout; replace with the board-approved signing authority
AP-09 | Authority matrix | Approval limit: Petty cash (PHP), per role or named user | Master > Generals > User Management > Authority Matrix | Accounting 10,000.00; Accounting Manager 50,000.00 |  | Sponsor | Configuration |  | Open | Transaction type petty_cash; replace with the board-approved signing authority
AP-10 | Authority matrix | Approval limit: Remittance (PHP), per role or named user | Master > Generals > User Management > Authority Matrix | Accounting 1,000,000.00; Accounting Manager no limit |  | Sponsor | Configuration |  | Open | Transaction type remittance; replace with the board-approved signing authority
AP-11 | Authority matrix | Approval limit: Remittance settlement (PHP), per role or named user | Master > Generals > User Management > Authority Matrix | Accounting 1,000,000.00; Accounting Manager no limit |  | Sponsor | Configuration |  | Open | Transaction type remittance_settlement; replace with the board-approved signing authority
AP-12 | Authority matrix | Who approves a new or changed limit (second administrator) | Master > Generals > User Management > Authority Matrix | Another administrator must approve |  | Sponsor | Configuration |  | Open
AP-13 | Maker-checker | Quotation approval before sending to the client | Master > Configuration (Sales, Quotations & Placement) | On |  | Sales head | Discovery |  | Open | workflow.quote_maker_checker
AP-14 | Maker-checker | Renewal approval | Master > Configuration (Policies, Endorsements & Renewals) | On |  | Operations head | Discovery |  | Open | renewals.maker_checker
AP-15 | Maker-checker | Claim settlement approval; settle automatically on approval | Master > Configuration (Claims) | On; on |  | Claims head | Discovery |  | Open | claims.settlement_maker_checker, claims.auto_settle_on_approval
AP-16 | Maker-checker | Finance documents (payment vouchers, cheques, payouts, remittances, debit notes, petty cash) | Master > Configuration (Accounting & Tax) | On |  | Accounting Manager | Discovery |  | Open | finance.maker_checker_enabled
AP-17 | Maker-checker | Journal voucher approval | Master > Configuration (Accounting & Tax) | On |  | Accounting Manager | Discovery |  | Open | journal.require_approval
AP-18 | Maker-checker | Period close approval | Master > Configuration (Accounting & Tax) | On |  | Accounting Manager | Discovery |  | Open | accounting.period_close_requires_approval
AP-19 | Maker-checker | Reinsurance treaty approval | Master > Configuration (Remittance & Reconciliation) | On |  | Processing Team lead | Discovery |  | Open | reinsurance.treaty_requires_approval
AP-20 | Maker-checker | Posting rule and account determination changes | Master > Finance > Configuration Approvals | Second approver required |  | Accounting Manager | Discovery |  | Open
AP-21 | Remittance | Remittance approval levels by amount | Accounts > Remittance > Approval Workflow | Delivered levels |  | Accounting Manager | Discovery |  | Open | Confirm levels at the workshop
AP-22 | Credit control | Client credit limits; instalment plan rules | Accounts > Credit Control > Client Credit Limits; Instalment Plans | None |  | Accounting Manager | Configuration |  | Open
AP-23 | Notifications | Approval request notifications to approvers and decision notices to makers | Master > Configuration (Notifications & E-mail) | On |  | System Administrator | Configuration |  | Open | notification.approval_requests

## E-mail and Templates
ID | Topic | Question or configuration item | BrokerVerse screen | OOTB default | Client answer | Owner (broker) | Needed by | Due date | Status | Notes and setting key
EM-01 | Sending | Switch e-mail sending on (after the SMTP test) | Master > Configuration (Notifications & E-mail) | Off |  | System Administrator | UAT |  | Open | notification.email_enabled
EM-02 | Sending | Sender name and address | Master > Configuration (Notifications & E-mail) | BrokerVerse <connect@iortatechnxt.com>: replace |  | System Administrator | Configuration |  | Open | notification.from_address
EM-03 | Sending | Largest total attachment size per e-mail | Master > Configuration (Notifications & E-mail) | 10 MB |  | System Administrator | Configuration |  | Open | email.max_attachment_mb
EM-04 | Clients | E-mail the official receipt PDF automatically when recorded; subject and text | Master > Configuration (Billing, Collections & Credit) | Off; delivered text |  | Accounting Manager | Configuration |  | Open | receipts.email_on_record, receipts.email_subject, receipts.email_template
EM-05 | Clients | E-mail the premium invoice PDF automatically when issued; subject, text, payment instructions | Master > Configuration (Billing, Collections & Credit) | Off; delivered text |  | Accounting Manager | Configuration |  | Open | billing.email_on_issue, billing.email_*, billing.payment_instructions
EM-06 | Clients | Premium payment reminder: subject and text | Master > Configuration (Billing, Collections & Credit) | Delivered text |  | Accounting Manager | Configuration |  | Open | collections.email_subject, collections.email_template
EM-07 | Clients | Renewal notices: labels, subject and text; order enforced | Master > Configuration (Policies, Endorsements & Renewals) | First, Second, Final Notice; delivered text; order on |  | Operations head | Configuration |  | Open | renewals.notice_*
EM-08 | Clients | Claim status updates and renewal reminders on or off | Master > Configuration (Notifications & E-mail) | On; on |  | Operations head | Configuration |  | Open | notification.claim_status, notification.renewal_reminder
EM-09 | Insurers | Preliminary loss advice: subject and text | Master > Configuration (Claims) | Delivered text |  | Claims head | Configuration |  | Open | claims.pla_subject, claims.pla_template
EM-10 | Insurers | Commission debit note e-mail | Master > Configuration (Billing, Collections & Credit) | Delivered text |  | Accounting Manager | Configuration |  | Open | direct_bill.email_subject, direct_bill.email_body
EM-11 | Insurers | Remittance statement and agency bill e-mails | Master > Configuration (Remittance & Reconciliation) | Delivered text |  | Accounting Manager | Configuration |  | Open | remittance.statement_email_*, remittance.bill_email_*
EM-12 | Users | Password reset e-mail | Master > Configuration (Security & Access) | Delivered text; code valid 15 minutes |  | IT head | Configuration |  | Open | security.reset_email_*, security.reset_code_minutes
EM-13 | Documents | Claim letters: acknowledgement, discharge voucher, data sheet | Master > Configuration (Claims) | Delivered wording |  | Claims head | Configuration |  | Open | claims.documents
EM-14 | Documents | Footer on official receipts (BIR permit or ATP details) | Master > Configuration (Billing, Collections & Credit) | Empty |  | Accounting Manager | Configuration |  | Open | documents.receipt_footer
EM-15 | Documents | Payment instructions on billing statements | Master > Configuration (Billing, Collections & Credit) | Delivered text |  | Accounting Manager | Configuration |  | Open | documents.payment_instructions
EM-16 | Documents | Disclaimer on the insurer comparison given to the client | Master > Configuration (Sales, Quotations & Placement) | Delivered disclaimer |  | Compliance officer | Configuration |  | Open | packages.comparison_disclaimer
EM-17 | Documents | Note on acknowledgement receipts | Master > Configuration (Billing, Collections & Credit) | "This acknowledgement receipt is not an official receipt..." |  | Accounting Manager | Configuration |  | Open | documents.acknowledgement_receipt_note
EM-18 | Privacy | Privacy notice version recorded with consents | Master > Configuration (Data Retention, Privacy & Uploads) | 1.0 |  | DPO | Configuration |  | Open | privacy.notice_version

## Taxes and LGU
ID | Topic | Question or configuration item | BrokerVerse screen | OOTB default | Client answer | Owner (broker) | Needed by | Due date | Status | Notes and setting key
TX-01 | Premium taxes | DST on premium: method (12.5% or PHP 0.50 per PHP 4.00 unit, fraction rounded up) as each insurer applies it | Master > Finance > Premium Taxes & LGU Rates | Per unit, PHP 0.50 per PHP 4.00 (12.5%) |  | Accounting Manager | Discovery |  | Open | Rule DST
TX-02 | Premium taxes | VAT on premium for products under the VAT regime | Master > Finance > Premium Taxes & LGU Rates | 12% |  | Accounting Manager | Discovery |  | Open | Rule VAT
TX-03 | Premium taxes | Premium tax for products under the premium tax regime | Master > Finance > Premium Taxes & LGU Rates | 2% |  | Accounting Manager | Discovery |  | Open | Rule PT
TX-04 | Premium taxes | Fire service tax: lines to which it applies | Master > Finance > Premium Taxes & LGU Rates | 2% on fire lines (fire, IAR, householder) |  | Accounting Manager | Discovery |  | Open | Rule FST
TX-05 | LGU | LGT rate per city or municipality where clients are located | Master > Finance > Premium Taxes & LGU Rates | 0.75% when the location has no rate |  | Accounting Manager | Configuration |  | Open | Rule LGT and LGU tax rates
TX-06 | Other charges | Other charges on premium (for example notarial fee) | Master > Finance > Premium Taxes & LGU Rates | Notarial fee rule delivered switched off |  | Accounting Manager | Discovery |  | Open | Rule NOTARIAL
TX-07 | Tax codes | Confirm output and input VAT codes | Master > Finance > Taxation | VAT12-OUT, VAT12-IN, VAT0, VATEX |  | Accounting Manager | Configuration |  | Open | Confirm with the tax adviser
TX-08 | Tax codes | Confirm EWT codes and ATC used by the broker | Master > Finance > Taxation | WC139, WC140, WI139, WI140, WI515, WI516, WC515, WC158, WI158, WC160, WI160, WC100, WI100, WC120, WI010, WI011, WC010, WC011 |  | Accounting Manager | Configuration |  | Open | bir.atc_by_payee
TX-09 | Tax codes | Final withholding on bank interest | Master > Finance > Taxation | FWT-INT 20% |  | Accounting Manager | Configuration |  | Open
TX-10 | VAT status | VAT-registered or non-VAT (percentage tax) | Master > Configuration (Billing, Collections & Credit) | VAT-registered |  | Accounting Manager | Discovery |  | Open | direct_bill.broker_vat_registered; no percentage tax working paper
TX-11 | BIR forms | Registered name, address, TIN of the withholding agent for BIR forms | Master > Generals > Organization > Company | From the letterhead company |  | Accounting Manager | Configuration |  | Open | bir.* settings are a fallback only
TX-12 | BIR forms | Which BrokerVerse documents serve as registered invoices and receipts under the EOPT Act | Master > Document Numbering | INV, OR, DN series available |  | Accounting Manager | Discovery |  | Open | Decision with the tax adviser; registration is the broker's
TX-13 | BIR forms | Computerized accounting system registration status and plan | Not a system setting | Not applicable |  | Accounting Manager | Discovery |  | Open | Philippine Regulatory Compliance Matrix
TX-14 | BIR forms | SLSP: is the broker required to submit | Accounts > Tax > SLSP Sales; SLSP Purchases | Delivered reports |  | Accounting Manager | Discovery |  | Open
TX-15 | Fallbacks | Fallback tax rates used only when no rule exists | Master > Configuration (Accounting & Tax) | VAT 12%; DST 12.5%; LGT 0.75%; FST 2% |  | Accounting Manager | Configuration |  | Open | tax.vat_rate, tax.dst_rate, tax.lgt_rate, tax.fst_rate

## Data Migration Sources
ID | Topic | Question or configuration item | BrokerVerse screen | OOTB default | Client answer | Owner (broker) | Needed by | Due date | Status | Notes and setting key
DM-01 | Organisation | Company, branches, departments: source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Company_, Branch_, Department_Upload_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-02 | Organisation | Employee hierarchy, designations, employees: source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Hierarchy_, Designation_Upload_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-03 | Access | Users with one role each: source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Users_Provisioning_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-04 | Insurance | Insurers with commission rate, warranty days, remittance terms, billing mode: source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Insurance_Company_Upload_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-05 | Insurance | Lines of business, products, policy types, covers (only what is missing): source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Line_of_Business_, Product_, Policy_Type_, Cover_Upload_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-06 | Insurance | Vehicle brands, models, variants: source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Vehicle_* templates |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-07 | Insurance | Signatories: source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Signatories_Upload_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-08 | Finance | Chart of accounts: source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Chart_of_Accounts_Upload_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-09 | Finance | Banks and bank accounts: source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Bank_, Bank_Account_Upload_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-10 | Finance | Currencies and exchange rates: source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Currency_, Exchange_Rate_Upload_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-11 | Finance | Transaction codes, write-off reasons: source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Transaction_Code_, Write_off_Reason_Upload_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-12 | Open business | In-force policies and their clients at go-live (insurer at 100%; co-insured entered on screen): source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Policies_Upload_Template.xlsx (go-live mode) |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-13 | Open business | Open premium receivables at the day before go-live: source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Open_Items_Upload_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-14 | Open business | Trial balance at the day before go-live: source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Opening_Balances_Upload_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-15 | Open business | Amounts due to insurers on old bills (paid by payment voucher): source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Disbursements_Upload_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-16 | Open business | Commission due to referrers earned before go-live: source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Disbursements_Upload_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-17 | Open business | Open claims on in-force policies (registered on screen after go-live): source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | No template |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-18 | Optional | Prospects and quotations in progress: source system and table or file, record count, extract owner, cleansing needed | See the template Instructions sheet | Leads_, Quotations_Upload_Template.xlsx |  | Data owner | Mock load 1 |  | Open | Data Migration and Cutover Plan
DM-19 | Scope | Data the broker wants to migrate beyond the OOTB scope (expired policies, closed claims, history, documents) | Not applicable | Out of OOTB scope |  | Sponsor | Discovery |  | Open | Change request: PHP 240,000.00 per legacy source (Rate Card)
DM-20 | Volumes | In-force policies, clients, open bills, active referrers (counts) | Not applicable | Up to 20,000 rows per import file |  | Data owner | Mobilisation |  | Open | Larger books loaded in several files
DM-21 | Schedule | Dates of mock load 1, mock load 2 (and 3), final extract | Not applicable | Two mock loads (small), three (medium, large) |  | Project manager | Mobilisation |  | Open | Implementation Approach and Plan
DM-22 | Cutover | Freeze time of the old system and parallel run, if any | Not applicable | Freeze at close of the day before go-live |  | Sponsor | Discovery |  | Open

## Integrations
ID | Topic | Question or configuration item | BrokerVerse screen | OOTB default | Client answer | Owner (broker) | Needed by | Due date | Status | Notes and setting key
IG-01 | E-mail | SMTP mailbox: host, port (587, STARTTLS), user, who owns it | Environment variable SMTP_URL (secret store) | None |  | IT head | Configuration |  | Open | Test password reset and quotation approval link
IG-02 | E-mail | Mail domain records (SPF, DKIM) so e-mails are not marked as spam | Broker DNS | Not applicable |  | IT head | Configuration |  | Open
IG-03 | Bank | Bank statement file per account (format, frequency, who downloads) | Accounts > Bank Reconciliation (Import statement) | BDO, BPI, Metrobank, generic |  | Accounting | Configuration |  | Open
IG-04 | Bank | Bank transactions file for remittance reconciliation | Accounts > Remittance > Reconciliation (Import) | CSV template |  | Accounting | Configuration |  | Open | Remittance_Bank_Transactions_Template
IG-05 | Payment gateway | Merchant account, credentials and notification (webhook) address registration | Master > Finance > Payment Gateways | PayMongo, Dragonpay (sandbox) |  | Accounting Manager | UAT |  | Open | Sandbox test, then one live payment
IG-06 | Insurers | Files exchanged with each insurer: slips, placement orders, statements, debit notes | Placement Slips; Insurer Reconciliation; Direct Bill Processing | PDF, CSV, Excel and e-mail |  | Processing Team lead | Discovery |  | Open | Insurer APIs are change requests
IG-07 | Accounting | Corporate ledger or consolidation package to feed | Reports > Financial Reports | Excel or CSV export |  | Accounting Manager | Discovery |  | Open | Direct interface is a change request
IG-08 | Single sign-on | Is sign-in through the corporate directory required | Not delivered | BrokerVerse user names and passwords with two-step verification |  | IT head | Discovery |  | Open | Gap (CR) if required
IG-09 | SMS | SMS notifications to clients | Not delivered | E-mail only |  | Operations head | Discovery |  | Open | Gap (CR) if required
IG-10 | API | Other systems that will call the BrokerVerse API (owner, purpose) | API (OpenAPI and Postman collection) | Every call checked against the user permissions |  | IT head | Discovery |  | Open | API and Dependency Catalogue
IG-11 | Network | Office IP ranges, VPN or allow-listing needs; supported browsers | Hosting (WAF) | Current Chrome, Edge or Firefox |  | IT head | Mobilisation |  | Open
IG-12 | Monitoring | Who receives monitoring alarms and the monthly service report | Hosting | iorta TechNXT on-call |  | IT head | Configuration |  | Open | Production Support Approach and Standards

## Reports
ID | Topic | Question or configuration item | BrokerVerse screen | OOTB default | Client answer | Owner (broker) | Needed by | Due date | Status | Notes and setting key
RP-01 | Schedules | Scheduled jobs: confirm times and which are switched on | Master > Schedules | Renewal notices 06:00; Policy expiry 00:15; Quotation expiry 00:30; Receivable ageing 07:00; Daily reports 05:00; E-mail outbox every 5 minutes; Collection reminders 08:00; Housekeeping 02:45; Dormant accounts 01:45; Remittance schedules off |  | System Administrator | Configuration |  | Open | Asia/Manila time
RP-02 | Retention | Generated report retention | Master > Configuration (Data Retention, Privacy & Uploads) | 90 days |  | System Administrator | Configuration |  | Open | reports.retention_days
RP-03 | Gaps | Reports the broker uses today that are not in the catalogue (attach samples) | Reports > All Reports | Catalogue below |  | Sponsor | Discovery |  | Open | New report: change request
RP-04 | Regulators | Reports the broker submits to the IC and how they are prepared today | Reports > Financial Reports | No IC-format report |  | Compliance officer | Discovery |  | Open
RP-05 | Operational reports | Production Register: used? by whom, how often, any column or filter needs | Reports > Operational Reports > Production | Delivered |  | Report owner | UAT |  | Open | Report code production-register
RP-06 | Operational reports | Claims Position: used? by whom, how often, any column or filter needs | Reports > Operational Reports > Claims | Delivered |  | Report owner | UAT |  | Open | Report code claims-position
RP-07 | Operational reports | Renewal Retention: used? by whom, how often, any column or filter needs | Reports > Operational Reports > Renewal | Delivered |  | Report owner | UAT |  | Open | Report code renewal-retention
RP-08 | Operational reports | Remittance Summary: used? by whom, how often, any column or filter needs | Reports > Operational Reports > Remittance | Delivered |  | Report owner | UAT |  | Open | Report code remittance-summary
RP-09 | Operational reports | Broker Commission Statement: used? by whom, how often, any column or filter needs | Reports > Operational Reports > Broker Commission | Delivered |  | Report owner | UAT |  | Open | Report code commission-statement
RP-10 | Operational reports | Claims Ageing: used? by whom, how often, any column or filter needs | Reports > All Reports > Claims Ageing | Delivered |  | Report owner | UAT |  | Open | Report code claims-ageing
RP-11 | Operational reports | Lead Conversion Funnel: used? by whom, how often, any column or filter needs | Reports > All Reports > Lead Conversion Funnel | Delivered |  | Report owner | UAT |  | Open | Report code lead-conversion-funnel
RP-12 | Operational reports | Placement Pipeline: used? by whom, how often, any column or filter needs | Reports > All Reports > Placement Pipeline | Delivered |  | Report owner | UAT |  | Open | Report code placement-pipeline
RP-13 | Operational reports | Market Response: used? by whom, how often, any column or filter needs | Reports > All Reports > Market Response | Delivered |  | Report owner | UAT |  | Open | Report code market-response
RP-14 | Operational reports | Reinsurance Cession Register: used? by whom, how often, any column or filter needs | Reports > All Reports > Reinsurance Cession Register | Delivered |  | Report owner | UAT |  | Open | Report code cession-register
RP-15 | Operational reports | Co-insurance Register: used? by whom, how often, any column or filter needs | Reports > Financial Reports > Co-insurance Register | Delivered |  | Report owner | UAT |  | Open | Report code coinsurance-register
RP-16 | Financial reports | SOA / Premium Receivable: used? by whom, how often, any column or filter needs | Reports > Financial Reports > SOA/Premium Receivable | Delivered |  | Report owner | UAT |  | Open | Report code premium-receivable-soa
RP-17 | Financial reports | Collection Report: used? by whom, how often, any column or filter needs | Reports > Financial Reports > Collection Report | Delivered |  | Report owner | UAT |  | Open | Report code collections-summary
RP-18 | Financial reports | Receivables Ageing: used? by whom, how often, any column or filter needs | Reports > All Reports > Receivables Ageing (definition screen: Accounts > Collections > Aging Report) | Delivered |  | Report owner | UAT |  | Open | Report code collections-ageing
RP-19 | Financial reports | Commission Receivable – Direct Bill: used? by whom, how often, any column or filter needs | Reports > All Reports > Commission Receivable – Direct Bill (definition screen: Accounts > Remittance > Direct Bill Processing) | Delivered |  | Report owner | UAT |  | Open | Report code direct-bill-commission
RP-20 | Financial reports | Receipts Register: used? by whom, how often, any column or filter needs | Reports > All Reports > Receipts Register (definition screen: Accounts > Receipts) | Delivered |  | Report owner | UAT |  | Open | Report code receipts-register
RP-21 | Financial reports | Payables / Disbursement Register: used? by whom, how often, any column or filter needs | Reports > Financial Reports > Payables | Delivered |  | Report owner | UAT |  | Open | Report code disbursement-register
RP-22 | Financial reports | Journal Register: used? by whom, how often, any column or filter needs | Reports > Financial Reports > Journal | Delivered |  | Report owner | UAT |  | Open | Report code journal-register
RP-23 | Financial reports | Trial Balance: used? by whom, how often, any column or filter needs | Reports > Financial Reports > Trial Balance | Delivered |  | Report owner | UAT |  | Open | Report code trial-balance
RP-24 | Financial reports | Incentive Results: used? by whom, how often, any column or filter needs | Reports > All Reports > Incentive Results (definition screen: Accounts > Incentive > Reports) | Delivered |  | Report owner | UAT |  | Open | Report code incentive-results
RP-25 | Financial reports | Due to Insurers by Co-insurer: used? by whom, how often, any column or filter needs | Reports > Financial Reports > Due to Insurers by Co-insurer | Delivered |  | Report owner | UAT |  | Open | Report code due-to-insurers-by-coinsurer
RP-26 | Financial reports | Income Statement: used? by whom, how often, any column or filter needs | Reports > Financial Reports > Income Statement; Accounts > Period End > Financial Statements | Delivered |  | Report owner | UAT |  | Open | Report code income-statement
RP-27 | Financial reports | Balance Sheet: used? by whom, how often, any column or filter needs | Reports > Financial Reports > Balance Sheet; Accounts > Period End > Financial Statements | Delivered |  | Report owner | UAT |  | Open | Report code balance-sheet
RP-28 | Financial reports | Trial Balance (Opening / Movement / Closing): used? by whom, how often, any column or filter needs | Reports > Financial Reports > Trial Balance Movement | Delivered |  | Report owner | UAT |  | Open | Report code trial-balance-ocm
RP-29 | Financial reports | General Ledger Detail: used? by whom, how often, any column or filter needs | Reports > Financial Reports > General Ledger Detail | Delivered |  | Report owner | UAT |  | Open | Report code gl-detail
RP-30 | Financial reports | Aged Payables to Insurers: used? by whom, how often, any column or filter needs | Reports > Financial Reports > Aged Payables to Insurers | Delivered |  | Report owner | UAT |  | Open | Report code aged-payables-insurers
RP-31 | Financial reports | Month-End Close Status: used? by whom, how often, any column or filter needs | Reports > Financial Reports > Month-End Close Status; Accounts > Period End > Month-End Close | Delivered |  | Report owner | UAT |  | Open | Report code month-end-close-status
RP-32 | Tax reports (BIR) | VAT Summary: used? by whom, how often, any column or filter needs | Accounts > Tax > VAT Summary | Delivered |  | Report owner | UAT |  | Open | Report code bir-vat-summary
RP-33 | Tax reports (BIR) | SAWT - Summary Alphalist of Withholding Taxes: used? by whom, how often, any column or filter needs | Accounts > Tax > SAWT | Delivered |  | Report owner | UAT |  | Open | Report code bir-sawt
RP-34 | Tax reports (BIR) | QAP - Quarterly Alphalist of Payees: used? by whom, how often, any column or filter needs | Accounts > Tax > QAP | Delivered |  | Report owner | UAT |  | Open | Report code bir-qap
RP-35 | Tax reports (BIR) | SLSP - Summary List of Sales: used? by whom, how often, any column or filter needs | Accounts > Tax > SLSP Sales | Delivered |  | Report owner | UAT |  | Open | Report code bir-slsp-sales
RP-36 | Tax reports (BIR) | SLSP - Summary List of Purchases: used? by whom, how often, any column or filter needs | Accounts > Tax > SLSP Purchases | Delivered |  | Report owner | UAT |  | Open | Report code bir-slsp-purchases
RP-37 | Reconciliation reports | Bank Reconciliation Statement: used? by whom, how often, any column or filter needs | Accounts > Bank Reconciliation > Reconciliation Statement Report | Delivered |  | Report owner | UAT |  | Open | Report code bank-reconciliation-statement
RP-38 | Reconciliation reports | Outstanding Cheques: used? by whom, how often, any column or filter needs | Accounts > Bank Reconciliation > Outstanding Cheques | Delivered |  | Report owner | UAT |  | Open | Report code bank-outstanding-cheques
RP-39 | Reconciliation reports | Deposits in Transit: used? by whom, how often, any column or filter needs | Accounts > Bank Reconciliation > Deposits in Transit | Delivered |  | Report owner | UAT |  | Open | Report code bank-deposits-in-transit
RP-40 | Reconciliation reports | Unmatched Bank Lines: used? by whom, how often, any column or filter needs | Accounts > Bank Reconciliation > Unmatched Bank Lines | Delivered |  | Report owner | UAT |  | Open | Report code bank-unmatched-lines
RP-41 | Reconciliation reports | Bank Book: used? by whom, how often, any column or filter needs | Accounts > Bank Reconciliation > Bank Book | Delivered |  | Report owner | UAT |  | Open | Report code bank-book
RP-42 | Management reports | Premium by Product / Month / Insurer: used? by whom, how often, any column or filter needs | Reports > All Reports > Premium by Product / Month / Insurer (definition screen: Dashboard > Executive Dashboard > Reports) | Delivered |  | Report owner | UAT |  | Open | Report code premium-by-product
RP-43 | Management reports | New Business vs Renewals: used? by whom, how often, any column or filter needs | Reports > All Reports > New Business vs Renewals (definition screen: Dashboard > Executive Dashboard > Reports) | Delivered |  | Report owner | UAT |  | Open | Report code new-vs-renewal