## Instructions
BrokerVerse Fit-Gap Register
One line per requirement found in the discovery workshops. Each line is classed, owned and decided. The register is signed by the process owners at the end of discovery (Small week 2, Medium week 3, Large week 5) and is then kept up to date until hypercare exit. Lines marked Example show how a line is filled in; delete them before the first workshop.
Item | Guidance
Requirement ID | FG-<area code>-<number>, for example FG-ACC-012. Never reuse an ID; a dropped line keeps its ID with status Withdrawn.
Area | The process area of the discovery workshops (list on the Lists sheet).
Requirement | What the broker needs, in its own words, with the volume or rule that matters.
Classification | Fit: delivered as it is. Configure: met by a setting or master data. Procedure: the broker changes how it works (workaround). Gap: needs a change to the product.
Solution | For Fit and Configure: the screen, setting or master (for example Master > Configuration > Billing, Collections & Credit). For Procedure: the new way of working, which goes into training. For Gap: the proposed change.
CR reference | For a Gap only: the change request number (Change Request Procedure and Form). A Gap is not in the go-live scope unless the steering committee approves it.
Effort | For Configure: hours of configuration. For Gap: the estimate in person-days from the change request.
Priority | Must have for go-live, Should have, Could have (after go-live).
Owner | One named person of the broker or of iorta TechNXT who closes the line.
Status | Open, Under analysis, Decided, Configured, Closed, Withdrawn.
Decision date | The date the class and solution were agreed (workshop or steering committee).
Decided by | The process owner, or the steering committee for a Gap.
Summary | The counts at the top of the Register sheet update themselves; report them in the weekly status report.

## Register
Lines by classification: | Fit |  | Configure |  | Procedure |  | Gap
Requirement ID | Area | Requirement | Classification | Solution | CR reference | Effort | Priority | Owner | Status | Decision date | Decided by | Remarks
FG-ACC-001 | Accounting and tax | Example. VAT-registered broker: output VAT on commission debit notes at 12%. | Fit | Delivered: direct bill debit notes add VAT at the tax code direct_bill.commission_vat_code (VAT12-OUT). |  |  | Must have | [Accounting Manager] | Decided |  | [name] | Example: delete
FG-BIL-002 | Billing and collection | Example. Official receipts e-mailed to the client with the PDF when recorded. | Configure | Switch on receipts.email_on_record (Master > Configuration > Billing, Collections & Credit > Receipts); SMTP mailbox set. |  | 1 hour | Should have | [System Administrator] | Decided |  | [name] | Example: delete
FG-REG-003 | Regulatory reporting | Example. Quarterly report to the Insurance Commission in its prescribed format. | Gap | Figures from the financial statements and production reports; a report in the IC format needs a change request. | CR-[number] | [days] | Could have | [Compliance officer] | Under analysis |  | Steering committee | Example: delete
FG-REM-004 | Remittance | Example. Remittances above PHP 1,000,000.00 approved by the Accounting Manager. | Configure | Authority Matrix, transaction type Remittance approval: Accounting PHP 1,000,000.00, Accounting Manager without limit (delivered default). |  | 0.5 hour | Must have | [Accounting Manager] | Decided |  | [name] | Example: delete
FG-POL-005 | Policy and servicing | Example. Brokers send the policy schedule by courier only. | Procedure | Print from Operations > Policy > Policy detail > Policy schedule; procedure added to the Operations training. |  |  | Should have | [Operations head] | Decided |  | [name] | Example: delete

## Lists
Area | Classification | Priority | Status
Organisation and users | Fit | Must have | Open
Sales and quotation | Configure | Should have | Under analysis
Placement | Procedure | Could have | Decided
Policy and servicing | Gap |  | Configured
Claims |  |  | Closed
Renewals |  |  | Withdrawn
Billing and collection
Remittance
Commission and incentives
Accounting and tax
Period end
Bank and insurer reconciliation
Reinsurance
Reports and dashboards
Regulatory reporting
Data privacy
Integrations
Data migration
Security and access
Hosting and operations