## Read me
BrokerVerse OOTB Implementation Plan
Companion workbook of the BrokerVerse Implementation Approach and Plan, version 1.0, 03 October 2026, iorta TechNXT.
Sheets
Small (8 weeks): one office, up to 25 users, up to 5,000 in-force policies (planning assumption).
Medium (12 weeks): up to 3 offices, 26 to 75 users, up to 25,000 in-force policies (planning assumption).
Large (16 to 20 weeks): more than 3 offices, more than 75 users, more than 25,000 in-force policies (planning assumption).
RACI: R = Responsible, A = Accountable (one per activity), C = Consulted, I = Informed.
Notes
The size is confirmed by the steering committee at mobilisation once data volumes are known.
Hypercare extends to cover the first month-end close when the close falls after the planned hypercare exit.
The plan assumes an out-of-the-box implementation: configuration only, no customisation.

## Small
BrokerVerse OOTB implementation plan: Small (8 weeks)
Shaded cells are the weeks in which the phase runs. Week 1 starts on the kick-off date.
Phase | Main activities | Start week | End week | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
Mobilisation | Kick-off, governance, data requests | 1 | 1
Discovery and fit-gap | Workshops, configuration workbook, fit-gap register | 1 | 2
Environment set-up | Test and production environments, backups, monitoring | 1 | 2
Configuration | Masters, products, rates, CoA, posting rules, numbering, approvals | 2 | 4
Data migration | Mock load 1 (wk 3), mock load 2 / rehearsal (wk 5), final load (wk 6) | 3 | 6
Integrations | E-mail, bank statement formats, payment gateway sandbox | 3 | 4
Training | Train-the-trainer (wk 4), end-user training (wk 5) | 4 | 5
System integration test | End-to-end flows across roles | 4 | 4
User acceptance test | UAT scripts with the broker data; sign-off | 5 | 6
Cutover | Freeze, final extract and loads, reconciliation, go/no-go | 6 | 6
Go-live | First day of transactions in BrokerVerse | 7 | 7 | [6 empty] | GO
Hypercare | Daily then weekly support; handover | 7 | 8
Milestones | Diamond = milestone in that week (text below) |  |  | ◆ | ◆ | ◆ | ◆ | ◆ | ◆ | ◆ | ◆
Week | Milestone
W1 | Kick-off
W2 | Config workbook signed
W3 | Mock 1 reconciled
W4 | SIT exit
W5 | Mock 2 reconciled
W6 | UAT sign-off; go/no-go
W7 | Go-live
W8 | Hypercare exit

## Medium
BrokerVerse OOTB implementation plan: Medium (12 weeks)
Shaded cells are the weeks in which the phase runs. Week 1 starts on the kick-off date.
Phase | Main activities | Start week | End week | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Mobilisation | Kick-off, governance, data requests | 1 | 1
Discovery and fit-gap | Workshops, configuration workbook, fit-gap register | 2 | 3
Environment set-up | Test and production environments, backups, monitoring | 1 | 2
Configuration | Masters, products, rates, CoA, posting rules, numbering, approvals | 3 | 6
Data migration | Mapping (wk 4), mock 1 (wk 5), mock 2 (wk 7), mock 3 / rehearsal and final load (wk 9) | 4 | 9
Integrations | E-mail (wk 5), bank statement formats and payment gateway (wk 6) | 5 | 6
Training | Train-the-trainer (wk 7), end-user training (wk 8 to 9) | 7 | 9
System integration test | Two cycles | 6 | 7
User acceptance test | Two cycles; sign-off | 8 | 9
Cutover | Freeze, final extract and loads, reconciliation, go/no-go | 9 | 9
Go-live | First day of transactions in BrokerVerse | 10 | 10 | [9 empty] | GO
Hypercare | Daily then weekly support; first close; handover | 10 | 12
Milestones | Diamond = milestone in that week (text below) |  |  | ◆ | ◆ | ◆ |  | ◆ | ◆ | ◆ |  | ◆ | ◆ |  | ◆
Week | Milestone
W1 | Kick-off
W2 | Environments ready
W3 | Config workbook signed
W5 | Mock 1 reconciled
W6 | Configuration complete
W7 | SIT exit; mock 2
W9 | UAT sign-off; go/no-go
W10 | Go-live
W12 | Hypercare exit

## Large
BrokerVerse OOTB implementation plan: Large (16 to 20 weeks)
Shaded cells are the weeks in which the phase runs. Week 1 starts on the kick-off date.
Phase | Main activities | Start week | End week | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
Mobilisation | Kick-off, governance, data requests, plan baselined | 1 | 2
Discovery and fit-gap | Workshops, configuration workbook, fit-gap register | 2 | 5
Environment set-up | Test and production environments, backups, monitoring | 2 | 3
Configuration | Masters, products, rates, CoA, posting rules, numbering, approvals | 4 | 9
Data migration | Mapping (wk 6), mocks 1 to 4 (wk 7, 10, 13, 14), final load (wk 14) | 6 | 14
Integrations | E-mail (wk 6), bank statement formats and payment gateway (wk 8) | 6 | 8
Training | Train-the-trainer (wk 10 to 11), end-user training (wk 12 to 13) | 10 | 13
System integration test | Two cycles; exit report | 9 | 11
User acceptance test | Two cycles; sign-off | 12 | 13
Cutover | Rehearsal, freeze, final extract and loads, reconciliation, go/no-go | 14 | 14
Go-live | All branches on one go-live date | 15 | 15 | [14 empty] | GO
Hypercare | First remittance, close and BIR cycle; handover | 15 | 20
Milestones | Diamond = milestone in that week (text below) |  |  | ◆ | ◆ | ◆ |  | ◆ |  | ◆ |  | ◆ |  | ◆ |  | ◆ | ◆ | ◆ |  |  | ◆ |  | ◆
Week | Milestone
W1 | Kick-off
W2 | Plan baselined
W3 | Environments ready
W5 | Config workbook signed
W7 | Mock 1 reconciled
W9 | Configuration complete
W11 | SIT exit
W13 | UAT sign-off
W14 | Go/no-go
W15 | Go-live
W18 | First close (typical)
W20 | Hypercare exit
16-week variant: discovery ends wk 4, configuration wk 8, three mock loads, go-live start of wk 13, hypercare wk 13 to 16.

## RACI
RACI: iorta TechNXT and the broker
R = Responsible, A = Accountable, C = Consulted, I = Informed.
Phase | Activity | iorta TechNXT PM | iorta TechNXT consultants | iorta TechNXT technical / DevOps | Broker sponsor | Broker PM | Broker key users / process owners | Broker IT / System Administrator | Broker Accounting Manager
Mobilisation | Project charter and baselined plan | R | C | C | A | R | I | I | I
Mobilisation | Governance set-up (steering committee, status, RAID log) | R | I | I | A | R | I | I | I
Mobilisation | Data request list issued and tracked | R | C | C | I | A | C | C | C
Discovery and fit-gap | Discovery workshops | A | R | I | I | R | R | C | R
Discovery and fit-gap | Configuration workbook | A | R | I | I | C | C | C | C
Discovery and fit-gap | Configuration decisions | C | R | I | I | A | R | C | R
Discovery and fit-gap | Fit-gap register sign-off | R | R | I | A | R | C | I | C
Environment set-up | Test and production environments | A | I | R | I | I | I | C | I
Environment set-up | Backups, restore test, monitoring | A | I | R | I | I | I | C | I
Configuration | Company, branches, users and security settings | A | R | C | I | I | C | R | I
Configuration | Insurers, commission, products, motor tariff | A | R | I | I | C | R | C | C
Configuration | Tax codes, premium taxes and LGU rates | A | R | I | I | C | C | I | R
Configuration | Chart of accounts, account determination, posting rules | A | R | I | I | C | C | I | R
Configuration | Document numbering (OR and invoice series per ATP) | A | R | I | I | C | C | C | R
Configuration | Approvals, maker-checker, authority matrix | A | R | I | I | C | R | C | R
Configuration | Schedules, e-mail texts, notifications | A | R | C | I | I | C | R | I
Data migration | Extraction from the old system | I | C | I | I | A | R | R | C
Data migration | Mapping to the upload templates | A | R | C | I | C | R | C | C
Data migration | Data cleansing | I | C | I | I | A | R | R | R
Data migration | Mock loads | A | R | R | I | C | C | C | C
Data migration | Reconciliation of counts and totals | A | R | C | I | C | R | I | R
Data migration | Sign-off of opening balances and open items | C | C | I | I | C | C | I | A
Integrations | SMTP mailbox and credentials | I | I | R | I | C | I | A | I
Integrations | Bank statement formats | A | R | C | I | I | R | C | C
Integrations | Payment gateway merchant account and credentials | C | I | R | I | C | I | A | C
Training | Train-the-trainer | A | R | I | I | C | R | C | C
Training | End-user training | C | C | I | I | A | R | C | C
Training | Assessment | C | R | I | I | A | R | I | I
System integration test | SIT execution and defect fixing | A | R | R | I | I | C | I | I
User acceptance test | UAT execution | C | C | I | I | A | R | R | R
User acceptance test | UAT sign-off | C | C | I | A | R | R | C | R
Cutover | Freeze of the old system and final extract | C | C | I | I | A | R | R | R
Cutover | Final loads and reconciliation | A | R | R | I | C | R | C | R
Cutover | Go/no-go decision | C | C | C | A | R | C | C | C
Go-live and hypercare | Go-live communication | C | I | I | A | R | C | C | I
Go-live and hypercare | Hypercare issue handling | A | R | R | I | R | C | R | C
Go-live and hypercare | First month-end close | C | R | C | I | I | R | I | A
Go-live and hypercare | Handover to production support | A | R | R | I | C | I | R | I
Change control | Change request impact assessment | A | R | R | I | C | C | C | C
Change control | Change request approval | C | I | I | A | R | C | C | C