## Instructions
BrokerVerse RAID Log
One shared log of risks, assumptions, issues and dependencies, kept by the iorta TechNXT project manager and reviewed in every weekly status meeting. Items rated High go to the steering committee. The risks and dependencies pre-filled from the Implementation Approach and Plan are typical of a BrokerVerse implementation: keep, change or close them at mobilisation.
Item | Guidance
ID | R-nnn, A-nnn, I-nnn or D-nnn with a running number. Never reuse an ID.
Probability (risks) | 1 Rare (under 10%), 2 Unlikely (10 to 30%), 3 Possible (30 to 50%), 4 Likely (50 to 80%), 5 Almost certain (over 80%).
Impact (risks and issues) | 1 Negligible, 2 Minor (a task slips), 3 Moderate (a milestone slips up to one week), 4 Major (go-live or budget at risk), 5 Severe (go-live missed, compliance or data loss).
Score and rating | Score = probability x impact. High: 15 to 25. Medium: 8 to 14. Low: 1 to 7. Calculated on the sheet; do not type over the formula.
Issue priority | An issue has happened. Priority follows impact: 4 or 5 High, 3 Medium, 1 or 2 Low.
Assumptions | Each assumption has a date by which it must be validated; an assumption found false becomes an issue or a risk.
Dependencies | What the project needs from someone outside the team (the broker, an insurer, a bank, the hosting provider), by when, and its state.
Status | Open, In progress, Closed. Fill the closure date and keep closed items on the sheet.
Summary | The Summary sheet counts open items by type and rating for the status report and the steering committee.

## Summary
RAID summary (open and in progress items)
Type | High | Medium | Low | Open total
Risks
Issues
Assumptions
Dependencies late or at risk
Risk matrix: open risks by probability (rows) and impact (columns)
Probability \ Impact | 1 | 2 | 3 | 4 | 5
5
4
3
2
1

## Risks
ID | Risk | Cause | Effect | Category | Owner | Probability | Impact | Score | Rating | Mitigation | Due date | Status | Raised on | Closed on
R-001 | Data arrives late or incomplete | Extracts from the old system not ready | Mock loads slip; go-live moves | Data | [owner] | 4 | 4 |  |  | Data requests in week 1; templates handed out at kick-off; data readiness tracked weekly; steering committee escalation after one week of delay |  | Open
R-002 | Poor data quality in the old system | Duplicates, missing fields, old balances | Rejected rows; receivables or balances do not reconcile | Data | [owner] | 3 | 4 |  |  | Two to four mock loads with reconciliation; the broker cleanses at source; rejected-row reports from each upload |  | Open
R-003 | Requests for customisation | Old system habits; new wishes | Scope and timeline grow | Scope | [owner] | 3 | 4 |  |  | Configure-first principle; fit-gap classes; change request process with steering committee approval |  | Open
R-004 | Key users unavailable | Business as usual takes priority | Decisions late; weak UAT and training | People | [owner] | 3 | 3 |  |  | Named key users with committed time; backups named; workshops scheduled at kick-off |  | Open
R-005 | Opening balances and open items do not agree | Cut-off differences | Ledger wrong from day one | Data | [owner] | 2 | 5 |  |  | Premiums Receivable balance equals the open item total; Due to Insurers reconciled to insurer statements; Accounting Manager signs off |  | Open
R-006 | Tax rates or ATC not confirmed | Tax adviser not engaged in time | Wrong VAT or withholding | Compliance | [owner] | 2 | 4 |  |  | Tax adviser review in the configuration phase; VAT Summary checked in UAT |  | Open
R-007 | Official receipt numbering out of line with the Authority to Print | Last numbers not supplied | Compliance exposure | Compliance | [owner] | 2 | 4 |  |  | Numbering set from the last number used; checked in UAT |  | Open
R-008 | E-mail or payment gateway credentials late | Provider onboarding | Approval links, receipts by e-mail, password resets and online payments not working | Integration | [owner] | 3 | 3 |  |  | Requested in mobilisation; the system works without the gateway; sandbox first |  | Open
R-009 | Users not ready at go-live | Training too early or skipped | Errors and slow work | People | [owner] | 2 | 3 |  |  | Role-based training, assessment, floor walkers in the first week |  | Open
R-010 | First month-end close outside hypercare | Go-live late in the month | Close issues found late | Schedule | [owner] | 2 | 3 |  |  | Hypercare extends to the first close |  | Open

## Assumptions
ID | Assumption | Basis | Effect if false | Owner | Validate by | Validated | Status | Remarks
A-001 | The size of the implementation (Small, Medium or Large) agreed at mobilisation stays valid once the data volumes are known. | Implementation Approach and Plan, sizing | Plan and price re-baselined | [PM] |  |  | Open
A-002 | The broker provides its SMTP mailbox before the integrations phase. | Dependencies on the broker | E-mails stay queued in the outbox | [IT head] |  |  | Open
A-003 | The delivered chart of accounts is used with the accountant's mapping, not replaced. | Configure-first principle | Posting rules and account determination redone | [Accounting Manager] |  |  | Open

## Issues
ID | Issue | Effect | Category | Owner | Impact | Priority | Action | Due date | Status | Raised on | Closed on | From risk
I-001 | [Example: bank statement export of one bank does not match the delivered formats] | [Bank reconciliation not testable in SIT] | Integration | [owner] | 3 |  | [Add an insurer or bank statement format in Master > Finance] |  | Open

## Dependencies
ID | Dependency | Provided by | Needed for | Needed by | Owner | State | Remarks
D-001 | Named project manager, key users and Accounting Manager | Broker | Mobilisation | Week 1 | [owner] | On track
D-002 | Insurer list and agreements, commission and referrer rates, product list | Broker | Configuration | End of discovery | [owner] | On track
D-003 | Chart of accounts and the accountant's mapping decisions | Broker | Ledger configuration | Start of configuration | [owner] | On track
D-004 | BIR Authority to Print or registered series; last numbers used | Broker | Document numbering | Configuration | [owner] | On track
D-005 | SMTP mailbox and credentials; payment gateway merchant account | Broker | Integrations | Integrations phase | [owner] | On track
D-006 | One recent statement export per bank account | Broker | Bank reconciliation formats | Integrations phase | [owner] | On track
D-007 | In-force policy, open receivable and trial balance extracts in the templates | Broker | Mock loads and cutover | Each mock load | [owner] | On track
D-008 | User list with roles and e-mail addresses | Broker | Training and go-live | Two weeks before training | [owner] | On track
D-009 | UAT testers and sign-off authority | Broker | UAT | UAT phase | [owner] | On track
D-010 | Production environment provisioned and backups tested | Hosting provider | Go-live | Before mock load 2 | [owner] | On track

## Lists
Status | Score | Category | Priority | Dependency state
Open | 1 | Scope | High | On track
In progress | 2 | Schedule | Medium | At risk
Closed | 3 | Data | Low | Late
| 4 | People |  | Delivered
| 5 | Technical
Integration
Compliance
Commercial
Hosting